## Sheet1
| Project | MW | Zero Date | State | Scope | Region | Customer | PROJECT START_Schedule | PROJECT START_Schedule_Exp/Actual | SITE OPENING_Schedule | SITE OPENING_Schedule_Exp/Actual | CVL START_Schedule | CVL START_Schedule_Exp/Actual | BOILER ERECTION START_Schedule | BOILER ERECTION START_Schedule_Exp/Actual | DRUM LIFTING_Schedule | DRUM LIFTING_Schedule_Exp/Actual | CEILING GIRDER/SEPERATOR ERECTION COMPLETION_Schedule | CEILING GIRDER/SEPERATOR ERECTION COMPLETION_Schedule_Exp/Actual | HYDRAULIC TEST_Schedule | HYDRAULIC TEST_Schedule_Exp/Actual | BOILER LIGHT UP_Schedule | BOILER LIGHT UP_Schedule_Exp/Actual | ALKALI BOIL OUT COMPLETION_Schedule | ALKALI BOIL OUT COMPLETION_Schedule_Exp/Actual | EDTA START_Schedule | EDTA START_Schedule_Exp/Actual | EDTA COMPLETION_Schedule | EDTA COMPLETION_Schedule_Exp/Actual | STEAM BLOWING START_Schedule | STEAM BLOWING START_Schedule_Exp/Actual | STEAM BLOWING COMPLETION_Schedule | STEAM BLOWING COMPLETION_Schedule_Exp/Actual | NORMALIZATION_Schedule | NORMALIZATION_Schedule_Exp/Actual | CONDENSER ERECTION START_Schedule | CONDENSER ERECTION START_Schedule_Exp/Actual | TURBINE ERECTION START_Schedule | TURBINE ERECTION START_Schedule_Exp/Actual | TG BOX UP_Schedule | TG BOX UP_Schedule_Exp/Actual | OIL FLUSHING START_Schedule | OIL FLUSHING START_Schedule_Exp/Actual | OIL FLUSHING COMPLETION_Schedule | OIL FLUSHING COMPLETION_Schedule_Exp/Actual | BARRING GEAR_Schedule | BARRING GEAR_Schedule_Exp/Actual | ROLLING_Schedule | ROLLING_Schedule_Exp/Actual | SYNCHRONISATION_Schedule | SYNCHRONISATION_Schedule_Exp/Actual | FULL LOAD_Schedule | FULL LOAD_Schedule_Exp/Actual | CAPACITY ADDITION_Schedule | CAPACITY ADDITION_Schedule_Exp/Actual | COMMERCIAL OPERATION DECLARATION_Schedule | COMMERCIAL OPERATION DECLARATION_Schedule_Exp/Actual | TRIAL OPERATION COMPLETION_Schedule | TRIAL OPERATION COMPLETION_Schedule_Exp/Actual | HAND OVER_Schedule | HAND OVER_Schedule_Exp/Actual | BES_Sch_Duration | BES_Act_Duration | FULL LOAD_Schedule_Duration
21 | SIPAT-5(500 MW) | 500 | 2003-12-15 | 5 | 0 | 3 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2005-03-15 | 2005-03-30 | 15-08-2005 | 07-10-2005 | N.A. | N.A. | 15-07-2006 | 27-12-2006 | 15-01-2007 | 21-11-2007 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 15-03-2007 | 15-02-2008 | N.A. | N.A. | 15-12-2005 | 05-04-2007 | N.A. | N.A. | 15-01-2007 | 06-12-2007 | N.A. | N.A. | 15-03-2007 | 10-07-2008 | 31-03-2007 | 06-08-2008 | N.A. | N.A. | 14-05-2007 | 13-08-2008 | 2007-09-14 | 27-12-2008 | N.A. | N.A. | 14-09-2007 | 27-12-2008 | 14-09-2007 | 31-12-2008 | N.A. | N.A. | 456 | 471 | 1369
22 | TROMBAY-8(250 MW) | 250 | 2006-06-05 | 9 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-01-01 | 2007-01-01 | 21-07-2007 | 14-06-2007 | N.A. | N.A. | 21-02-2008 | 29-08-2008 | 21-05-2008 | 30-09-2008 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 30-09-2008 | 30-11-2008 | N.A. | N.A. | 05-10-2007 | 15-11-2007 | N.A. | N.A. | 05-06-2008 | 06-07-2008 | N.A. | N.A. | 05-07-2008 | 06-12-2008 | 01-08-2008 | 15-12-2008 | N.A. | N.A. | 21-08-2008 | 14-01-2009 | 2008-10-06 | 29-03-2009 | N.A. | N.A. | 06-10-2008 | 29-03-2009 | 06-10-2008 | 29-03-2009 | N.A. | N.A. | 210 | 210 | 854
23 | BAKRESWAR - MP UNIT-5 (2 X 210 MW) | 210 | 2004-11-30 | 0 | 0 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2005-09-30 | 2005-12-01 | 30-01-2006 | 09-08-2006 | N.A. | N.A. | 30-12-2006 | 24-03-2008 | 31-03-2007 | 29-06-2008 | 16-04-2007 | 15-07-2008 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 15-04-2007 | 28-01-2009 | N.A. | N.A. | 30-09-2005 | 01-12-2005 | N.A. | N.A. | 15-03-2007 | 25-09-2008 | N.A. | N.A. | 30-03-2007 | 30-01-2009 | 15-04-2007 | 28-02-2009 | N.A. | N.A. | 30-06-2007 | 30-03-2009 | 2007-10-29 | 27-06-2009 | N.A. | N.A. | 30-10-2007 | 24-06-2009 | 30-10-2007 | 24-06-2009 | 29-10-2007 | 27-06-2009 | 304 | 366 | 1063
24 | GIRAL UNIT-2 (2X125 MW) | 125 | 2005-12-15 | 1 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2006-12-14 | 2006-12-14 | 31-03-2007 | 10-05-2007 | N.A. | N.A. | 31-12-2007 | 28-03-2008 | 31-03-2008 | 15-09-2008 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 24-03-2008 | 30-10-2008 | N.A. | N.A. | 02-05-2007 | 09-09-2007 | N.A. | N.A. | 02-03-2008 | 10-11-2008 | N.A. | N.A. | 30-04-2008 | 15-11-2008 | 18-05-2008 | 20-11-2008 | N.A. | N.A. | 14-06-2008 | 26-12-2008 | 2008-07-14 | 27-06-2009 | N.A. | N.A. | 14-07-2008 | 12-03-2011 | 14-07-2008 | 12-03-2011 | N.A. | N.A. | 364 | 364 | 942
25 | BHILAI TPS-2(250 MW) | 250 | 2005-03-31 | 5 | 1 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2006-02-28 | 2006-05-21 | 30-07-2006 | 08-10-2006 | N.A. | N.A. | 15-03-2007 | 13-10-2007 | 15-07-2007 | 05-09-2008 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 15-09-2007 | 28-01-2009 | N.A. | N.A. | 30-09-2006 | 19-02-2007 | N.A. | N.A. | 30-06-2007 | 31-12-2008 | N.A. | N.A. | 31-08-2007 | 20-01-2009 | 25-09-2007 | 10-03-2009 | N.A. | N.A. | 15-10-2007 | 28-03-2009 | 2007-10-15 | 12-07-2009 | N.A. | N.A. | 15-01-2008 | 21-10-2011 | 15-01-2008 | 30-11-2009 | N.A. | N.A. | 334 | 416 | 928
26 | KAHALGAON UNIT-7(500) | 500 | 2003-12-15 | 8 | 0 | 0 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2004-10-15 | 2004-11-17 | 15-03-2005 | 28-03-2005 | N.A. | N.A. | 15-02-2006 | 31-10-2006 | 15-08-2006 | 15-11-2008 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 15-10-2006 | 01-03-2009 | N.A. | N.A. | 15-07-2005 | 16-08-2006 | N.A. | N.A. | 15-08-2006 | 31-08-2007 | N.A. | N.A. | 15-09-2006 | 04-01-2009 | 15-10-2006 | 09-03-2009 | N.A. | N.A. | 15-12-2006 | 31-03-2009 | 2007-04-15 | 31-07-2009 | N.A. | N.A. | 15-04-2007 | 20-03-2010 | 15-04-2007 | 11-04-2010 | N.A. | N.A. | 305 | 338 | 1217
27 | SURATGARH 6 (1X250 MW) | 250 | 2006-06-15 | 1 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-03-15 | 2007-05-21 | 12-08-2007 | 30-09-2007 | N.A. | N.A. | 28-03-2008 | 31-05-2008 | 28-07-2008 | 25-01-2009 | 29-07-2008 | 17-02-2009 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 17-09-2008 | 16-03-2009 | N.A. | N.A. | 03-09-2007 | 21-04-2008 | N.A. | N.A. | 20-07-2008 | 12-01-2009 | N.A. | N.A. | 27-08-2008 | 15-03-2009 | 07-09-2008 | 24-03-2009 | N.A. | N.A. | 16-10-2008 | 31-03-2009 | 2008-12-16 | 29-08-2009 | N.A. | N.A. | 30-12-2009 | 30-12-2009 | 15-12-2008 | 13-10-2009 | N.A. | N.A. | 273 | 340 | 915
28 | KOTA UNIT-7 (1X195 MW) | 195 | 2006-06-15 | 1 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-04-06 | 2007-05-21 | 03-09-2007 | 28-10-2007 | N.A. | N.A. | 19-04-2008 | 31-05-2008 | 19-08-2008 | 22-01-2009 | 26-08-2008 | 21-02-2009 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 09-10-2008 | 01-05-2009 | N.A. | N.A. | 03-10-2007 | 19-05-2008 | N.A. | N.A. | 17-08-2008 | 06-02-2009 | N.A. | N.A. | 24-09-2008 | 05-05-2009 | 11-10-2008 | 15-05-2009 | N.A. | N.A. | 07-11-2008 | 30-05-2009 | 2009-01-07 | 31-08-2009 | N.A. | N.A. | 15-12-2009 | 15-12-2009 | 06-01-2009 | 14-12-2009 | N.A. | N.A. | 295 | 340 | 937
29 | BUDGE BUDGE | 250 | 2006-12-24 | 10 | 1 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-07-17 | 2007-08-10 | 31-12-2007 | 10-02-2008 | N.A. | N.A. | 25-08-2008 | 28-09-2008 | 08-12-2008 | 19-03-2009 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 22-03-2009 | 10-06-2009 | N.A. | N.A. | 18-02-2008 | 29-05-2008 | N.A. | N.A. | 14-12-2008 | 31-05-2009 | N.A. | N.A. | 13-01-2009 | 10-06-2009 | 03-02-2009 | 20-06-2009 | N.A. | N.A. | 29-04-2009 | 12-07-2009 | 2009-06-29 | 29-09-2009 | N.A. | N.A. | 29-06-2009 | 27-02-2010 | 29-06-2009 | 27-02-2010 | N.A. | N.A. | 205 | 229 | 918
30 | VIJAYAWADA STG- IV (1X500 MW) | 500 | 2005-08-05 | 11 | 0 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2006-08-04 | 2006-08-18 | 04-01-2007 | 10-05-2007 | N.A. | N.A. | 04-12-2007 | 28-12-2007 | 04-05-2008 | 25-12-2008 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 04-07-2008 | 05-03-2009 | N.A. | N.A. | 04-08-2006 | 18-08-2006 | N.A. | N.A. | 04-05-2008 | 15-10-2008 | N.A. | N.A. | 04-06-2008 | 31-01-2009 | 05-07-2008 | 31-03-2009 | N.A. | N.A. | 04-08-2008 | 06-04-2009 | 2008-11-04 | 08-10-2009 | N.A. | N.A. | 04-11-2008 | 28-01-2010 | 04-11-2008 | 28-01-2010 | 04-11-2008 | 28-01-2010 | 364 | 378 | 1187
31 | CHHABRA UNIT-1 (2X250 MW) | 250 | 2006-03-03 | 1 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-02-15 | 2007-03-23 | 02-07-2007 | 07-08-2007 | N.A. | N.A. | 16-02-2008 | 16-04-2008 | 17-06-2008 | 26-01-2009 | 24-06-2008 | 18-02-2009 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 07-08-2008 | 26-03-2009 | N.A. | N.A. | 21-06-2007 | 18-01-2008 | N.A. | N.A. | 12-05-2008 | 28-02-2009 | N.A. | N.A. | 19-06-2008 | 22-03-2009 | 08-07-2008 | 30-03-2009 | N.A. | N.A. | 03-09-2008 | 16-04-2009 | 2008-11-03 | 30-10-2009 | N.A. | N.A. | 04-11-2008 | 11-06-2010 | 04-11-2008 | 11-06-2010 | N.A. | N.A. | 349 | 385 | 976
32 | CHANDRAPURA TPS UNIT-7 (2 X 250MW) | 250 | 2004-06-30 | 12 | 1 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2005-02-27 | 2005-10-17 | 07-07-2005 | 25-04-2006 | N.A. | N.A. | 06-06-2005 | 30-04-2007 | 16-10-2006 | 06-07-2008 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 11-11-2006 | 19-12-2008 | N.A. | N.A. | 27-02-2005 | 17-10-2005 | N.A. | N.A. | 01-09-2006 | 18-04-2008 | N.A. | N.A. | 21-10-2006 | 21-09-2008 | 06-11-2006 | 01-10-2008 | N.A. | N.A. | 30-11-2006 | 06-01-2009 | 2007-01-27 | 04-11-2009 | N.A. | N.A. | 27-01-2007 | 02-11-2011 | 27-01-2007 | 02-11-2011 | N.A. | N.A. | 242 | 474 | 941
33 | DADRI NCTPP UNIT V (1 X 490 MW ) | 490 | 2006-07-31 | 13 | 0 | 2 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-09-30 | 2007-12-12 | 29-02-2008 | 30-04-2008 | N.A. | N.A. | 21-03-2009 | 26-03-2009 | 30-09-2009 | 23-07-2009 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 31-08-2009 | 10-10-2009 | N.A. | N.A. | 31-05-2007 | 06-08-2007 | 31-05-2007 | 17-06-2008 | 31-05-2009 | 17-07-2009 | N.A. | N.A. | 30-06-2009 | 09-11-2009 | 31-08-2009 | 10-12-2009 | N.A. | N.A. | 30-09-2009 | 25-12-2009 | 2010-01-30 | 31-01-2010 | N.A. | N.A. | 30-01-2010 | 31-01-2010 | 30-01-2010 | 31-01-2010 | 30-01-2010 | 31-01-2010 | 426 | 499 | 1279
34 | PARLI UNIT-2 (1X250MW) | 250 | 2006-08-31 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-05-30 | 2007-10-17 | 30-11-2007 | 15-04-2008 | N.A. | N.A. | 30-06-2008 | 18-12-2008 | 30-10-2008 | 12-07-2009 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 30-11-2007 | 25-07-2008 | N.A. | N.A. | 30-11-2008 | 29-05-2009 | N.A. | N.A. | N.A. | N.A. | 31-01-2009 | 31-10-2009 | N.A. | N.A. | 28-02-2009 | 12-11-2009 | 2009-04-30 | 10-02-2010 | N.A. | N.A. | 30-04-2009 | 31-07-2010 | 30-04-2009 | 31-07-2010 | N.A. | N.A. | 272 | 412 | 973
35 | PARAS UNIT-2 (1X250 MW) | 250 | 2006-08-31 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-07-30 | 2007-09-14 | 30-01-2008 | 15-05-2008 | N.A. | N.A. | 30-08-2008 | 18-02-2009 | 30-12-2008 | 22-07-2009 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 30-01-2008 | 18-08-2008 | N.A. | N.A. | 30-01-2009 | 31-07-2009 | N.A. | N.A. | N.A. | N.A. | 31-03-2009 | 29-10-2009 | N.A. | N.A. | 30-04-2009 | 30-11-2009 | 2009-06-30 | 27-03-2010 | N.A. | N.A. | 30-06-2009 | 06-08-2010 | 30-06-2009 | 06-08-2010 | N.A. | N.A. | 333 | 379 | 1034
36 | CHANDRAPURA TPS UNIT-8 (2 X 250MW) | 250 | 2004-06-30 | 12 | 1 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2005-04-27 | 2006-02-01 | 07-09-2005 | 14-08-2006 | N.A. | N.A. | 07-08-2006 | 02-11-2007 | 16-12-2006 | 29-11-2009 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 11-01-2006 | 03-03-2010 | N.A. | N.A. | 27-04-2005 | 01-02-2006 | N.A. | N.A. | 01-11-2006 | 03-09-2009 | N.A. | N.A. | 21-12-2006 | 04-03-2010 | 06-01-2007 | 22-03-2010 | N.A. | N.A. | 30-01-2007 | 31-03-2010 | 2007-03-27 | 31-03-2010 | N.A. | N.A. | 30-04-2007 | 15-07-2011 | 14-04-2007 | 27-11-2010 | N.A. | N.A. | 301 | 581 | 1000
37 | SURAT LIGNITE POWER PROJECT UNIT-3 (2X125 MW) | 125 | 2006-03-31 | 14 | 1 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | 15-09-2006 | 31-10-2006 | 2007-01-06 | 2007-02-19 | 06-05-2007 | 25-08-2007 | N.A. | N.A. | 22-02-2008 | 06-11-2008 | 24-07-2008 | 19-07-2009 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 06-07-2007 | 19-02-2007 | N.A. | N.A. | 23-03-2008 | 28-07-2009 | N.A. | N.A. | 23-05-2008 | 30-07-2009 | 13-08-2008 | 10-08-2009 | N.A. | N.A. | 20-09-2008 | 29-11-2009 | 2008-11-10 | 12-04-2010 | N.A. | N.A. | 10-11-2008 | 31-01-2011 | 10-11-2008 | 31-01-2011 | N.A. | N.A. | 281 | 325 | 955
38 | SURAT LIGNITE POWER PROJECT UNIT-4 (2X125 MW) | 125 | 2006-03-31 | 14 | 1 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-05-06 | 2007-07-09 | 06-09-2007 | 15-11-2007 | N.A. | N.A. | 22-06-2008 | 07-03-2009 | 24-11-2008 | 31-12-2009 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 16-11-2007 | 03-07-2008 | N.A. | N.A. | 23-07-2008 | 12-02-2010 | N.A. | N.A. | 23-09-2008 | 31-12-2009 | 13-12-2008 | 28-02-2010 | N.A. | N.A. | 20-01-2009 | 25-03-2010 | 2009-03-10 | 23-04-2010 | N.A. | N.A. | 10-03-2009 | 27-01-2012 | 10-03-2009 | 27-01-2012 | N.A. | N.A. | 401 | 465 | 1075
39 | CHHABRA UNIT-2 (2X250 MW) | 250 | 2006-03-03 | 1 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-05-02 | 2007-04-21 | 02-10-2007 | 26-11-2007 | N.A. | N.A. | 16-05-2008 | 21-04-2009 | 17-09-2008 | 31-12-2009 | 18-09-2008 | 03-02-2010 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 07-11-2008 | 05-03-2010 | N.A. | N.A. | 21-09-2007 | 15-01-2009 | N.A. | N.A. | 12-08-2008 | 10-01-2010 | N.A. | N.A. | 19-09-2008 | 22-12-2009 | 08-10-2008 | 22-01-2010 | N.A. | N.A. | 03-12-2008 | 31-03-2010 | 2009-03-12 | 04-05-2010 | N.A. | N.A. | 12-03-2009 | 15-10-2011 | 12-03-2009 | 15-10-2011 | N.A. | N.A. | 425 | 414 | 1105
40 | KAKATIYA TPP (1X500 MW) | 500 | 2005-01-09 | 11 | 0 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-02-09 | 2007-03-21 | 09-06-2007 | 26-08-2007 | N.A. | N.A. | 09-05-2008 | 04-05-2008 | 09-11-2008 | 28-01-2010 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 30-09-2007 | 25-04-2008 | N.A. | N.A. | 09-09-2008 | 17-11-2009 | N.A. | N.A. | N.A. | N.A. | 09-12-2008 | 24-03-2010 | N.A. | N.A. | 09-02-2009 | 31-03-2010 | 2009-04-09 | 04-05-2010 | N.A. | N.A. | 09-04-2009 | 15-10-2011 | 09-04-2009 | 15-10-2011 | N.A. | N.A. | 761 | 801 | 1551
41 | RAICHUR TPS UNIT-8 (1X250 MW) | 250 | 2007-03-30 | 15 | 0 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-12-29 | 2007-12-12 | 29-05-2008 | 14-08-2008 | N.A. | N.A. | 29-11-2008 | 25-03-2009 | 29-04-2009 | 15-12-2009 | 20-05-2009 | 29-01-2010 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 24-06-2009 | 04-03-2010 | N.A. | N.A. | 29-05-2008 | 24-01-2009 | N.A. | N.A. | 29-04-2009 | 02-01-2010 | N.A. | N.A. | 25-05-2009 | 13-02-2010 | 29-05-2009 | 18-03-2010 | N.A. | N.A. | 29-07-2009 | 09-04-2010 | 2009-09-29 | 26-06-2010 | N.A. | N.A. | 29-09-2009 | 11-12-2010 | 29-09-2009 | 11-12-2010 | 29-09-2009 | 11-12-2010 | 274 | 257 | 914
42 | BARSINGSAR-TPP UNIT-1 (2X125 MW) | 125 | 2005-12-29 | 1 | 1 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2006-10-06 | 2007-03-14 | 03-02-2007 | 21-06-2007 | N.A. | N.A. | 22-11-2007 | 11-08-2008 | 23-04-2008 | 15-09-2009 | 30-04-2008 | 21-09-2009 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 02-06-2008 | 03-10-2009 | N.A. | N.A. | 15-04-2007 | 10-03-2008 | N.A. | N.A. | 28-02-2008 | 31-03-2009 | N.A. | N.A. | 29-04-2008 | 29-08-2009 | 13-05-2008 | 15-09-2009 | N.A. | N.A. | 28-06-2008 | 27-10-2009 | 2008-07-28 | 28-06-2010 | N.A. | N.A. | 28-08-2008 | 24-01-2012 | 28-08-2008 | 06-02-2012 | N.A. | N.A. | 281 | 440 | 942
43 | DADRI NCTPP UNIT VI (1 X 490 MW) | 490 | 2006-11-30 | 13 | 0 | 2 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-09-30 | 2007-12-21 | 29-02-2008 | 30-04-2008 | N.A. | N.A. | 28-02-2009 | 26-03-2009 | 30-09-2009 | 08-03-2010 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 30-12-2009 | 27-05-2010 | N.A. | N.A. | 30-07-2008 | 29-01-2009 | 30-07-2008 | 29-01-2009 | 30-09-2009 | 24-02-2010 | N.A. | N.A. | 30-10-2009 | 24-06-2010 | 30-12-2009 | 05-07-2010 | N.A. | N.A. | 30-01-2010 | 16-07-2010 | 2010-05-30 | 29-07-2010 | N.A. | N.A. | 30-05-2010 | 02-11-2010 | 30-05-2010 | 02-11-2010 | 30-05-2010 | 02-11-2010 | 304 | 386 | 1277
44 | MEJIA PH-II UNIT-1 (UNIT-7) (2 X 500 MW ) | 500 | 2006-12-31 | 0 | 1 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-10-01 | 2007-09-26 | 28-02-2008 | 29-03-2008 | N.A. | N.A. | 31-01-2009 | 09-04-2009 | 31-07-2009 | 31-12-2009 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 05-10-2009 | 24-03-2010 | N.A. | N.A. | 15-10-2008 | 26-09-2008 | N.A. | N.A. | 24-07-2009 | 09-11-2009 | N.A. | N.A. | 17-09-2009 | 28-02-2010 | 18-10-2009 | 10-04-2010 | N.A. | N.A. | 31-10-2009 | 12-04-2010 | 2009-12-31 | 30-09-2010 | N.A. | N.A. | 31-01-2010 | 02-08-2011 | 30-01-2010 | 26-02-2012 | N.A. | N.A. | 274 | 269 | 1096
45 | JHAJJAR(INDIRA GANDHI STPP) UNIT-1 (3X500MW) | 500 | 2007-07-06 | 16 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-05-05 | 2008-06-23 | 05-10-2008 | 12-12-2008 | N.A. | N.A. | 05-09-2009 | 28-01-2010 | 05-03-2010 | 01-07-2010 | 12-03-2010 | 29-07-2010 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 05-05-2010 | 31-08-2010 | N.A. | N.A. | 12-02-2009 | 07-04-2009 | 14-04-2009 | 07-06-2009 | 14-03-2010 | 07-04-2010 | N.A. | N.A. | 14-06-2010 | 04-09-2010 | 04-07-2010 | 28-09-2010 | N.A. | N.A. | 14-07-2010 | 10-10-2010 | 2010-09-30 | 31-10-2010 | N.A. | N.A. | 14-11-2010 | 05-03-2011 | 14-11-2010 | 07-11-2011 | N.A. | N.A. | 304 | 353 | 1182
46 | KORBA NTPC STAGE III UNIT-7 (1X500MW) | 500 | 2006-03-24 | 2 | 0 | 1 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-01-23 | 2007-10-17 | 23-06-2007 | 27-02-2008 | N.A. | N.A. | 23-06-2008 | 28-01-2009 | 23-01-2009 | 28-02-2010 | 23-02-2009 | 31-03-2010 | N.A. | N.A. | 23-02-2009 | 31-03-2010 | N.A. | N.A. | 23-04-2009 | 04-08-2010 | N.A. | N.A. | 23-11-2007 | 19-04-2009 |  | 07-08-2009 | 23-01-2009 | 31-12-2009 | N.A. | N.A. | 23-02-2009 | 22-09-2010 | 23-03-2009 | 27-10-2010 | N.A. | N.A. | 23-05-2009 | 25-11-2010 | 2009-07-23 | 26-12-2010 | N.A. | N.A. | 23-09-2009 | 21-03-2011 | 23-10-2009 | 26-06-2011 | N.A. | N.A. | 305 | 572 | 1217
47 | RAYALASEEMA STAGE-III UNIT-5 (1X210 MW ) | 210 | 2007-01-25 | 11 | 0 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-12-24 | 2008-07-16 | 24-04-2008 | 19-12-2008 | N.A. | N.A. | 24-12-2008 | 14-09-2009 | 24-04-2009 | 12-07-2010 | N.A. | N.A. | N.A. | N.A. | 04-05-2009 | 31-07-2010 | N.A. | N.A. | 24-06-2009 | 03-10-2010 | N.A. | N.A. | 24-06-2008 | 02-08-2009 | N.A. | N.A. | 24-03-2009 | 22-11-2010 | N.A. | N.A. | N.A. | N.A. | 09-07-2009 | 21-11-2010 | N.A. | N.A. | 24-07-2009 | 29-11-2010 | 2009-10-31 | 31-12-2010 | N.A. | N.A. | 31-10-2009 | 10-02-2011 | 31-10-2009 | 31-12-2010 | 31-10-2009 | 21-02-2011 | 333 | 538 | 1010
48 | BARSINGSAR-TPP UNIT-2 (2X125 MW) | 125 | 2005-12-29 | 1 | 1 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-02-06 | 2007-05-04 | 03-06-2007 | 14-09-2007 | N.A. | N.A. | 22-03-2008 | 01-06-2009 | 23-08-2008 | 19-02-2010 | 30-08-2008 | 08-03-2010 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 02-10-2008 | 11-04-2010 | N.A. | N.A. | 15-08-2007 | 18-07-2008 | N.A. | N.A. | 28-06-2008 | 19-12-2009 | N.A. | N.A. | 29-08-2008 | 25-03-2010 | 13-09-2008 | 02-05-2010 | N.A. | N.A. | 28-10-2008 | 05-06-2010 | 2008-11-28 | 25-01-2011 | N.A. | N.A. | 28-12-2008 | 24-01-2012 | 28-12-2008 | 30-01-2012 | N.A. | N.A. | 404 | 491 | 1065
49 | FARAKKA STPP UNIT-6 (1 X 500 MW) | 500 | 2006-10-30 | 0 | 0 | 2 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-09-01 | 2008-05-30 | 30-01-2008 | 04-02-2009 | N.A. | N.A. | 30-01-2009 | 12-03-2010 | 30-08-2009 | 12-10-2010 | N.A. | N.A. | N.A. | N.A. | 31-10-2009 | 26-12-2010 | N.A. | N.A. | 30-11-2009 | 07-02-2011 | N.A. | N.A. |  | 26-06-2009 |  | 26-08-2009 | 30-08-2009 | 27-02-2010 | N.A. | N.A. | 30-09-2009 | 30-09-2010 | 30-10-2009 | 27-02-2011 | N.A. | N.A. | 30-12-2009 | 07-03-2011 | 2010-04-30 | 23-03-2011 | N.A. | N.A. | 30-04-2010 | 28-02-2012 | 30-04-2010 | 28-02-2012 | N.A. | N.A. | 306 | 578 | 1278
50 | MEJIA PH-II UNIT-2 (UNIT-8) (2 X 500 MW ) | 500 | 2006-12-31 | 0 | 1 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-01-01 | 2007-12-30 | 31-05-2008 | 08-07-2008 | N.A. | N.A. | 30-04-2009 | 27-07-2009 | 30-10-2009 | 01-07-2010 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 15-01-2009 | 15-01-2009 | N.A. | N.A. | 24-10-2009 | 14-07-2010 | N.A. | N.A. | N.A. | N.A. | 18-01-2010 | 21-10-2010 | N.A. | N.A. | 31-01-2010 | 11-11-2010 | 2010-03-31 | 26-03-2011 | N.A. | N.A. | 31-03-2010 | 16-08-2012 | 15-03-2010 | 01-08-2012 | 30-04-2010 | 12-08-2012 | 366 | 364 | 1186
51 | SIMHADRI STPP STAGE-II UNIT-3 (2X500 MW) | 500 | 2007-03-26 | 11 | 0 | 3 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-01-25 | 2008-01-25 | 25-06-2008 | 29-11-2008 | N.A. | N.A. | 25-06-2009 | 03-12-2009 | 25-01-2010 | 28-09-2010 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 29-10-2008 | 21-03-2009 |  | 03-08-2009 | 29-12-2009 | 16-12-2010 | N.A. | N.A. | N.A. | N.A. | 19-03-2010 | 16-03-2011 | N.A. | N.A. | 29-03-2010 | 29-03-2011 | 2010-09-25 | 31-03-2011 | N.A. | N.A. | 25-09-2010 | 16-11-2011 | 25-09-2010 | 04-11-2011 | N.A. | N.A. | 305 | 305 | 1279
52 | KOTHAGUDEM TPS STG - VI (1 X 500 MW) | 500 | 2007-02-22 | 11 | 0 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-12-15 | 2008-04-10 | 22-05-2008 | 18-08-2008 | N.A. | N.A. | 22-04-2009 | 23-10-2009 | 22-09-2009 | 31-10-2010 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 22-01-2010 | 08-02-2011 | N.A. | N.A. | 15-12-2007 | 10-04-2008 | N.A. | N.A. | 22-10-2009 | 22-12-2010 | N.A. | N.A. | 22-12-2009 | 03-02-2011 | 22-01-2010 | 14-03-2011 | N.A. | N.A. | 22-02-2010 | 30-03-2011 | 2010-05-22 | 26-06-2011 | N.A. | N.A. | 22-05-2010 | 23-10-2011 | 22-05-2010 | 23-10-2011 | 22-05-2010 | 23-10-2011 | 296 | 413 | 1185
53 | SANTALDIH EXTN UNIT-6 (1X250 MW) | 250 | 2007-03-23 | 0 | 1 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-12-29 | 2008-04-25 | 13-04-2008 | 02-10-2008 | N.A. | N.A. | 27-12-2008 | 10-12-2009 | 29-05-2009 | 10-05-2010 | N.A. | N.A. | N.A. | N.A. | 09-06-2009 | 13-08-2010 | N.A. | N.A. | 08-07-2009 | 14-10-2010 | N.A. | N.A. | 30-05-2008 | 14-09-2009 | N.A. | N.A. | 26-01-2009 | 10-07-2010 | N.A. | N.A. | 28-03-2009 | 29-09-2010 | 20-04-2009 | 26-10-2010 | N.A. | N.A. | 20-07-2009 | 21-11-2010 | 2009-09-22 | 29-06-2011 | N.A. | N.A. | 22-09-2009 | 08-10-2011 | 22-09-2009 | 08-10-2011 | N.A. | N.A. | 281 | 399 | 914
54 | MAITHON RBTPP UNIT-1 (2X525 MW) | 525 | 2007-10-25 | 12 | 0 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-07-25 | 2008-09-08 | 22-12-2008 | 22-03-2009 | N.A. | N.A. | 25-11-2009 | 23-03-2010 | 10-05-2010 | 05-12-2010 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 30-07-2010 | 10-03-2011 | N.A. | N.A. | 25-05-2009 | 10-08-2009 | N.A. | N.A. | 21-04-2010 | 02-11-2010 | N.A. | N.A. | 21-06-2010 | 26-01-2011 | 15-07-2010 | 08-02-2011 | N.A. | N.A. | 19-08-2010 | 28-03-2011 | 2010-09-25 | 30-06-2011 | N.A. | N.A. | 28-09-2010 | 01-09-2011 | 25-09-2010 | 17-01-2012 | N.A. | N.A. | 274 | 319 | 1066
55 | KODERMA TPP UNIT-1 (2X500 MW) | 500 | 2007-07-21 | 12 | 1 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-04-20 | 2008-09-15 | 17-09-2008 | 08-03-2009 | N.A. | N.A. | 21-08-2009 | 07-03-2010 | 05-02-2010 | 30-12-2010 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 18-02-2009 | 26-08-2009 | N.A. | N.A. | 18-01-2010 | 20-12-2010 | N.A. | N.A. | 24-03-2010 | 22-03-2011 | 15-04-2010 | 12-05-2011 | N.A. | N.A. | 05-05-2010 | 27-06-2011 | 2010-05-08 | 20-07-2011 | N.A. | N.A. | 19-06-2010 | 18-07-2013 | 19-06-2010 | 21-10-2013 | N.A. | N.A. | 274 | 422 | 1022
56 | DURGAPUR STEEL TPS UNIT-1 (2X500 MW) | 500 | 2007-08-03 | 0 | 1 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-05-03 | 2008-07-06 | 30-09-2008 | 29-04-2009 | N.A. | N.A. | 03-09-2009 | 30-03-2010 | 03-03-2010 | 27-02-2011 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 03-03-2009 | 14-09-2009 | N.A. | N.A. | 31-01-2010 | 13-11-2010 | N.A. | N.A. | 06-04-2010 | 26-04-2011 | 25-05-2010 | 04-05-2011 | N.A. | N.A. | 03-06-2010 | 12-07-2011 | 2010-07-27 | 29-07-2011 | N.A. | N.A. | 31-08-2010 | 15-05-2012 | 31-08-2010 | 04-01-2013 | N.A. | N.A. | 274 | 338 | 1089
57 | KHAPERKHEDA TPS (1X500 MW) | 500 | 2007-01-23 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-12-22 | 2008-02-12 | 22-06-2008 | 28-11-2008 | N.A. | N.A. | 22-05-2009 | 05-11-2009 | 22-12-2009 | 27-10-2010 | 22-01-2010 | 17-11-2010 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 22-02-2010 | 06-02-2011 | N.A. | N.A. | 22-09-2008 | 27-03-2009 | N.A. | N.A. | 22-11-2009 | 31-10-2010 | N.A. | N.A. | N.A. | N.A. | 22-02-2010 | 09-03-2011 | N.A. | N.A. | 22-03-2010 | 31-03-2011 | 2010-05-22 | 05-08-2011 | N.A. | N.A. | 22-05-2010 | 16-04-2012 | 22-05-2010 | 04-04-2012 | N.A. | N.A. | 333 | 385 | 1215
58 | HARDUAGANJ EXTENSION UNIT-8 (2 X 250 MW ) | 250 | 2006-09-07 | 13 | 2 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | 10-01-2007 | 30-01-2008 | 2007-07-07 | 2008-08-25 | 07-01-2008 | 30-01-2009 | N.A. | N.A. | 07-12-2008 | 30-11-2009 | 07-04-2009 | 25-03-2011 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 07-07-2009 | 19-06-2011 | N.A. | N.A. | 07-04-2008 | 06-11-2009 | N.A. | N.A. | 07-04-2009 | 10-02-2011 | N.A. | N.A. | 07-05-2009 | 25-06-2011 | 07-07-2009 | 30-06-2011 | N.A. | N.A. | 07-08-2009 | 10-08-2011 | 2009-10-07 | 27-09-2011 | N.A. | N.A. | 07-10-2009 | 01-02-2012 | 07-10-2009 | 30-01-2012 | N.A. | N.A. | 303 | 718 | 1126
59 | JHAJJAR(INDIRA GANDHI STPP) UNIT-2 (3X500MW) | 500 | 2007-07-06 | 16 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-08-05 | 2008-12-12 | 05-01-2009 | 09-04-2009 | N.A. | N.A. | 05-12-2009 | 04-05-2010 | 05-06-2010 | 29-05-2011 | 12-06-2010 | 16-06-2011 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 05-08-2010 | 11-08-2011 | N.A. | N.A. | 12-05-2009 | 05-12-2009 | 14-07-2009 | 05-02-2010 | 14-06-2010 | 04-04-2011 | N.A. | N.A. | 14-09-2010 | 09-09-2011 | 01-10-2010 | 09-10-2011 | N.A. | N.A. | 14-10-2010 | 21-10-2011 | 2010-12-31 | 05-11-2011 | N.A. | N.A. | 14-02-2011 | 21-04-2012 | 14-02-2011 | 03-10-2013 | N.A. | N.A. | 396 | 525 | 1274
60 | NEYVELI TPS II EXPANSION UNIT-1 (2X250 MW) | 250 | 2005-08-19 | 17 | 1 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2006-06-20 | 2007-04-28 | 19-11-2006 | 06-02-2008 | N.A. | N.A. | 18-09-2007 | 01-07-2009 | 19-02-2008 | 28-02-2011 | 01-04-2008 | 10-03-2011 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 01-05-2008 | 02-04-2011 | N.A. | N.A. | 20-06-2006 | 29-06-2008 | N.A. | N.A. | 17-01-2008 | 10-01-2010 | N.A. | N.A. | 18-03-2008 | 31-12-2010 | 18-04-2008 | 12-02-2011 | N.A. | N.A. | 19-05-2008 | 18-05-2011 | 2008-07-19 | 04-02-2012 | N.A. | N.A. | 19-08-2008 | 03-07-2015 | 19-08-2008 | 27-09-2016 | N.A. | N.A. | 305 | 617 | 1065
61 | BHUSAWAL UNIT-4 (2X500MW ) | 500 | 2007-01-23 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-02-28 | 2008-03-26 | 22-08-2008 | 09-01-2009 | N.A. | N.A. | 24-07-2009 | 31-03-2010 | 22-02-2010 | 05-03-2011 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 22-11-2008 | 14-03-2009 | N.A. | N.A. | 22-01-2010 | 21-12-2010 | N.A. | N.A. | N.A. | N.A. | 22-04-2010 | 28-03-2011 | N.A. | N.A. | 22-05-2010 | 11-05-2011 | 2010-08-22 | 07-03-2012 | N.A. | N.A. | 22-08-2010 | 18-07-2012 | 24-08-2010 | 18-07-2012 | N.A. | N.A. | 401 | 428 | 1307
62 | BELLARY TPS UNIT-2 (1X500 MW) | 500 | 2007-09-19 | 15 | 1 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | 18-12-2007 | 22-05-2008 | 2008-08-18 | 2008-11-17 | 18-02-2009 | 06-04-2009 | N.A. | N.A. | 18-01-2010 | 24-06-2010 | 18-07-2010 | 04-02-2011 | 03-08-2010 | 18-04-2011 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 16-09-2010 | 09-11-2011 | N.A. | N.A. | 18-08-2009 | 05-03-2010 | N.A. | N.A. | 18-05-2010 | 25-07-2011 | N.A. | N.A. | 02-08-2010 | 18-11-2011 | 18-09-2010 | 09-01-2012 | N.A. | N.A. | 18-11-2010 | 27-01-2012 | 2011-02-18 | 23-03-2012 | N.A. | N.A. | 18-02-2011 | 10-03-2013 | 18-02-2011 | 09-03-2013 | 18-02-2011 | 10-03-2013 | 334 | 425 | 1248
63 | DURGAPUR STEEL TPS UNIT-2 (2X500 MW) | 500 | 2007-08-03 | 0 | 1 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-08-03 | 2008-11-15 | 30-12-2008 | 08-07-2009 | N.A. | N.A. | 03-12-2009 | 26-12-2010 | 03-06-2010 | 16-11-2011 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 03-06-2009 | 25-02-2010 | N.A. | N.A. | 30-04-2010 | 13-11-2011 | N.A. | N.A. | 06-07-2010 | 12-01-2012 | 15-08-2010 | 12-02-2012 | N.A. | N.A. | 03-09-2010 | 12-03-2012 | 2010-10-27 | 23-03-2012 | N.A. | N.A. | 27-10-2010 | 05-03-2013 | 27-10-2010 | 25-03-2014 | N.A. | N.A. | 366 | 470 | 1181
64 | MAITHON RBTPP UNIT-2 (2X525 MW) | 525 | 2007-10-25 | 12 | 0 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-01-25 | 2009-01-25 | 22-06-2009 | 22-06-2009 | N.A. | N.A. | 25-05-2010 | 23-10-2010 | 10-11-2010 | 29-08-2011 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 30-01-2011 | 20-11-2011 | N.A. | N.A. | 25-11-2009 | 02-07-2010 | N.A. | N.A. | 21-10-2010 | 10-09-2011 | N.A. | N.A. | 21-12-2010 | 10-11-2011 | 15-01-2011 | 16-12-2011 | N.A. | N.A. | 09-02-2011 | 17-03-2012 | 2011-03-25 | 23-03-2012 | N.A. | N.A. | 25-03-2011 | 24-07-2012 | 25-03-2011 | 31-07-2012 | N.A. | N.A. | 458 | 458 | 1247
65 | VALLUR TPS UNIT-1 (2X500 MW) | 500 | 2007-08-13 | 17 | 0 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-06-12 | 2009-01-05 | 12-11-2008 | 10-06-2009 | N.A. | N.A. | 12-11-2009 | 15-06-2010 | 12-06-2010 | 28-08-2011 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 12-09-2010 | 01-12-2011 | N.A. | N.A. | 12-04-2009 | 10-12-2009 | 12-06-2009 | 26-12-2009 | 12-06-2010 | 30-09-2011 | N.A. | N.A. | 12-07-2010 | 26-12-2011 | 12-08-2010 | 26-02-2012 | N.A. | N.A. | 12-10-2010 | 09-03-2012 | 2011-02-12 | 28-03-2012 | N.A. | N.A. | 30-04-2011 | 29-11-2012 | 30-04-2011 | 23-03-2013 | N.A. | N.A. | 304 | 511 | 1279
66 | BHUSAWAL UNIT-5 (2X500MW ) | 500 | 2007-01-23 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-06-22 | 2008-08-03 | 22-12-2008 | 20-04-2009 | N.A. | N.A. | 22-11-2009 | 29-06-2010 | 22-06-2010 | 22-11-2011 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 22-03-2009 | 29-10-2009 | N.A. | N.A. | 22-05-2010 | 09-07-2011 | N.A. | N.A. | N.A. | N.A. | 22-08-2010 | 06-02-2012 | N.A. | N.A. | 22-09-2010 | 03-03-2012 | 2010-12-22 | 30-03-2012 | N.A. | N.A. | 22-09-2010 | 01-06-2013 | 22-09-2010 | 01-06-2013 | N.A. | N.A. | 516 | 558 | 1429
67 | SIMHADRI STPP STAGE-II UNIT-4 (2X500 MW) | 500 | 2007-03-26 | 11 | 0 | 3 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-06-25 | 2008-06-25 | 25-11-2008 | 24-03-2009 | N.A. | N.A. | 25-11-2009 | 31-03-2010 | 25-06-2010 | 07-12-2011 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 27-10-2010 | 18-02-2012 | N.A. | N.A. | 29-03-2009 | 08-04-2011 |  | 15-04-2011 | 29-05-2010 | 19-12-2011 | N.A. | N.A. | N.A. | N.A. | 19-08-2010 | 22-03-2012 | N.A. | N.A. | 29-08-2010 | 30-03-2012 | 2011-02-25 | 30-03-2012 | N.A. | N.A. | 25-02-2011 | 30-09-2012 | 25-02-2011 | 29-12-2012 | N.A. | N.A. | 457 | 457 | 1432
68 | MAUDA THERMAL POWER PROJECT UNIT-1 (2X500 MW) | 500 | 2008-11-28 | 3 | 0 | 1 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-09-27 | 2009-08-30 | 27-02-2010 | 02-06-2010 | N.A. | N.A. | 27-01-2011 | 08-04-2011 | 27-09-2011 | 20-12-2011 | N.A. | N.A. | 23-09-2011 | 09-01-2012 | 30-09-2011 | 11-01-2012 | 29-10-2011 | 11-02-2012 | 27-11-2011 | 03-03-2012 | N.A. | N.A. | 27-07-2010 | 19-01-2011 | 27-09-2010 | 25-02-2011 | 27-09-2011 | 30-12-2011 | 05-10-2011 | 15-01-2012 | 27-11-2011 | 07-03-2012 | 20-12-2011 | 28-03-2012 | N.A. | N.A. | 27-01-2012 | 08-04-2012 | 2012-04-27 | 19-04-2012 | N.A. | N.A. | 27-04-2012 | 13-03-2013 | 27-04-2012 | 28-01-2014 | N.A. | N.A. | 303 | 275 | 1246
69 | PARICHHA TPS EXTN UNIT-5 (2 X 250 MW) | 250 | 2006-08-04 | 13 | 2 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-05-04 | 2008-02-25 | 20-10-2007 | 05-09-2008 | N.A. | N.A. | 29-08-2008 | 20-04-2009 | 15-01-2009 | 26-02-2010 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 30-03-2009 | 31-12-2011 | N.A. | N.A. | 05-01-2008 | 20-06-2009 | N.A. | N.A. | 08-01-2009 | 11-04-2010 | N.A. | N.A. | 11-03-2009 | 10-01-2012 | 10-04-2009 | 18-01-2012 | N.A. | N.A. | 30-04-2009 | 05-02-2012 | 2009-07-02 | 24-05-2012 | N.A. | N.A. | 02-07-2009 | 17-07-2012 | 02-07-2009 | 24-06-2012 | N.A. | N.A. | 273 | 570 | 1063
70 | HARDUAGANJ EXTENSION UNIT-9 (2 X 250 MW ) | 250 | 2006-09-07 | 13 | 2 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | 10-05-2007 | 30-01-2008 | 2007-11-07 | 2008-11-20 | 07-05-2008 | 31-03-2009 | N.A. | N.A. | 07-04-2009 | 26-02-2010 | 07-08-2009 | 20-11-2011 | N.A. | N.A. | 22-08-2009 | 16-12-2011 | 26-08-2009 | 20-12-2011 | 27-10-2009 | 04-02-2012 | 07-11-2009 | 12-02-2012 | N.A. | N.A. | 07-08-2008 | 09-03-2010 | N.A. | N.A. | 07-08-2009 | 31-12-2011 | 08-08-2009 | 11-01-2012 | 07-09-2009 | 14-03-2012 | 07-11-2009 | 23-03-2012 | N.A. | N.A. | 07-12-2009 | 02-04-2012 | 2010-02-07 | 25-05-2012 | N.A. | N.A. | 07-02-2010 | 06-10-2012 | 07-02-2010 | 06-10-2012 | N.A. | N.A. | 426 | 805 | 1249
71 | RIHAND STPP STAGE-III UNIT- 5 (2X500 MW ) | 500 | 2009-01-28 | 13 | 0 | 1 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-11-27 | 2010-02-07 | 27-04-2010 | 06-08-2010 | N.A. | N.A. | 27-03-2011 | 30-06-2011 | 27-09-2011 | 31-01-2012 | 27-09-2011 | 19-02-2012 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 27-11-2011 | 19-03-2012 | N.A. | N.A. | 16-09-2010 | 28-09-2010 | 16-11-2010 | 30-11-2010 | 16-10-2011 | 30-01-2012 | N.A. | N.A. | 16-12-2011 | 25-03-2012 | 11-01-2012 | 24-04-2012 | N.A. | N.A. | 16-02-2012 | 19-05-2012 | 2012-04-27 | 25-05-2012 | N.A. | N.A. | 27-04-2012 | 19-11-2012 | 27-04-2012 | 07-03-2013 | N.A. | N.A. | 303 | 375 | 1185
72 | VINDHYACHAL STPP STAGE-IV UNIT-11 (2X500 MW) | 500 | 2009-01-29 | 4 | 0 | 1 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-11-28 | 2010-03-11 | 28-04-2010 | 30-06-2010 | N.A. | N.A. | 28-03-2011 | 30-06-2011 | 28-09-2011 | 14-02-2012 | 01-10-2011 | 19-02-2012 | 13-10-2011 | 17-02-2012 | 19-10-2011 | 19-02-2012 | 30-10-2011 | 11-03-2012 | 28-11-2011 | 26-03-2012 | N.A. | N.A. | 17-09-2010 | 29-10-2010 | 17-11-2010 | 17-12-2010 | 17-10-2011 | 31-12-2011 | 08-11-2011 | 27-01-2012 | 17-12-2011 | 21-03-2012 | 11-01-2012 | 24-04-2012 | N.A. | N.A. | 17-02-2012 | 13-06-2012 | 2012-04-28 | 14-06-2012 | N.A. | N.A. | 28-04-2012 | 01-03-2013 | 28-04-2012 | 28-09-2013 | N.A. | N.A. | 303 | 406 | 1185
73 | BINA UNIT-1 (2 X 250 MW) | 250 | 2008-09-20 | 4 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-07-20 | 2010-01-04 | 19-11-2009 | 24-03-2010 | N.A. | N.A. | 19-09-2010 | 04-02-2011 | 19-01-2011 | 25-02-2012 | N.A. | N.A. | N.A. | N.A. | 31-03-2011 | 07-03-2012 | N.A. | N.A. | 10-05-2011 | 04-05-2012 | N.A. | N.A. | 19-01-2010 | 31-10-2010 | N.A. | N.A. | 05-03-2011 | 11-07-2011 | N.A. | N.A. | 10-04-2011 | 11-04-2012 | 25-05-2011 | 26-05-2012 | N.A. | N.A. | 19-06-2011 | 27-06-2012 | 2011-07-19 | 12-08-2012 | N.A. | N.A. | 19-09-2011 | 29-08-2012 | 19-09-2011 | 21-03-2014 | N.A. | N.A. | 303 | 471 | 1032
74 | JHAJJAR(INDIRA GANDHI STPP) UNIT-3 (3X500MW) | 500 | 2007-07-06 | 16 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-11-05 | 2009-03-30 | 05-04-2009 | 12-11-2009 | N.A. | N.A. | 05-03-2010 | 30-04-2011 | 05-09-2010 | 17-05-2012 | 12-09-2010 | 10-06-2012 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 05-11-2010 | 03-08-2012 | N.A. | N.A. | 14-08-2009 | 16-02-2011 | 14-10-2009 | 12-07-2011 | 14-09-2010 | 02-06-2012 | N.A. | N.A. | 14-12-2010 | 31-08-2012 | 31-12-2010 | 28-10-2012 | N.A. | N.A. | 14-01-2011 | 07-11-2012 | 2011-03-31 | 07-11-2012 | N.A. | N.A. | 14-05-2011 | 26-04-2013 | 14-05-2011 | 30-11-2013 | N.A. | N.A. | 488 | 633 | 1364
75 | ADHUNIK TPP UNIT-1 (2X270 MW) | 270 | 2009-05-19 | 12 | 0 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-03-20 | 2010-03-18 | 30-07-2010 | 27-08-2010 | N.A. | N.A. | 30-04-2011 | 06-09-2011 | 30-09-2011 | 20-04-2012 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 10-10-2011 | 21-06-2012 | N.A. | N.A. | 30-09-2010 | 29-12-2010 | N.A. | N.A. | 24-08-2011 | 20-10-2011 | N.A. | N.A. | 24-09-2011 | 14-05-2012 | 24-10-2011 | 25-05-2012 | N.A. | N.A. | 24-11-2011 | 13-11-2012 | 2012-01-31 | 19-11-2012 | N.A. | N.A. | 31-01-2012 | 27-01-2013 | 31-01-2012 | 27-01-2013 | 31-01-2012 |  | 305 | 303 | 987
76 | KODERMA TPP UNIT-2 (2X500 MW) | 500 | 2007-07-21 | 12 | 1 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-07-20 | 2009-02-25 | 17-12-2008 | 09-07-2009 | N.A. | N.A. | 21-11-2009 | 09-09-2010 | 05-05-2010 | 26-04-2012 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 18-05-2009 | 29-01-2011 | N.A. | N.A. | 18-04-2010 | 20-07-2012 | N.A. | N.A. | 24-06-2010 | 10-10-2012 | 21-07-2010 | 23-01-2013 | N.A. | N.A. | 08-08-2010 | 11-02-2013 | 2010-09-21 | 15-02-2013 | N.A. | N.A. | 21-09-2010 | 14-06-2014 | 21-09-2010 | 14-01-2015 | N.A. | N.A. | 365 | 585 | 1158
77 | VALLUR TPS UNIT-2 (2X500 MW) | 500 | 2007-08-13 | 17 | 0 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-11-12 | 2009-07-18 | 13-04-2009 | 26-12-2009 | N.A. | N.A. | 12-04-2010 | 31-12-2010 | 12-11-2010 | 16-07-2012 | N.A. | N.A. | 01-12-2010 | 26-09-2012 | 12-12-2010 | 28-09-2012 | 25-01-2011 | 27-11-2012 | 28-02-2011 | 19-12-2012 | N.A. | N.A. | 12-09-2009 | 11-05-2011 | 12-11-2009 | 24-10-2011 | 12-11-2010 | 19-07-2012 | 12-11-2010 | 26-10-2012 | 12-12-2010 | 20-12-2012 | 12-02-2011 | 31-01-2013 | N.A. | N.A. | 12-03-2011 | 26-02-2013 | 2011-07-12 | 28-02-2013 | N.A. | N.A. | 12-07-2011 | 25-08-2013 | 12-07-2011 | 25-11-2013 | N.A. | N.A. | 457 | 705 | 1429
78 | UKAI UNIT-6 (1X500 MW) | 500 | 2007-10-06 | 14 | 1 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-03-02 | 2009-05-06 | 15-07-2009 | 31-12-2009 | N.A. | N.A. | 10-03-2010 | 14-10-2010 | 30-09-2010 | 07-03-2012 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 12-08-2009 | 27-06-2011 | 12-09-2009 | 13-07-2011 | 30-08-2010 | 27-02-2012 | N.A. | N.A. | 15-10-2010 | 03-07-2012 | 17-11-2010 | 21-09-2012 | N.A. | N.A. | 26-12-2010 | 30-09-2012 | 2011-02-06 | 05-03-2013 | N.A. | N.A. | 06-02-2011 | 06-07-2014 | 06-02-2011 | 06-07-2014 | N.A. | N.A. | 513 | 578 | 1219
79 | NORTH CHENNAI TPS STAGE-II UNIT-2 (2X600 MW) | 600 | 2008-08-16 | 17 | 1 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-07-17 | 2009-07-18 | 17-12-2009 | 25-03-2010 | N.A. | N.A. | 17-11-2010 | 28-03-2011 | 29-05-2011 | 11-04-2012 | N.A. | N.A. | N.A. | N.A. | 19-06-2011 | 24-06-2012 | 28-06-2011 | 11-09-2012 | 22-07-2011 | 09-10-2012 | N.A. | N.A. | 18-04-2010 | 12-05-2011 | N.A. | N.A. | 19-03-2011 | 03-08-2012 | 20-04-2011 | 17-08-2012 | 19-05-2011 | 28-09-2012 | 19-06-2011 | 13-10-2012 | N.A. | N.A. | 03-08-2011 | 17-12-2012 | 2011-11-18 | 09-03-2013 | N.A. | N.A. | 18-11-2011 | 08-05-2014 | 18-11-2011 | 08-05-2014 |  |  | 335 | 336 | 1189
80 | PARICHHA TPS EXTN UNIT-6 (2 X 250 MW) | 250 | 2006-08-04 | 13 | 2 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2007-09-04 | 2008-05-05 | 20-02-2008 | 04-12-2008 | N.A. | N.A. | 29-12-2008 | 16-11-2009 | 15-05-2009 | 28-04-2012 | N.A. | N.A. | 01-06-2009 | 11-05-2012 | 05-06-2009 | 15-05-2012 | 19-07-2009 | 09-08-2012 | 30-07-2009 | 17-08-2012 | N.A. | N.A. | 05-05-2008 | 15-12-2009 | N.A. | N.A. | 08-05-2009 | 20-05-2011 | 09-05-2009 | 04-04-2012 | 08-06-2009 | 19-08-2012 | 10-08-2009 | 30-08-2012 | N.A. | N.A. | 30-08-2009 | 17-09-2012 | 2009-11-02 | 11-03-2013 | N.A. | N.A. | 02-11-2009 | 18-04-2013 | 02-11-2009 | 18-04-2013 | N.A. | N.A. | 396 | 640 | 1186
81 | BELA (1X270 MW) | 270 | 2009-04-01 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-12-26 | 2010-03-06 | 26-06-2010 | 27-08-2010 | N.A. | N.A. | 15-04-2011 | 06-06-2011 | 15-08-2011 | 29-02-2012 | 15-09-2011 | 10-05-2012 | 20-09-2011 | 01-04-2012 | 25-09-2011 | 05-04-2012 | 19-10-2011 | 20-04-2012 | 15-10-2011 | 25-05-2012 | N.A. | N.A. | 25-08-2010 | 01-01-2011 | N.A. | N.A. | 16-07-2011 | 31-07-2012 | 18-09-2011 | 25-06-2012 | 15-09-2011 | 30-07-2012 | 15-10-2011 | 12-09-2012 | N.A. | N.A. | 28-11-2011 | 07-03-2013 | 2012-01-25 | 20-03-2013 | N.A. | N.A. | 25-01-2012 | 18-07-2013 | 25-01-2012 |  | N.A. | N.A. | 269 | 339 | 1029
82 | KORBA WEST (1 X 500 MW) | 500 | 2008-12-31 | 2 | 2 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-10-30 | 2010-05-24 | 31-05-2010 | 29-11-2010 | N.A. | N.A. | 30-05-2011 | 20-09-2011 | 30-10-2011 | 30-09-2012 | N.A. | N.A. | 27-11-2011 | 18-11-2012 | 05-12-2011 | 26-11-2012 | 24-12-2011 | 07-01-2013 | 31-12-2011 | 24-01-2013 | N.A. | N.A. | 30-08-2010 | 27-04-2011 | N.A. | N.A. | 21-09-2011 | 19-05-2012 | 28-09-2011 | 28-08-2012 | 27-10-2011 | 21-11-2012 | 21-01-2012 | 30-01-2013 | N.A. | N.A. | 28-02-2012 | 18-03-2013 | 2012-06-30 | 22-03-2013 | N.A. | N.A. | 30-06-2012 | 05-09-2013 | 30-06-2012 | 03-01-2014 | N.A. | N.A. | 303 | 509 | 1277
83 | SATPURA UNIT-10 ( 2 X 250 MW ) | 250 | 2009-02-27 | 4 | 2 | 1 | 0 | 27-02-2009 | 27-02-2009 | 01-07-2009 | 30-10-2009 | 01-09-2009 | 27-11-2009 | 2010-01-01 | 2010-04-08 | 30-04-2010 | 10-12-2010 | N.A. | N.A. | 31-01-2011 | 04-11-2011 | 31-07-2011 | 10-10-2012 | N.A. | N.A. | 31-08-2011 | 29-11-2012 | 31-10-2011 | 04-12-2012 | 31-10-2011 | 23-12-2012 | 31-10-2011 | 04-01-2013 | N.A. | N.A. | 01-10-2010 | 28-11-2011 | 01-12-2010 | 06-12-2011 | 30-09-2011 | 13-10-2012 | 31-10-2011 | 24-11-2012 | 30-10-2011 | 13-01-2013 | 19-11-2011 | 30-01-2013 | N.A. | N.A. | 30-11-2011 | 22-02-2013 | 2012-01-27 | 22-03-2013 | N.A. | N.A. | 27-01-2012 | 18-08-2013 | 27-01-2012 | 09-09-2014 |  |  | 308 | 405 | 1064
84 | VINDHYACHAL STPP STAGE-IV UNIT-12 (2X500 MW) | 500 | 2009-01-29 | 4 | 0 | 1 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-03-28 | 2010-06-24 | 28-08-2010 | 25-01-2011 | N.A. | N.A. | 28-07-2011 | 28-03-2012 | 28-01-2012 | 21-12-2012 | N.A. | N.A. | 01-02-2012 | 29-12-2012 | 06-02-2012 | 31-12-2012 | 28-02-2012 | 25-01-2013 | 28-03-2012 | 12-02-2013 | N.A. | N.A. | 17-01-2011 | 17-05-2012 | 17-03-2011 | 15-06-2012 | 17-02-2012 | 26-12-2012 | 17-03-2012 | 05-01-2013 | 17-04-2012 | 19-02-2013 | 07-05-2012 | 08-03-2013 | N.A. | N.A. | 28-06-2012 | 22-03-2013 | 2012-08-28 | 22-03-2013 | N.A. | N.A. | 28-08-2012 | 27-03-2014 | 28-08-2012 | 09-06-2014 | N.A. | N.A. | 423 | 511 | 1307
85 | AMRAVATI TPP PH-I UNIT-1 (5 X 270 MW) | 270 | 2009-11-30 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-07-31 | 2010-10-03 | 30-11-2010 | 01-03-2011 | N.A. | N.A. | 31-08-2011 | 11-03-2012 | 30-11-2011 | 25-08-2012 | N.A. | N.A. | 25-12-2011 | 15-10-2012 | 30-12-2011 | 19-10-2012 | 05-01-2012 | 11-01-2013 | 30-01-2012 | 31-01-2013 | N.A. | N.A. | 31-03-2011 | 11-05-2011 | N.A. | N.A. | 31-01-2012 | 09-06-2012 | 01-02-2012 | 08-09-2012 | 25-02-2012 | 26-12-2012 | 29-02-2012 | 19-01-2013 | N.A. | N.A. | 29-02-2012 | 09-03-2013 | 2012-03-30 | 25-03-2013 | N.A. | N.A. | 31-05-2012 | 08-06-2013 | 31-05-2012 | 31-05-2013 | N.A. | N.A. | 243 | 307 | 851
86 | MAUDA THERMAL POWER PROJECT UNIT-2 (2X500 MW) | 500 | 2008-11-28 | 3 | 0 | 1 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-02-27 | 2010-05-16 | 27-07-2010 | 05-12-2010 | N.A. | N.A. | 27-06-2011 | 30-11-2011 | 27-02-2012 | 27-11-2012 | N.A. | N.A. | 28-03-2012 | 30-11-2012 | 30-03-2012 | 03-12-2012 | 27-03-2012 | 23-12-2012 | 27-04-2012 | 31-01-2013 | N.A. | N.A. | 27-12-2010 | 25-05-2012 | 27-02-2011 | 02-07-2012 | 27-02-2012 | 30-12-2012 | 27-03-2012 | 12-12-2012 | 27-04-2012 | 25-02-2013 | 20-05-2012 | 09-03-2013 | N.A. | N.A. | 27-06-2012 | 26-03-2013 | 2012-09-27 | 29-03-2013 | N.A. | N.A. | 27-09-2012 | 29-03-2014 | 27-09-2012 | 26-04-2014 | N.A. | N.A. | 456 | 534 | 1399
87 | ADHUNIK TPP UNIT-2 (2X270 MW) | 270 | 2009-07-31 | 12 | 0 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-05-20 | 2010-10-31 | 30-09-2010 | 20-02-2011 | N.A. | N.A. | 30-06-2011 | 20-03-2012 | 30-11-2011 | 15-10-2012 | N.A. | N.A. | 01-12-2011 | 16-01-2013 | 05-12-2011 | 25-01-2013 | 06-12-2011 | 03-03-2013 | 21-12-2011 | 11-03-2013 | N.A. | N.A. | 30-11-2010 | 30-05-2011 | N.A. | N.A. | 24-10-2011 | 22-03-2013 | 05-11-2011 | 11-01-2013 | 24-11-2011 | 28-02-2013 | 24-12-2011 | 22-03-2013 | N.A. | N.A. | 24-01-2012 | 29-03-2013 | 2012-03-31 | 29-03-2013 | N.A. | N.A. | 31-03-2012 | 21-06-2013 | 31-03-2012 | 21-06-2013 | 31-03-2012 |  | 293 | 457 | 974
88 | BINA UNIT-2 (2 X 250 MW) | 250 | 2008-09-20 | 4 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-10-20 | 2010-01-28 | 19-02-2010 | 06-06-2010 | N.A. | N.A. | 19-12-2010 | 24-05-2011 | 19-04-2011 | 09-11-2012 | N.A. | N.A. | 24-06-2011 | 22-11-2012 | 30-06-2011 | 26-11-2012 | 20-07-2011 | 22-12-2012 | 10-08-2011 | 14-01-2013 | N.A. | N.A. | 19-04-2010 | 28-05-2011 | N.A. | N.A. | 05-06-2010 | 16-04-2012 | 30-06-2011 | 29-09-2012 | 30-07-2011 | 10-12-2012 | 24-08-2011 | 31-01-2013 | N.A. | N.A. | 19-09-2011 | 04-03-2013 | 2011-12-19 | 31-03-2013 | N.A. | N.A. | 19-12-2011 | 06-04-2013 | 19-12-2011 | 21-03-2014 | N.A. | N.A. | 395 | 495 | 1185
89 | NORTH CHENNAI TPS STAGE-II UNIT-1 (2X600 MW) | 600 | 2008-02-18 | 17 | 1 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-01-18 | 2009-01-20 | 20-06-2009 | 12-04-2010 | N.A. | N.A. | 21-05-2010 | 10-09-2011 | 30-11-2010 | 28-11-2012 | N.A. | N.A. | 21-12-2010 | 11-01-2013 | 23-12-2010 | 13-01-2013 | 30-12-2010 | 24-03-2013 | 23-01-2011 | 30-04-2013 | N.A. | N.A. | 20-10-2009 | 28-04-2011 | N.A. | N.A. | 20-09-2010 | 06-06-2013 | 22-10-2010 | 02-02-2013 | 20-11-2010 | 07-05-2013 | 21-12-2010 | 06-06-2013 | N.A. | N.A. | 20-02-2011 | 30-06-2013 | 2011-05-22 | 13-09-2013 | N.A. | N.A. | 22-05-2011 | 18-03-2014 | 22-05-2011 | 18-03-2014 |  |  | 335 | 337 | 1189
90 | CHHABRA UNIT-3 (2X250 MW) | 250 | 2008-08-20 | 1 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-07-27 | 2010-06-23 | 22-01-2010 | 31-12-2010 | N.A. | N.A. | 23-09-2010 | 19-03-2012 | 15-02-2011 | 31-12-2012 | N.A. | N.A. | 26-02-2011 | 19-01-2013 | 02-03-2011 | 22-01-2013 | 20-03-2011 | 03-03-2013 | 20-04-2011 | 15-03-2013 | N.A. | N.A. | 22-02-2010 | 27-08-2011 | N.A. | N.A. | 27-03-2011 | 25-01-2013 | 07-04-2011 | 25-01-2013 | 04-05-2011 | 14-03-2013 | N.A. | N.A. | N.A. | N.A. | 31-05-2011 | 15-05-2013 | 2011-07-31 | 14-09-2013 | N.A. | N.A. | 31-07-2011 | 31-12-2013 | 31-07-2011 | 31-12-2013 | N.A. | N.A. | 341 | 672 | 1075
91 | RIHAND STPP STAGE-III UNIT- 6 (2X500 MW ) | 500 | 2009-01-28 | 13 | 0 | 1 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-03-27 | 2010-04-25 | 27-08-2010 | 22-01-2011 | N.A. | N.A. | 27-07-2011 | 16-02-2012 | 27-01-2012 | 29-12-2012 | N.A. | N.A. | 27-01-2012 | 24-01-2013 | 30-01-2012 | 31-01-2013 | 27-02-2012 | 22-06-2013 | 27-03-2012 | 05-07-2013 | N.A. | N.A. | 16-01-2011 | 26-07-2012 | 16-03-2011 | 07-10-2012 | 16-02-2012 | 27-02-2013 | 17-03-2012 | 27-05-2013 | 17-04-2012 | 02-08-2013 | 11-05-2012 | 12-09-2013 | N.A. | N.A. | 27-05-2012 | 30-09-2013 | 2012-08-27 | 07-10-2013 | N.A. | N.A. | 27-08-2012 | 27-03-2014 | 27-08-2012 | 01-05-2014 | N.A. | N.A. | 423 | 452 | 1307
92 | SHREE SINGAJI (EARLIER MALWA) TPP STAGE-1 UNIT-1 (2X600 MW) | 600 | 2008-12-12 | 4 | 2 | 3 | 0 | 12-12-2008 | 12-12-2008 | 12-06-2009 | 12-07-2009 | 12-07-2009 | 10-02-2010 | 2009-10-12 | 2010-06-30 | 11-05-2010 | 08-03-2011 | N.A. | N.A. | 11-04-2011 | 25-04-2012 | 11-11-2011 | 01-01-2013 | N.A. | N.A. | 11-11-2011 | 13-05-2013 | 30-11-2011 | 17-05-2013 | 11-12-2011 | 04-06-2013 | 11-12-2011 | 09-07-2013 | N.A. | N.A. | 12-08-2010 | 31-12-2011 | 12-10-2010 | 31-12-2011 | 11-10-2011 | 09-03-2013 | 01-10-2011 | 07-05-2013 | 11-11-2011 | 15-06-2013 | 05-01-2012 | 09-07-2013 | N.A. | N.A. | 11-01-2012 | 31-08-2013 | 2012-03-11 | 18-11-2013 | N.A. | N.A. | 11-06-2012 | 01-02-2014 | 11-05-2012 | 14-11-2014 |  |  | 304 | 565 | 1185
93 | BARH STPP STAGE-II UNIT-4 (2X660MW) | 660 | 2008-03-31 | 8 | 0 | 0 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-03-31 | 2009-08-26 | N.A. | N.A. | N.A. | N.A. | 30-09-2010 | 31-05-2012 | 25-04-2011 | 25-11-2012 | N.A. | N.A. | 15-05-2011 | 17-02-2013 | 25-05-2011 | 26-02-2013 | 01-07-2011 | 24-04-2013 | 31-07-2011 | 01-06-2013 | N.A. | N.A. | 14-08-2010 | 18-02-2011 | 14-10-2010 | 27-10-2011 | 14-09-2011 | 28-02-2013 | 14-11-2011 | 17-04-2013 | 14-12-2011 | 31-05-2013 | 14-01-2012 | 23-08-2013 | N.A. | N.A. | 14-02-2012 | 12-10-2013 | 2012-06-14 | 30-11-2013 | N.A. | N.A. | 14-06-2012 | 15-11-2014 | 14-06-2012 | 14-03-2015 | 14-06-2012 |  | 365 | 513 | 1536
94 | SATPURA UNIT-11 ( 2 X 250 MW ) | 250 | 2009-02-27 | 4 | 2 | 1 | 0 | 27-02-2009 | 27-02-2009 | 01-07-2009 | 30-10-2009 | 01-01-2010 | 07-01-2010 | 2010-05-01 | 2010-07-01 | 30-08-2010 | 16-02-2011 | N.A. | N.A. | 31-05-2011 | 30-04-2012 | 30-11-2011 | 30-06-2013 | N.A. | N.A. | 31-12-2011 | 21-07-2013 | 29-02-2012 | 25-07-2013 | 29-02-2012 | 18-08-2013 | 29-02-2012 | 29-08-2013 | N.A. | N.A. | 01-02-2011 | 18-08-2012 | 01-04-2011 | 15-05-2012 | 30-01-2012 | 30-05-2013 | 29-02-2012 | 28-06-2013 | 29-02-2012 | 12-08-2013 | 19-03-2012 | 08-09-2013 | N.A. | N.A. | 30-03-2012 | 02-10-2013 | 2012-05-27 | 25-12-2013 | N.A. | N.A. | 27-05-2012 | 16-03-2014 | 27-05-2012 | 23-05-2014 | N.A. | N.A. | 428 | 489 | 1185
95 | AMRAVATI TPP PH-I UNIT-2 (5 X 270 MW) | 270 | 2009-11-30 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-09-30 | 2010-10-20 | 31-01-2011 | 25-03-2011 | N.A. | N.A. | 31-10-2011 | 31-03-2012 | 31-01-2012 | 31-03-2013 | N.A. | N.A. | 25-02-2012 | 20-06-2013 | 29-02-2012 | 27-06-2013 | 05-03-2012 | 27-10-2013 | 30-03-2012 | 12-11-2013 | N.A. | N.A. | 31-05-2011 | 16-09-2011 | N.A. | N.A. | 31-03-2012 | 20-02-2013 | 01-04-2012 | 27-04-2013 | 25-04-2012 | 21-07-2013 | 30-04-2012 | 13-08-2013 | N.A. | N.A. | 30-04-2012 | 01-02-2014 | 2012-05-30 | 17-02-2014 | N.A. | N.A. | 31-07-2012 | 28-03-2014 | 31-07-2012 | 31-05-2014 | N.A. | N.A. | 304 | 324 | 912
96 | DB SUPER TPP (JANJGIR CHAMPA) UNIT-1 (2X600 MW) | 600 | 2010-06-24 | 2 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-05-25 | 2011-03-14 | 24-09-2011 | 06-10-2011 | N.A. | N.A. | 26-07-2012 | 17-08-2012 | 25-12-2012 | 22-03-2013 | N.A. | N.A. | N.A. | N.A. | 20-01-2013 | 14-06-2013 | 25-01-2013 | 02-08-2013 | 24-02-2013 | 13-08-2013 | N.A. | N.A. | 25-12-2011 | 25-04-2012 | N.A. | N.A. | 25-12-2012 | 16-08-2013 | 01-03-2013 | 07-07-2013 | 27-03-2013 | 21-08-2013 | 27-04-2013 | 16-09-2013 | N.A. | N.A. | 23-05-2013 | 09-10-2013 | 2013-08-22 | 23-02-2014 | N.A. | N.A. | 22-09-2013 | 28-02-2014 | 22-09-2013 | 23-08-2014 | 22-09-2013 |  | 335 | 263 | 1155
98 | VALLUR TPS UNIT-3 (1X500 MW) | 500 | 2009-07-28 | 17 | 0 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-05-27 | 2010-10-22 | 27-10-2010 | 29-07-2011 | N.A. | N.A. | 27-10-2011 | 30-09-2012 | 27-05-2012 | 31-08-2013 | N.A. | N.A. | 11-06-2012 | 13-11-2013 | 20-06-2012 | 18-11-2013 | 27-07-2012 | 23-12-2013 | 27-08-2012 | 08-01-2014 | N.A. | N.A. | 27-03-2011 | 15-06-2012 | 27-05-2011 | 15-09-2012 | 27-05-2012 | 24-09-2013 | 27-07-2012 | 13-12-2013 | 27-08-2012 | 22-01-2014 | 15-09-2012 | 14-02-2014 | N.A. | N.A. | 27-09-2012 | 28-02-2014 | 2013-01-27 | 28-02-2014 | N.A. | N.A. | 28-02-2013 | 26-02-2015 | 27-01-2013 | 03-06-2015 | N.A. | N.A. | 303 | 451 | 1279
99 | JINDAL POWER LTD-RAIGARH UNIT # 1 (4X600MW) (NUMBER AT SITE-2) | 600 | 2008-12-27 | 2 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-11-16 | 2011-11-16 | 25-02-2012 | 06-03-2012 | N.A. | N.A. | 12-11-2012 | 31-01-2013 | 02-03-2013 | 30-03-2013 | N.A. | N.A. | 29-03-2013 | 07-06-2013 | 02-04-2013 | 09-06-2013 | 04-03-2013 | 30-07-2013 | 15-03-2013 | 15-08-2013 | N.A. | N.A. | 17-03-2012 | 04-10-2012 | N.A. | N.A. | 19-01-2013 | 30-05-2013 | 01-03-2013 | 20-05-2013 | 20-03-2013 | 30-08-2013 | 25-03-2013 | 11-09-2013 | N.A. | N.A. | 15-05-2013 | 30-09-2013 | 2013-06-15 | 10-03-2014 | N.A. | N.A. | 15-06-2013 | 14-03-2014 | 15-06-2013 | 26-08-2014 |  |  | 1054 | 1054 | 1631
100 | MARWA TPP UNIT-1 (2X500 MW) | 500 | 2008-12-31 | 2 | 2 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-01-30 | 2010-02-15 | 31-08-2010 | 06-08-2010 | N.A. | N.A. | 30-08-2011 | 05-10-2011 | 30-01-2012 | 14-01-2013 | N.A. | N.A. | 21-02-2012 | 01-08-2013 | 27-02-2012 | 21-08-2013 | 14-03-2012 | 01-10-2013 | 31-03-2012 | 27-10-2013 | N.A. | N.A. | 30-11-2010 | 07-03-2011 | N.A. | N.A. | 21-12-2011 | 23-02-2013 | 28-12-2011 | 14-02-2013 | 27-01-2012 | 15-08-2013 | 21-04-2012 | 09-11-2013 | N.A. | N.A. | 28-05-2012 | 21-12-2013 | 2012-09-30 | 30-03-2014 | N.A. | N.A. | 30-09-2012 | 31-03-2016 | 30-09-2012 | 16-01-2018 | N.A. | N.A. | 395 | 411 | 1369
101 | JINDAL POWER LTD-RAIGARH UNIT # 2 (4X600MW) (NUMBER AT SITE-3) | 600 | 2008-12-27 | 2 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2012-02-14 | 2011-11-16 | 25-05-2012 | 05-07-2012 | N.A. | N.A. | 10-02-2013 | 16-04-2013 | 31-05-2013 | 25-11-2013 | N.A. | N.A. | 29-06-2013 | 26-11-2013 | 02-07-2013 | 27-11-2013 | 04-06-2013 | 18-12-2013 | 15-06-2013 | 14-01-2014 | N.A. | N.A. | 15-06-2012 | 27-07-2012 | N.A. | N.A. | 19-04-2013 | 30-08-2013 | 01-06-2013 | 08-10-2013 | 20-06-2013 | 20-01-2014 | 25-06-2013 | 10-02-2014 | N.A. | N.A. | 15-08-2013 | 22-02-2014 | 2013-09-15 | 30-03-2014 | N.A. | N.A. | 15-09-2013 | 31-03-2014 | 15-09-2013 | 13-08-2014 |  |  | 1144 | 1054 | 1723
102 | DPL DURGAPUR UNIT-8 (250 MW) | 250 | 2010-07-28 | 0 | 1 | 0 | 0 | 28-07-2010 | 28-07-2010 | 04-10-2010 | 31-01-2011 | 12-01-2011 | 25-02-2011 | 2011-06-08 | 2011-09-30 | 19-11-2011 | 19-04-2012 | N.A. | N.A. | 07-11-2012 | 24-01-2013 | 24-07-2013 | 20-01-2014 | N.A. | N.A. | 02-08-2013 | 06-02-2014 | 05-08-2013 | 07-02-2014 | 10-08-2013 | 26-02-2014 | 02-09-2013 | 04-03-2014 | N.A. | N.A. | 09-04-2012 | 28-06-2012 | 06-07-2012 | 20-09-2012 | 19-05-2013 | 19-07-2013 | 23-05-2013 | 11-11-2013 | 19-07-2013 | 19-02-2014 | 31-10-2013 | 03-03-2014 | N.A. | N.A. | 28-11-2013 | 28-03-2014 | 2013-12-18 | 31-03-2014 | N.A. | N.A. | 15-01-2014 | 07-10-2014 | 28-12-2013 | 12-06-2015 | N.A. | N.A. | 315 | 429 | 1239
103 | AVANTHA POWER (KWPCL) PHASE-I (1X600MW) | 600 | 2009-05-01 | 2 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-04-30 | 2010-11-20 | 31-10-2010 | 21-05-2011 | N.A. | N.A. | 31-10-2011 | 06-07-2012 | 30-04-2012 | 06-03-2013 | N.A. | N.A. | 15-05-2012 | 11-07-2013 | 30-05-2012 | 15-07-2013 | 01-06-2012 | 01-08-2013 | 30-06-2012 | 23-08-2013 | N.A. | N.A. | 31-01-2011 | 15-03-2012 | 31-03-2011 | 25-05-2012 | 31-03-2012 | 27-09-2013 | 10-04-2012 | 22-06-2013 | 30-04-2012 | 05-09-2013 | 30-06-2012 | 28-09-2013 | N.A. | N.A. | 31-07-2012 | 08-10-2013 | 2012-10-31 | 31-03-2014 | N.A. | N.A. | 31-10-2012 | 31-03-2014 | 31-10-2012 | 01-03-2015 | 31-10-2012 |  | 364 | 568 | 1279
104 | JITPL DERANG UNIT-1(2 X 600 MW) | 600 | 2009-06-26 | 18 | 0 | 3 | 0 | N.A. | N.A. | 20-06-2010 | 20-06-2010 | N.A. | N.A. | 2010-08-16 | 2010-12-10 | 15-01-2011 | 05-08-2011 | N.A. | N.A. | 22-10-2011 | 13-02-2013 | 22-04-2012 | 10-12-2013 | N.A. | N.A. | 25-04-2012 | 19-12-2013 | 22-05-2012 | 26-12-2013 | 08-06-2012 | 24-01-2014 | 22-07-2012 | 12-02-2014 | N.A. | N.A. | 22-02-2011 | 20-04-2012 | 22-03-2011 | 04-07-2012 | 09-05-2012 | 08-08-2013 | 09-05-2012 | 06-11-2013 | 22-06-2012 | 15-01-2014 | 13-07-2012 | 14-02-2014 | N.A. | N.A. | 10-08-2012 | 29-03-2014 | 2012-08-26 | 10-05-2014 | N.A. | N.A. | 26-08-2012 | 18-04-2015 | 26-08-2012 | 24-04-2015 | N.A. | N.A. | 416 | 532 | 1157
105 | CHHABRA UNIT-4 (2X250 MW) | 250 | 2008-08-20 | 1 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-09-27 | 2010-12-20 | 22-03-2010 | 06-06-2011 | N.A. | N.A. | 23-11-2010 | 07-12-2012 | 15-04-2011 | 17-01-2014 | N.A. | N.A. | 26-04-2011 | 20-01-2014 | 02-05-2011 | 24-01-2014 | 20-05-2011 | 11-03-2014 | 20-06-2011 | 20-03-2014 | N.A. | N.A. | 22-04-2010 | 20-10-2012 | N.A. | N.A. | 27-05-2011 | 29-03-2014 | 07-06-2011 | 04-02-2014 | 04-07-2011 | 12-03-2014 | 10-07-2011 | 29-03-2014 | N.A. | N.A. | 31-07-2011 | 23-04-2014 | 2011-09-30 | 30-06-2014 | N.A. | N.A. | 30-09-2011 | 30-12-2014 | 30-09-2011 | 30-12-2014 | N.A. | N.A. | 403 | 852 | 1136
106 | SHREE SINGAJI (EARLIER MALWA) TPP STAGE-1 UNIT-2 (2X600 MW) | 600 | 2008-12-12 | 4 | 2 | 3 | 0 | 12-12-2008 | 12-12-2008 | 12-06-2009 | 12-07-2009 | 12-11-2009 | 05-04-2010 | 2010-02-12 | 2010-12-03 | 11-09-2010 | 30-09-2011 | N.A. | N.A. | 11-08-2011 | 30-11-2012 | 11-03-2012 | 25-12-2013 | N.A. | N.A. | 24-03-2012 | 11-02-2014 | 31-03-2012 | 13-02-2014 | 01-04-2012 | 07-03-2014 | 11-04-2012 | 16-05-2014 | N.A. | N.A. | 12-12-2010 | 28-09-2012 | 12-02-2011 | 25-12-2012 | 11-02-2012 | 23-02-2014 | 11-03-2012 | 06-03-2014 | 11-03-2012 | 18-09-2014 | 05-05-2012 | 22-09-2014 | N.A. | N.A. | 11-05-2012 | 11-10-2014 | 2012-07-11 | 15-10-2014 | N.A. | N.A. | 11-10-2012 | 28-12-2014 | 11-09-2012 | 31-07-2015 | N.A. | N.A. | 427 | 721 | 1307
107 | JINDAL POWER LTD-RAIGARH UNIT # 3 (4X600MW) (NUMBER AT SITE-1) | 600 | 2008-12-27 | 2 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2012-08-15 | 2012-11-23 | 11-12-2012 | 27-02-2013 | N.A. | N.A. | 05-09-2013 | 30-10-2013 | 05-02-2014 | 25-01-2014 | N.A. | N.A. | 08-03-2014 | 06-02-2014 | 11-03-2014 | 09-02-2014 | 15-03-2014 | 20-02-2014 | 05-04-2014 | 07-03-2014 | N.A. | N.A. | 18-01-2013 | 01-10-2013 | N.A. | N.A. | 15-01-2014 | 10-02-2014 | 15-02-2014 | 15-12-2013 | 15-03-2014 | 14-03-2014 | 15-04-2014 | 28-03-2014 | N.A. | N.A. | 15-05-2014 | 31-03-2014 | 2014-06-16 | 07-01-2015 | N.A. | N.A. | 30-08-2014 | 14-01-2015 | 15-08-2014 | 14-01-2015 |  |  | 1327 | 1427 | 1997
108 | NEYVELI TPS II EXPANSION UNIT-2 (2X250 MW) | 250 | 2005-08-19 | 17 | 1 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2006-10-20 | 2007-07-25 | 19-03-2007 | 31-05-2008 | N.A. | N.A. | 18-01-2008 | 30-07-2010 | 19-06-2008 | 28-02-2013 | N.A. | N.A. | 01-07-2008 | 23-05-2013 | 10-07-2008 | 26-05-2013 | 01-08-2008 | 23-07-2013 | 01-09-2008 | 14-08-2013 | N.A. | N.A. | 19-05-2007 | 30-06-2009 | N.A. | N.A. | 17-05-2008 | 06-05-2011 | 16-06-2008 | 14-02-2012 | 18-07-2008 | 06-06-2012 | 18-08-2008 | 09-08-2012 | N.A. | N.A. | 19-09-2008 | 23-11-2014 | 2008-11-19 | 24-01-2015 | N.A. | N.A. | 22-11-2008 | 21-04-2015 | 19-12-2008 | 04-05-2016 | N.A. | N.A. | 427 | 705 | 1188
109 | JITPL, DERANG UNIT-2 (2 X 600 MW) | 600 | 2009-06-26 | 18 | 0 | 3 | 0 | N.A. | N.A. | 20-06-2010 | 20-06-2010 | N.A. | N.A. | 2010-11-14 | 2011-04-29 | 13-04-2011 | 27-12-2011 | N.A. | N.A. | 20-01-2012 | 18-05-2013 | 21-07-2012 | 02-08-2014 | N.A. | N.A. | 25-07-2012 | 10-08-2014 | 22-08-2012 | 14-08-2014 | 06-09-2012 | 27-09-2014 | 21-10-2012 | 29-10-2014 | N.A. | N.A. | 22-05-2011 | 01-08-2013 | 22-06-2011 | 06-11-2013 | 10-08-2012 | 25-07-2014 | 10-08-2012 | 18-08-2014 | 22-09-2012 | 21-10-2014 | 11-10-2012 | 11-11-2014 | N.A. | N.A. | 08-11-2012 | 14-12-2014 | 2012-11-24 | 24-01-2015 | N.A. | N.A. | 24-11-2012 | 07-02-2015 | 24-11-2012 | 21-02-2015 | N.A. | N.A. | 506 | 672 | 1247
110 | AMRAVATI TPP PH-I UNIT-3 (5 X 270 MW) | 270 | 2009-11-30 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-11-30 | 2011-01-06 | 31-03-2011 | 17-06-2011 | N.A. | N.A. | 31-12-2011 | 11-10-2012 | 31-03-2012 | 12-03-2014 | N.A. | N.A. | 25-04-2012 | 05-10-2014 | 30-04-2012 | 12-10-2014 | 05-05-2012 | 10-12-2014 | 30-05-2012 | 28-12-2014 | N.A. | N.A. | 31-07-2011 | 20-01-2012 | N.A. | N.A. | 31-05-2012 | 19-06-2013 | 01-06-2012 | 24-10-2013 | 25-06-2012 | 30-12-2013 | 30-06-2012 | 16-01-2014 | N.A. | N.A. | 30-06-2012 | 18-01-2015 | 2012-07-30 | 29-01-2015 | N.A. | N.A. | 30-09-2012 | 02-02-2015 | 30-09-2012 | 02-02-2015 | N.A. | N.A. | 365 | 402 | 973
111 | BARH STPP STAGE-II UNIT-5 (2X660MW) | 660 | 2008-03-31 | 8 | 0 | 0 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-09-30 | 2010-02-26 | N.A. | N.A. | N.A. | N.A. | 30-03-2011 | 29-11-2013 | 30-10-2011 | 11-06-2014 | N.A. | N.A. | 15-12-2011 | 13-10-2014 | 21-12-2011 | 29-10-2014 | 01-12-2012 | 12-11-2014 | 30-01-2012 | 07-01-2015 | N.A. | N.A. | 14-02-2011 | 25-01-2012 | 14-04-2011 | 01-01-2013 | 14-03-2012 | 21-04-2014 | 14-05-2012 | 09-02-2014 | 14-06-2012 | 04-12-2014 | 14-07-2012 | 05-12-2014 | N.A. | N.A. | 14-08-2012 | 01-03-2015 | 2012-12-14 | 04-03-2015 | N.A. | N.A. | 14-12-2012 | 18-02-2016 | 14-12-2012 | 20-03-2017 | N.A. | N.A. | 548 | 697 | 1719
112 | AMRAVATI TPP PH-I UNIT-4 (5 X 270 MW) | 270 | 2009-11-30 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-01-31 | 2011-02-17 | 31-05-2011 | 27-11-2011 | N.A. | N.A. | 29-02-2012 | 30-03-2013 | 31-05-2012 | 26-12-2014 | N.A. | N.A. | 25-06-2012 | 29-12-2014 | 30-06-2012 | 01-01-2015 | 05-05-2012 | 12-01-2015 | 30-05-2012 | 24-01-2015 | N.A. | N.A. | 30-09-2011 | 29-06-2012 | N.A. | N.A. | 31-07-2012 | 04-10-2013 | 01-08-2012 | 09-06-2014 | 25-08-2012 | 07-10-2014 | 31-08-2012 | 02-12-2014 | N.A. | N.A. | 30-08-2012 | 02-03-2015 | 2012-09-30 | 04-03-2015 | N.A. | N.A. | 30-11-2012 | 07-03-2015 | 30-11-2012 | 07-03-2015 | N.A. | N.A. | 427 | 444 | 1035
113 | TUTICORIN UNIT-1 (2X500 MW ) | 500 | 2009-01-28 | 17 | 2 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-11-25 | 2010-11-03 | 29-04-2010 | 29-09-2011 | N.A. | N.A. | 31-03-2011 | 28-09-2012 | 31-10-2011 | 19-03-2014 | N.A. | N.A. | 01-11-2011 | 05-04-2014 | 13-11-2011 | 10-04-2014 | 15-11-2011 | 21-05-2014 | 10-12-2011 | 19-06-2014 | N.A. | N.A. | 15-09-2010 | 10-07-2012 | N.A. | N.A. | 14-10-2011 | 23-10-2013 | 30-10-2011 | 20-01-2014 | 14-12-2011 | 06-06-2014 | 30-12-2011 | 20-07-2014 | N.A. | N.A. | 28-01-2012 | 18-02-2015 | 2012-03-28 | 10-03-2015 | N.A. | N.A. | 31-03-2012 | 06-06-2015 | 28-04-2012 | 22-01-2016 | N.A. | N.A. | 301 | 644 | 1155
114 | AMRAVATI TPP PH-I UNIT-5 (5 X 270 MW) | 270 | 2009-11-30 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-03-31 | 2011-03-25 | 31-07-2011 | 13-01-2012 | N.A. | N.A. | 30-04-2012 | 06-12-2014 | 31-07-2012 | 26-01-2015 | N.A. | N.A. | 25-08-2012 | 29-01-2015 | 30-08-2012 | 02-02-2015 | 05-09-2012 | 06-02-2015 | 30-09-2012 | 15-02-2015 | N.A. | N.A. | 30-11-2011 | 16-07-2013 | N.A. | N.A. | 30-09-2012 | 19-10-2014 | 01-10-2012 | 10-12-2014 | 25-10-2012 | 09-02-2015 | 31-10-2012 | 26-02-2015 | N.A. | N.A. | 30-10-2012 | 11-03-2015 | 2012-11-30 | 12-03-2015 | N.A. | N.A. | 31-01-2013 | 25-03-2015 | 31-01-2013 | 01-12-2015 | N.A. | N.A. | 486 | 480 | 1096
115 | DB SUPER TPP (JANJGIR CHAMPA) UNIT-2 (2X600 MW) | 600 | 2010-06-24 | 2 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-09-25 | 2011-08-05 | 24-01-2012 | 24-02-2012 | N.A. | N.A. | 25-11-2012 | 04-03-2013 | 25-04-2013 | 24-12-2013 | N.A. | N.A. | 10-05-2013 | 09-01-2014 | 20-05-2013 | 13-01-2014 | 25-05-2013 | 28-02-2014 | 24-06-2013 | 07-03-2014 | N.A. | N.A. | 25-03-2012 | 15-12-2012 | N.A. | N.A. | 25-04-2013 | 16-01-2014 | 01-07-2013 | 20-01-2014 | 27-07-2013 | 02-03-2014 | 27-08-2013 | 26-03-2014 | N.A. | N.A. | 23-10-2013 | 30-03-2014 | 2013-12-22 | 24-03-2015 | N.A. | N.A. | 22-01-2014 | 21-03-2016 | 22-01-2014 | 21-03-2016 |  |  | 458 | 407 | 1277
116 | JINDAL POWER LTD-RAIGARH UNIT # 4 (4X600MW) (NUMBER AT SITE-4) | 600 | 2008-12-27 | 2 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2012-09-15 | 2013-05-03 | 31-01-2013 | 18-10-2013 | N.A. | N.A. | 16-11-2013 | 26-07-2014 | 02-05-2014 | 15-01-2015 | N.A. | N.A. | 08-05-2014 | 21-01-2015 | 28-05-2014 | 24-01-2015 | 10-06-2014 | 08-02-2015 | 30-06-2014 | 23-02-2015 | N.A. | N.A. | 15-03-2013 | 10-02-2014 | N.A. | N.A. | 14-04-2014 | 22-10-2014 | 14-05-2014 | 23-10-2014 | 30-06-2014 | 13-02-2015 | 15-07-2014 | 16-03-2015 | N.A. | N.A. | 14-08-2014 | 26-03-2015 | 2014-09-15 | 28-03-2015 | N.A. | N.A. | 30-11-2014 | 11-12-2016 | 15-11-2014 | 11-12-2016 | N.A. | N.A. | 1358 | 1588 | 2088
117 | SIKKA TPS UNIT-3 ( 2X250 MW ) | 250 | 2011-07-10 | 14 | 1 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | 01-08-2011 | 09-08-2011 | 2011-12-15 | 2011-10-24 | 13-05-2012 | 29-03-2012 | N.A. | N.A. | 13-01-2013 | 02-03-2013 | 13-06-2013 | 22-03-2014 | N.A. | N.A. | 13-07-2013 | 17-11-2014 | 20-07-2013 | 19-11-2014 | 13-05-2013 | 08-12-2014 | 22-09-2013 | 31-12-2014 | N.A. | N.A. | 13-06-2012 | 30-10-2012 | N.A. | N.A. | 03-05-2013 | 06-06-2014 | 03-06-2013 | 15-07-2014 | 18-06-2013 | 22-10-2014 | 13-07-2013 | 06-12-2014 | N.A. | N.A. | 27-08-2013 | 09-02-2015 | 2013-10-10 | 29-03-2015 | N.A. | N.A. | 10-10-2013 | 14-09-2015 | 10-10-2013 |  | N.A. | N.A. | 158 | 106 | 823
118 | CHANDRAPUR MEGA POWER PROJECT UNIT-8 (2X500 MW) | 500 | 2009-02-09 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-01-09 | 2010-06-01 | 09-07-2010 | 29-03-2011 | N.A. | N.A. | 09-06-2011 | 05-06-2012 | 09-01-2012 | 30-03-2014 | N.A. | N.A. | 09-02-2012 | 24-05-2014 | 09-03-2012 | 27-06-2014 | 09-03-2012 | 21-09-2014 | 09-04-2012 | 18-10-2014 | N.A. | N.A. | 09-10-2010 | 25-04-2012 | N.A. | N.A. | 09-12-2011 | 23-11-2013 | 09-01-2012 | 03-03-2014 | 09-02-2012 | 09-08-2014 | 09-03-2012 | 15-12-2014 | 09-04-2012 | 11-01-2015 | 09-04-2012 | 11-01-2015 | 2012-05-09 | 29-03-2015 | N.A. | N.A. | 09-07-2012 | 04-06-2016 | 09-07-2012 | 10-11-2015 | N.A. | N.A. | 334 | 477 | 1185
119 | MUZAFFARPUR TPP STG.II UNIT-3 (2X195 MW) | 195 | 2010-03-12 | 8 | 0 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-12-11 | 2011-08-30 | 11-04-2011 | 06-03-2012 | N.A. | N.A. | 11-01-2012 | 25-02-2013 | 11-05-2012 | 08-11-2014 | N.A. | N.A. | 11-05-2012 | 12-12-2014 | 30-05-2012 | 17-12-2014 | 20-06-2012 | 23-01-2015 | 11-07-2012 | 12-02-2015 | N.A. | N.A. | 11-08-2011 | 10-12-2012 | N.A. | N.A. | 11-06-2012 | 30-09-2014 | 20-06-2012 | 09-01-2015 | 20-07-2012 | 12-03-2015 | 20-08-2012 | 23-03-2015 | N.A. | N.A. | 11-09-2012 | 31-03-2015 | 2012-11-11 | 31-03-2015 | N.A. | N.A. | 11-11-2012 | 10-03-2017 | 11-11-2012 | 19-12-2017 | N.A. | N.A. | 274 | 536 | 975
120 | KRISHNAPATNAM UNIT-1 (2X800 MW) | 800 | 2008-08-29 | 11 | 15 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-01-27 | 2011-02-20 | N.A. | N.A. | 27-09-2010 | 30-10-2011 | 30-07-2011 | 24-03-2013 | 18-01-2012 | 13-08-2013 | N.A. | N.A. | N.A. | N.A. | 29-02-2012 | 09-09-2013 | N.A. | N.A. |  | 13-03-2014 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 31-05-2012 | 31-03-2014 | 2012-07-28 | 28-08-2014 | N.A. | N.A. | 22-08-2012 | 04-02-2015 | 28-07-2012 | 04-02-2015 | N.A. | N.A. | 516 | 905 | 1429
121 | KRISHNAPATNAM UNIT-2 (2X800 MW) | 800 | 2008-08-29 | 11 | 15 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-07-27 | 2011-04-27 | N.A. | N.A. | 27-03-2011 | 31-12-2011 | 30-01-2012 | 17-12-2013 | 18-07-2012 | 22-06-2014 | N.A. | N.A. |  |  | N.A. | N.A. | 24-04-2012 | 13-09-2014 | 29-05-2012 | 20-11-2014 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 30-11-2012 | 16-12-2014 | 2013-01-28 | 17-03-2015 | N.A. | N.A. | 22-02-2013 | 23-08-2015 | 28-01-2013 | 23-08-2015 | N.A. | N.A. | 697 | 971 | 1613
122 | ANPARA D TPP UNIT-6 (2 X 500 MW) | 500 | 2008-01-13 | 13 | 7 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | 01-06-2008 | 20-02-2009 | 2009-02-13 | 2010-08-02 | 12-08-2009 | 03-04-2011 | N.A. | N.A. | 11-06-2010 | 29-10-2012 | 12-11-2010 | 18-12-2014 | N.A. | N.A. | 13-11-2010 | 24-01-2015 | 28-11-2010 | 27-01-2015 | 11-01-2011 | 18-02-2015 | 10-02-2011 | 03-03-2015 | N.A. | N.A. | 13-11-2009 | 13-06-2012 | 13-01-2010 | 15-01-2013 | 12-11-2010 | 20-02-2014 | 27-11-2010 | 22-12-2014 | 06-01-2011 | 13-03-2015 | 27-01-2011 | 22-03-2015 | N.A. | N.A. | 18-02-2011 | 31-03-2015 | 2011-04-12 | 06-06-2015 | N.A. | N.A. | 12-04-2011 | 08-05-2016 | 12-04-2011 | 28-11-2016 | 12-04-2011 | 29-11-2016 | 397 | 932 | 1185
123 | BONGAIGAON PROJECT UNIT-1 (3 X 250 MW) | 250 | 2008-02-05 | 19 | 0 | 0 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2008-11-05 | 2009-04-30 | 05-03-2009 | 25-01-2010 | N.A. | N.A. | 05-12-2009 | 31-01-2011 | 05-05-2010 | 29-11-2014 | N.A. | N.A. | 10-05-2010 | 28-12-2014 | 17-05-2010 | 31-12-2014 | 20-05-2010 | 01-03-2015 | 20-06-2010 | 01-04-2015 | N.A. | N.A. | 05-07-2009 | 28-12-2011 | 06-09-2009 | 05-05-2012 | 05-05-2010 | 29-05-2015 | 11-05-2010 | 16-01-2015 | 04-06-2010 | 06-05-2015 | 12-07-2010 | 03-06-2015 | N.A. | N.A. | 05-08-2010 | 22-06-2015 | 2010-11-05 | 22-06-2015 | N.A. | N.A. | 05-11-2010 | 26-03-2016 | 05-11-2010 | 01-04-2016 | N.A. | N.A. | 274 | 450 | 1004
124 | TUTICORIN UNIT-2 (2X500 MW ) | 500 | 2009-01-28 | 17 | 2 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-04-25 | 2010-12-15 | 29-09-2010 | 22-09-2011 | N.A. | N.A. | 31-08-2011 | 09-11-2012 | 31-03-2012 | 23-09-2014 | N.A. | N.A. | 01-04-2012 | 10-10-2014 | 13-04-2012 | 14-10-2014 | 15-04-2012 | 02-02-2015 | 10-05-2012 | 26-02-2015 | N.A. | N.A. | 15-02-2011 | 21-01-2013 | N.A. | N.A. | 14-03-2012 | 11-04-2014 | 30-03-2012 | 08-09-2014 | 14-05-2012 | 05-12-2014 | 31-05-2012 | 24-03-2015 | N.A. | N.A. | 28-06-2012 | 09-04-2015 | 2012-08-28 | 09-07-2015 | N.A. | N.A. | 31-08-2012 | 28-08-2015 | 28-09-2012 | 03-05-2016 | N.A. | N.A. | 452 | 686 | 1308
125 | VINDHYACHAL STPP STAGE-V UNIT-13 (1X500 MW) | 500 | 2012-05-03 | 4 | 0 | 1 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2013-03-02 | 2013-06-28 | 02-08-2013 | 24-11-2013 | N.A. | N.A. | 02-07-2014 | 20-08-2014 | 02-01-2015 | 23-04-2015 | N.A. | N.A. | 25-01-2015 | 24-04-2015 | 02-02-2015 | 27-04-2015 | 02-02-2015 | 08-05-2015 | 02-03-2015 | 29-05-2015 | N.A. | N.A. | 02-12-2013 | 08-07-2014 | 02-02-2014 | 10-09-2014 | 02-01-2015 | 25-01-2015 | 01-02-2015 | 25-04-2015 | 02-03-2015 | 24-06-2015 | 22-04-2015 | 23-07-2015 | N.A. | N.A. | 02-05-2015 | 06-08-2015 | 2015-05-02 | 06-08-2015 | N.A. | N.A. | 02-08-2015 | 30-10-2015 | 02-08-2015 | 09-12-2015 | N.A. | N.A. | 303 | 421 | 1094
126 | SIKKA TPS UNIT-4 ( 2X250 MW ) | 250 | 2011-07-10 | 14 | 1 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | 01-08-2011 | 09-08-2011 | 2012-03-15 | 2012-01-09 | 13-08-2012 | 23-05-2012 | N.A. | N.A. | 13-04-2013 | 30-06-2013 | 13-09-2013 | 18-10-2014 | N.A. | N.A. | 13-09-2013 | 20-01-2015 | 20-09-2013 | 23-01-2015 | 13-11-2013 | 21-02-2015 | 13-11-2013 | 03-03-2015 | N.A. | N.A. | 13-09-2012 | 04-01-2013 | N.A. | N.A. | 03-08-2013 | 07-03-2014 | 18-09-2013 | 25-11-2014 | 03-10-2013 | 22-01-2015 | 13-10-2013 | 15-03-2015 | N.A. | N.A. | 27-11-2013 | 30-08-2015 | 2014-01-10 | 25-09-2015 | N.A. | N.A. | 10-01-2014 | 27-12-2015 | 10-01-2014 |  | N.A. | N.A. | 249 | 183 | 915
127 | HNPCL/VIZAG TPP UNIT-1 (2 X 520 MW) | 520 | 2010-06-30 | 11 | 1 | 0 | 0 | 30-06-2010 | 30-06-2010 | 30-08-2010 | 28-10-2010 | N.A. | N.A. | 2011-06-30 | 2011-05-30 | 15-11-2011 | 10-01-2012 | N.A. | N.A. | 30-09-2012 | 28-12-2012 | 15-02-2013 | 22-03-2014 | N.A. | N.A. | 17-02-2013 | 10-08-2014 | 04-03-2013 | 14-08-2014 | 15-03-2013 | 24-09-2014 | 15-04-2013 | 20-03-2015 | N.A. | N.A. | 15-02-2012 | 25-07-2012 | 15-03-2012 | 06-11-2012 | 31-01-2013 | 24-09-2013 | 01-03-2013 | 27-03-2014 | 31-03-2013 | 25-06-2014 | 30-04-2013 | 05-08-2014 | 15-05-2013 | 04-12-2015 | 15-05-2013 | 06-12-2015 | 2013-06-15 | 06-12-2015 | N.A. | N.A. | 30-06-2013 | 10-01-2016 | 30-06-2013 | 05-09-2016 | 30-06-2013 |  | 365 | 334 | 1081
128 | SAGARDIGHI TPP UNIT-3 (2X500 MW) | 500 | 2011-02-22 | 0 | 8 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | 09-09-2011 | 26-09-2011 | 2012-03-04 | 2012-03-16 | 22-08-2012 | 13-09-2012 | N.A. | N.A. | 08-07-2013 | 31-08-2013 | 22-04-2014 | 30-01-2015 | N.A. | N.A. | 25-04-2014 | 13-02-2015 | 05-05-2014 | 17-02-2015 | 07-05-2014 | 27-02-2015 | 01-06-2014 | 11-03-2015 | N.A. | N.A. | 25-11-2012 | 14-06-2013 | N.A. | N.A. | 08-04-2014 | 24-07-2014 | 24-04-2014 | 19-01-2015 | 08-06-2014 | 24-02-2015 | 25-06-2014 | 16-03-2015 | N.A. | N.A. | 22-08-2014 | 31-03-2015 | 2014-09-15 | 14-12-2015 | N.A. | N.A. | 22-11-2014 | 01-07-2016 | 22-09-2014 | 28-09-2017 | N.A. | N.A. | 376 | 388 | 1301
129 | BARA PRAYAGRAJ STPP UNIT-1 (3X660 MW) | 660 | 2009-10-21 | 20 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-11-20 | 2011-07-12 | N.A. | N.A. | 20-05-2011 | 10-03-2012 | 20-06-2012 | 24-10-2013 | 20-02-2013 | 31-03-2015 | N.A. | N.A. | 21-02-2013 | 06-04-2015 | 20-03-2013 | 04-05-2015 | 01-05-2013 | 30-06-2015 | 20-05-2013 | 18-08-2015 | N.A. | N.A. | 21-02-2012 | 31-01-2013 | 21-03-2012 | 09-02-2013 | 20-02-2013 | 20-02-2014 | 21-03-2013 | 18-12-2014 | 20-04-2013 | 18-03-2015 | 20-05-2013 | 29-06-2015 | N.A. | N.A. | 20-07-2013 | 31-10-2015 | 2013-08-20 | 25-12-2015 | N.A. | N.A. | 20-09-2013 | 29-02-2016 | 20-09-2013 | 07-03-2016 | N.A. | N.A. | 395 | 629 | 1399
130 | KAKATIYA STG -2 (1X600 MW) | 600 | 2009-01-21 | 21 | 0 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-01-21 | 2011-05-05 | 21-07-2010 | 07-04-2012 | N.A. | N.A. | 21-07-2011 | 24-06-2013 | 21-01-2012 | 31-05-2015 | N.A. | N.A. | 01-02-2012 | 20-07-2015 | 06-02-2012 | 26-07-2015 | 20-03-2012 | 15-08-2015 | 21-04-2012 | 30-08-2015 | N.A. | N.A. | 21-05-2010 | 06-05-2013 | 21-07-2010 | 06-05-2013 | 21-01-2012 | 17-11-2014 | 30-01-2012 | 25-06-2015 | 21-02-2012 | 23-08-2015 | 21-03-2012 | 26-09-2015 | N.A. | N.A. | 21-05-2012 | 22-10-2015 | 2012-07-21 | 31-12-2015 | N.A. | N.A. | 21-07-2012 | 24-03-2016 | 21-07-2012 | 24-03-2016 | N.A. | N.A. | 365 | 834 | 1277
131 | LALITPUR STP PROJECT UNIT-2 (3 X 660 MW) | 660 | 2011-03-21 | 13 | 0 | 2 | 0 | 21-03-2011 | 21-03-2011 | 20-12-2011 | 20-12-2011 | N.A. | N.A. | 2012-06-20 | 2012-09-27 | N.A. | N.A. |  | 27-04-2013 | 20-01-2014 | 29-09-2014 | 05-09-2014 | 17-08-2015 | N.A. | N.A. |  | 18-08-2015 | 02-10-2014 | 23-08-2015 |  | 24-09-2015 | 02-12-2014 | 01-11-2015 | N.A. | N.A. | 20-05-2013 | 24-06-2014 | 20-07-2013 | 24-07-2014 | 05-09-2014 | 02-11-2015 |  | 27-07-2015 | 05-11-2014 | 05-11-2015 | 05-12-2014 | 05-11-2015 | N.A. | N.A. | 20-01-2015 | 23-12-2015 | 2015-02-05 | 08-01-2016 | N.A. | N.A. | 20-02-2015 | 14-10-2016 | 20-02-2015 | 17-01-2017 | 20-02-2015 |  | 457 | 556 | 1417
132 | GOINDWAL THERMAL POWER PROJECT UNIT-1 (2X270MW) | 270 | 2009-10-19 | 7 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-07-30 | 2010-09-06 | 19-12-2010 | 08-03-2011 | N.A. | N.A. | 31-08-2011 | 10-04-2012 | 31-12-2011 | 19-01-2013 | N.A. | N.A. | 15-01-2012 | 29-01-2013 | 31-01-2012 | 03-02-2013 | 04-02-2012 | 11-03-2013 | 19-02-2012 | 23-03-2013 | N.A. | N.A. | 28-02-2011 | 18-08-2011 | N.A. | N.A. | 30-11-2011 | 09-11-2012 | 05-01-2012 | 05-12-2012 | 19-01-2012 | 04-02-2013 | 02-02-2012 | 02-03-2013 | N.A. | N.A. | 20-03-2012 | 06-07-2013 | 2012-07-18 | 14-02-2016 | N.A. | N.A. | 18-07-2012 |  | 18-07-2012 |  | N.A. | N.A. | 284 | 322 | 1003
133 | BELLARY UNIT-3 (700 MW) | 700 | 2010-09-29 | 15 | 1 | 3 | 0 | 28-09-2010 | 28-09-2010 | 27-07-2011 | 27-06-2011 | 27-07-2011 | 27-06-2011 | 2012-01-27 | 2012-11-26 | N.A. | N.A. | 27-02-2013 | 27-02-2014 | 27-08-2013 | 30-11-2014 | 27-03-2014 | 28-03-2015 | N.A. | N.A. | 10-04-2014 | 03-05-2015 | 10-04-2014 | 04-05-2015 | 15-04-2014 | 23-07-2015 | 15-05-2014 | 10-10-2015 | N.A. | N.A. | 27-12-2012 | 07-11-2013 | 27-12-2012 | 07-11-2013 | 27-02-2014 | 12-06-2015 | 01-03-2014 | 25-05-2015 | 27-03-2014 | 29-09-2015 | 27-04-2014 | 05-11-2015 | N.A. | N.A. | 27-05-2014 | 25-12-2015 | 2014-05-27 | 01-03-2016 | N.A. | N.A. | 27-05-2014 | 16-09-2016 | 27-05-2014 | 31-01-2022 | N.A. | N.A. | 485 | 789 | 1336
134 | ANPARA D TPP UNIT-7 (2 X 500 MW) | 500 | 2008-01-13 | 13 | 7 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | 01-09-2008 | 20-02-2009 | 2009-05-13 | 2010-11-27 | 12-11-2009 | 05-12-2011 | N.A. | N.A. | 11-09-2010 | 03-07-2013 | 12-02-2011 | 31-08-2015 | N.A. | N.A. | 13-02-2011 | 15-10-2015 | 28-02-2011 | 19-10-2015 | 11-04-2011 | 31-10-2015 | 10-05-2011 | 28-11-2015 | N.A. | N.A. | 13-02-2010 | 25-10-2012 | 13-04-2010 | 07-10-2013 | 12-02-2011 | 30-03-2014 | 27-02-2011 | 11-09-2015 | 06-04-2011 | 05-01-2016 | 27-04-2011 | 20-01-2016 | N.A. | N.A. | 18-05-2011 | 23-02-2016 | 2011-07-12 | 06-03-2016 | N.A. | N.A. | 12-07-2011 | 18-10-2016 | 12-07-2011 | 10-03-2017 | 12-07-2011 | 11-03-2017 | 486 | 1049 | 1276
135 | SINGARENI (ADILABAD) UNIT-1 (2X600 MW) | 600 | 2011-11-11 | 21 | 9 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2012-08-12 | 2013-02-14 | 08-02-2013 | 12-09-2013 | N.A. | N.A. | 10-12-2013 | 27-08-2014 | 28-05-2014 | 03-07-2015 | N.A. | N.A. |  | 04-11-2015 |  | 14-11-2015 |  | 20-12-2015 |  | 05-01-2016 | N.A. | N.A. | 14-05-2013 | 31-07-2014 | 14-07-2013 | 27-10-2014 | 09-05-2014 | 31-07-2015 |  | 05-08-2015 |  | 16-10-2015 | 11-09-2014 | 27-12-2015 | N.A. | N.A. | 09-11-2014 | 13-03-2016 | 2014-12-09 | 13-03-2016 | N.A. | N.A. | 09-02-2015 | 25-09-2016 | 09-02-2015 | 25-09-2016 | N.A. | N.A. | 275 | 461 | 1124
136 | GOINDWAL THERMAL POWER PROJECT UNIT-2 (2X270MW) | 270 | 2009-10-19 | 7 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-10-30 | 2010-11-19 | 19-03-2011 | 24-07-2011 | N.A. | N.A. | 30-11-2011 | 26-09-2012 | 30-03-2012 | 25-09-2013 | N.A. | N.A. | 15-04-2012 | 26-09-2013 | 30-04-2012 | 29-09-2013 | 04-05-2012 | 19-12-2013 | 19-05-2012 | 30-12-2013 | N.A. | N.A. | 28-05-2011 | 05-03-2012 | N.A. | N.A. | 29-02-2012 | 27-12-2013 | 19-03-2012 | 30-09-2013 | 19-04-2012 | 28-11-2013 | 02-05-2012 | 27-12-2013 | N.A. | N.A. | 20-06-2012 | 04-03-2014 | 2012-10-18 | 15-03-2016 | N.A. | N.A. | 18-10-2012 |  | 18-10-2012 |  | N.A. | N.A. | 376 | 396 | 1095
137 | NABINAGAR UNIT-1 (4X250 MW ) | 250 | 2008-01-22 | 8 | 0 | 0 | 0 | 01-10-2010 | 01-10-2010 | N.A. | N.A. | N.A. | N.A. | 2011-05-31 | 2011-07-15 | 30-09-2011 | 20-10-2012 | N.A. | N.A. | 30-06-2012 | 11-04-2014 | 30-11-2012 | 30-03-2015 | N.A. | N.A. | 03-12-2012 | 02-09-2015 | 08-12-2012 | 13-09-2015 | 10-12-2012 | 18-12-2015 | 31-12-2012 | 08-01-2016 | N.A. | N.A. | 28-02-2012 | 06-02-2014 | 30-04-2012 | 01-09-2014 | 31-12-2012 | 17-12-2015 | 03-01-2013 | 14-08-2015 | 31-01-2013 | 30-12-2015 | 10-02-2013 | 08-02-2016 | N.A. | N.A. | 28-02-2013 | 20-03-2016 | 2013-05-31 | 20-03-2016 | 31-05-2013 | 20-03-2016 | 31-05-2013 | 05-01-2017 | 31-05-2013 | 05-09-2017 | N.A. | N.A. | 1225 | 1270 | 1956
138 | CHANDRAPUR MEGA POWER PROJECT UNIT-9 (2X500 MW) | 500 | 2009-02-09 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-04-09 | 2011-01-05 | 09-10-2010 | 25-09-2011 | N.A. | N.A. | 09-09-2011 | 30-10-2012 | 09-04-2012 | 07-05-2015 | N.A. | N.A. | 09-05-2012 | 19-08-2015 | 09-06-2012 | 21-08-2015 | 09-06-2012 | 09-12-2015 | 09-07-2012 | 26-12-2015 | N.A. | N.A. | 09-01-2011 | 14-11-2013 | N.A. | N.A. | 09-03-2012 | 23-05-2015 | 09-04-2012 | 17-06-2015 | 09-05-2012 | 21-11-2015 | 09-06-2012 | 02-03-2016 | N.A. | N.A. | 09-07-2012 | 21-03-2016 | 2012-08-09 | 21-03-2016 | N.A. | N.A. | 09-10-2012 | 24-11-2016 | 09-10-2012 | 03-12-2016 | N.A. | N.A. | 424 | 695 | 1277
139 | BOKARO ` A` TPS (1X500 MW) | 500 | 2008-09-16 | 12 | 1 | 0 | 0 | 16-09-2008 | 16-09-2008 | N.A. | N.A. | N.A. | N.A. | 2009-07-16 | 2009-11-24 | 16-12-2009 | 01-08-2012 | N.A. | N.A. | 15-11-2010 | 10-12-2013 | 14-06-2011 | 28-09-2014 | N.A. | N.A. | 30-06-2011 | 20-01-2015 | 14-07-2011 | 24-01-2015 | 15-07-2011 | 24-02-2015 | 14-08-2011 | 04-03-2015 | N.A. | N.A. | 15-06-2010 | 15-11-2012 | 16-07-2010 | 15-12-2012 | 16-05-2011 | 31-07-2014 | 05-06-2011 | 06-09-2014 | 15-07-2011 | 05-03-2015 | 15-08-2011 | 19-03-2015 | N.A. | N.A. | 12-09-2011 | 31-03-2015 | 2011-12-16 | 22-03-2016 | N.A. | N.A. | 16-12-2011 | 23-02-2017 | 16-12-2011 | 24-03-2017 | 16-12-2011 |  | 303 | 434 | 1186
140 | JHABUA PHASE-I (1 X 600 MW) | 600 | 2010-03-18 | 4 | 0 | 1 | 0 | N.A. | N.A. | 18-09-2010 | 27-09-2010 | N.A. | N.A. | 2010-12-18 | 2011-04-15 | 18-06-2011 | 17-01-2012 | N.A. | N.A. | 18-06-2012 | 22-12-2012 | 18-11-2012 | 12-03-2014 | N.A. | N.A. | 05-12-2012 | 17-05-2015 | 30-12-2012 | 21-05-2015 | 05-01-2013 | 10-06-2015 | 30-01-2013 | 27-06-2015 | N.A. | N.A. | 18-09-2011 | 30-07-2012 | 18-11-2011 | 30-08-2012 | 18-11-2012 | 23-12-2013 | 05-01-2013 | 03-06-2014 | 30-01-2013 | 30-05-2015 | 10-02-2013 | 12-06-2015 | N.A. | N.A. | 18-02-2013 | 23-02-2016 | 2013-04-18 | 22-03-2016 | N.A. | N.A. | 18-04-2013 | 02-05-2016 | 18-04-2013 | 02-05-2016 | 18-04-2013 |  | 275 | 393 | 1127
141 | LALITPUR STP PROJECT UNIT-1 (3 X 660 MW) | 660 | 2011-03-21 | 13 | 0 | 2 | 0 | 21-03-2011 | 21-03-2011 | 20-12-2011 | 20-12-2011 | N.A. | N.A. | 2012-02-20 | 2012-03-23 | N.A. | N.A. |  | 23-01-2013 | 20-09-2013 | 27-04-2014 | 05-05-2014 | 15-01-2015 | N.A. | N.A. |  | 29-01-2015 | 02-06-2014 | 03-02-2015 |  | 15-03-2015 | 02-08-2014 | 10-04-2015 | N.A. | N.A. | 20-01-2013 | 10-12-2013 | 20-03-2013 | 31-12-2013 | 05-05-2014 | 30-10-2014 | N.A. | N.A. | 05-07-2014 | 09-03-2015 | 05-08-2014 | 17-04-2015 | N.A. | N.A. | 20-09-2014 | 09-06-2015 | 2014-10-05 | 26-03-2016 | N.A. | N.A. | 20-10-2014 | 01-10-2015 | 20-10-2014 | 31-03-2016 | N.A. | N.A. | 336 | 368 | 1294
142 | MAUDA THERMAL POWER PROJECT UNIT-3 (2X660 MW) | 660 | 2012-03-30 | 3 | 0 | 1 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2013-01-29 | 2013-05-12 | N.A. | N.A. | 08-09-2013 | 15-06-2014 | 30-08-2014 | 22-11-2015 | 28-07-2015 | 03-01-2016 | N.A. | N.A. | 22-07-2015 | 06-01-2016 | 28-07-2015 | 10-01-2016 | 30-08-2015 | 24-01-2016 | 30-09-2015 | 03-03-2016 | N.A. | N.A. | 27-02-2014 | 15-03-2014 | 28-04-2014 | 15-01-2015 | 31-05-2015 | 19-10-2015 | 30-06-2015 | 22-11-2015 | 31-07-2015 | 12-03-2016 | 31-08-2015 | 13-03-2016 | N.A. | N.A. | 31-12-2015 | 28-03-2016 | 2016-02-29 | 28-03-2016 | N.A. | N.A. | 31-05-2016 | 05-01-2017 | 30-04-2016 | 18-03-2017 | N.A. | N.A. | 305 | 408 | 1431
143 | YERMARUS TPS UNIT-1 (2X800 MW) | 800 | 2010-04-09 | 15 | 10 | 3 | 0 | N.A. | N.A. | 31-12-2010 | 09-09-2011 | 20-12-2010 | 18-03-2012 | 2011-07-13 | 2012-10-29 | N.A. | N.A. | 21-01-2011 | 29-04-2013 | 09-01-2013 | 31-07-2014 | 08-09-2013 | 10-08-2015 | N.A. | N.A. | 15-10-2013 | 02-09-2015 | 31-10-2013 | 06-09-2015 | 15-11-2013 | 03-11-2015 | 08-12-2013 | 12-01-2016 | N.A. | N.A. | 09-01-2012 | 30-10-2013 | 23-04-2012 | 09-01-2014 | 08-09-2013 | 31-12-2014 | 10-11-2013 | 04-02-2015 | 30-11-2013 | 31-03-2015 | 08-12-2013 | 12-09-2015 | N.A. | N.A. | 08-01-2014 | 09-02-2016 | 2014-04-08 | 29-03-2016 | N.A. | N.A. | 08-04-2014 | 07-03-2017 | 08-04-2014 | 12-01-2018 | N.A. | N.A. | 460 | 934 | 1460
144 | PARLI TPS UNIT-8 (1X250 MW) | 250 | 2009-01-20 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-01-20 | 2010-08-20 | 20-07-2010 | 10-04-2011 | N.A. | N.A. | 20-06-2011 | 25-12-2012 | 20-08-2011 | 22-05-2015 | N.A. | N.A. | 20-09-2011 | 03-09-2015 | 19-10-2011 | 06-09-2015 | 20-10-2011 | 17-12-2015 | 19-11-2011 | 06-01-2016 | N.A. | N.A. | 20-07-2010 | 24-04-2012 | N.A. | N.A. | 20-08-2011 | 11-12-2014 | 20-08-2011 | 21-05-2015 | 20-09-2011 | 10-10-2015 | 20-10-2011 | 05-02-2016 | N.A. | N.A. | 20-11-2011 | 03-03-2016 | 2011-12-19 | 30-03-2016 | N.A. | N.A. | 20-02-2012 | 18-11-2016 | 19-01-2012 | 24-04-2017 | N.A. | N.A. | 365 | 577 | 1063
145 | HNPCL/VIZAG TPP UNIT-2 (2 X 520 MW) | 520 | 2010-06-30 | 11 | 1 | 0 | 0 | 30-06-2010 | 30-06-2010 | N.A. | N.A. | N.A. | N.A. | 2011-09-30 | 2011-09-29 | 15-02-2012 | 18-04-2012 | N.A. | N.A. | 30-12-2012 | 28-03-2013 | 15-05-2013 | 30-07-2014 | N.A. | N.A. | 17-05-2013 | 17-04-2015 | 02-06-2013 | 26-04-2015 | 15-06-2013 | 05-10-2015 | 15-07-2013 | 21-01-2016 | N.A. | N.A. | 15-05-2012 | 23-11-2012 | 15-06-2012 | 04-03-2013 | 30-04-2013 | 20-02-2014 | 01-06-2013 | 21-08-2014 | 30-06-2013 | 21-04-2015 | 30-07-2013 | 30-05-2015 | N.A. | N.A. | 15-08-2013 | 31-03-2016 | 2013-09-15 | 31-03-2016 | N.A. | N.A. | 30-09-2013 | 02-07-2016 | 30-09-2013 | 16-03-2017 | 30-09-2013 |  | 457 | 456 | 1173
146 | LALITPUR STP PROJECT UNIT-3 (3 X 660 MW) | 660 | 2011-03-21 | 13 | 0 | 2 | 0 | 21-03-2011 | 21-03-2011 | 20-12-2011 | 20-12-2011 | N.A. | N.A. | 2012-10-20 | 2012-11-28 | N.A. | N.A. |  | 28-09-2013 | 20-05-2014 | 31-03-2015 | 05-01-2015 | 09-01-2016 | N.A. | N.A. |  | 13-01-2016 | 02-02-2015 | 20-01-2016 |  | 16-02-2016 | 02-04-2015 | 08-03-2016 | N.A. | N.A. | 20-09-2013 | 25-05-2015 | 20-11-2013 | 15-06-2015 | 05-01-2015 | 10-02-2016 |  | 14-12-2015 | 05-03-2015 | 18-02-2016 | 15-04-2015 | 16-03-2016 | N.A. | N.A. | 20-05-2015 | 30-03-2016 | 2015-06-05 | 01-04-2016 | N.A. | N.A. | 20-06-2015 | 23-12-2016 | 20-06-2015 | 10-02-2017 | N.A. | N.A. | 579 | 618 | 1537
147 | BHAVNAGAR CFBC BECL UNIT-1 ( 2X 250 MW) | 250 | 2010-02-18 | 14 | 0 | 1 | 0 | N.A. | N.A. | 01-11-2010 | 08-11-2010 | N.A. | N.A. | 2010-11-19 | 2011-12-31 | 22-05-2011 | 03-06-2012 | N.A. | N.A. | 20-03-2012 | 05-03-2014 | 16-08-2012 | 28-02-2015 | N.A. | N.A. | 17-08-2012 | 04-06-2015 | 16-09-2012 | 08-06-2015 | 01-10-2012 | 20-07-2015 | 31-10-2012 | 04-10-2015 | N.A. | N.A. | 30-11-2011 | 29-05-2013 | N.A. | N.A. | 18-07-2012 | 27-06-2014 | 17-08-2012 | 18-11-2014 | 17-09-2012 | 30-06-2015 | 18-10-2012 | 30-10-2015 | N.A. | N.A. | 17-12-2012 | 25-11-2015 | 2013-02-05 | 16-05-2016 | N.A. | N.A. | 18-02-2013 | 29-01-2017 | 05-02-2013 | 24-03-2017 | N.A. | N.A. | 274 | 681 | 1083
148 | MARWA TPP UNIT-2 (2X500 MW) | 500 | 2009-02-28 | 2 | 2 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-03-30 | 2010-04-26 | 31-10-2010 | 06-03-2011 | N.A. | N.A. | 30-10-2011 | 06-09-2012 | 30-03-2012 | 08-05-2014 | N.A. | N.A. | 21-04-2012 | 24-06-2014 | 27-04-2012 | 29-06-2014 | 24-05-2012 | 03-09-2014 | 31-05-2012 | 23-09-2014 | N.A. | N.A. | 31-01-2011 | 20-10-2011 | N.A. | N.A. | 21-02-2012 | 02-12-2013 | 28-02-2012 | 29-03-2014 | 27-03-2012 | 18-10-2014 | 21-06-2012 | 16-01-2015 | N.A. | N.A. | 28-07-2012 | 31-03-2015 | 2012-11-30 | 15-07-2016 | N.A. | N.A. | 30-11-2012 | 31-07-2016 | 30-11-2012 | 24-01-2017 | N.A. | N.A. | 395 | 422 | 1371
149 | BARA PRAYAGRAJ STPP UNIT-2 (3X660 MW) | 660 | 2009-10-21 | 20 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-04-20 | 2011-09-12 | N.A. | N.A. | 20-10-2011 | 21-06-2012 | 20-11-2012 | 29-01-2015 | 20-07-2013 | 03-03-2016 | N.A. | N.A. | 21-07-2013 | 02-04-2016 | 20-08-2013 | 03-04-2016 | 01-10-2013 | 23-04-2016 | 20-10-2013 | 15-05-2016 | N.A. | N.A. | 21-07-2012 | 10-06-2013 | 21-08-2012 | 20-09-2013 | 20-07-2013 | 14-05-2015 | 21-08-2013 | 05-11-2015 | 20-09-2013 | 16-03-2016 | 20-10-2013 | 18-03-2016 | N.A. | N.A. | 20-12-2013 | 07-07-2016 | 2014-01-20 | 06-09-2016 | N.A. | N.A. | 20-02-2014 | 09-09-2016 | 20-02-2014 | 20-11-2016 | N.A. | N.A. | 546 | 691 | 1552
150 | SINGARENI (ADILABAD) UNIT-2 (2X600 MW) | 600 | 2011-11-11 | 21 | 9 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2012-12-12 | 2013-05-28 | 08-06-2013 | 14-12-2013 | N.A. | N.A. | 10-04-2014 | 03-11-2014 | 28-09-2014 | 03-08-2015 | N.A. | N.A. |  | 17-01-2016 |  | 22-01-2016 |  | 29-02-2016 |  | 25-03-2016 | N.A. | N.A. | 14-09-2013 | 14-08-2014 | N.A. | N.A. | 09-09-2014 | 03-11-2015 |  | 20-11-2015 |  | 05-03-2016 |  | 30-04-2016 | N.A. | N.A. | 09-03-2015 | 28-05-2016 | 2015-04-09 | 25-11-2016 | N.A. | N.A. | 09-06-2015 | 02-12-2016 | 09-06-2015 | 02-12-2016 | N.A. | N.A. | 397 | 564 | 1245
151 | SAGARDIGHI TPP UNIT-4 (2X500 MW) | 500 | 2011-02-22 | 0 | 8 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | 09-12-2011 | 22-09-2011 | 2012-06-04 | 2012-03-16 | 22-11-2012 | 25-01-2013 | N.A. | N.A. | 08-10-2013 | 21-04-2014 | 22-07-2014 | 19-02-2016 | N.A. | N.A. | 25-07-2014 | 09-03-2016 | 05-08-2014 | 13-03-2016 | 07-08-2014 | 30-04-2016 | 01-09-2014 | 09-07-2016 | N.A. | N.A. | 25-02-2013 | 27-08-2013 | N.A. | N.A. | 08-07-2014 | 10-02-2016 | 24-07-2014 | 04-03-2016 | 08-09-2014 | 07-05-2016 | 25-09-2014 | 09-08-2016 | N.A. | N.A. | 22-11-2014 | 15-10-2016 | 2014-12-22 | 15-12-2016 | N.A. | N.A. | 22-02-2015 | 20-12-2016 | 22-12-2014 | 07-10-2017 | 22-02-2015 |  | 468 | 388 | 1399
152 | NASIK INDIA BULLS PH-I UNIT-2 (5 X 270 MW ) | 270 | 2009-11-24 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-09-24 | 2010-12-08 | 24-02-2011 | 27-07-2011 | N.A. | N.A. | 24-12-2011 | 03-07-2012 | 24-04-2012 | 27-11-2013 | N.A. | N.A. | 10-05-2012 | 01-01-2014 | 15-05-2012 | 06-01-2014 | 20-05-2012 | 01-03-2014 | 14-06-2012 | 14-03-2014 | N.A. | N.A. | 24-05-2011 | 28-09-2011 | N.A. | N.A. | 24-04-2012 | 16-10-2013 | 10-05-2012 | 09-10-2013 | 14-06-2012 | 13-01-2014 | 18-06-2012 | 10-03-2014 | N.A. | N.A. | 24-06-2012 | 21-03-2016 | 2012-08-24 | 15-02-2017 | N.A. | N.A. | 24-10-2012 | 31-03-2016 | 24-10-2012 | 31-03-2016 | 24-10-2012 | 01-04-2016 | 304 | 379 | 1004
153 | MAUDA THERMAL POWER PROJECT UNIT-4 (2X660 MW) | 660 | 2012-03-30 | 3 | 0 | 1 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2013-07-29 | 2013-12-19 | N.A. | N.A. | 08-02-2014 | 27-01-2015 | 28-02-2015 | 10-08-2016 | 28-01-2016 | 13-12-2016 | N.A. | N.A. | 29-01-2016 | 16-12-2016 | 06-02-2016 | 23-12-2016 | 29-02-2016 | 21-01-2017 | 30-03-2016 | 17-02-2017 | N.A. | N.A. | 27-08-2014 | 15-10-2015 | 27-10-2014 | 16-10-2015 | 30-11-2015 | 13-09-2016 | 31-12-2015 | 22-08-2016 | 31-01-2016 | 30-01-2017 | 28-02-2016 | 31-01-2017 | N.A. | N.A. | 30-06-2016 | 18-03-2017 | 2016-08-31 | 18-03-2017 | N.A. | N.A. | 30-11-2016 | 20-08-2017 | 31-10-2016 | 23-10-2017 | N.A. | N.A. | 486 | 629 | 1615
154 | BONGAIGAON PROJECT UNIT-2 (3 X 250 MW) | 250 | 2008-02-05 | 19 | 0 | 0 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-03-05 | 2010-03-11 | 05-07-2009 | 12-10-2010 | N.A. | N.A. | 05-04-2010 | 10-04-2012 | 05-09-2010 | 27-03-2016 | N.A. | N.A. | 10-09-2010 | 30-04-2016 | 17-09-2010 | 04-05-2016 | 20-09-2010 | 03-10-2016 | 20-10-2010 | 30-11-2016 | N.A. | N.A. | 05-11-2009 | 30-01-2016 | 05-01-2010 | 30-01-2016 | 05-09-2010 | 23-01-2017 | 11-09-2010 | 10-09-2016 | 04-10-2010 | 22-12-2016 | 12-11-2010 | 25-01-2017 | N.A. | N.A. | 05-12-2010 | 13-02-2017 | 2011-03-05 | 22-03-2017 | N.A. | N.A. | 05-03-2011 | 01-11-2017 | 05-03-2011 | 09-12-2017 | N.A. | N.A. | 394 | 765 | 1124
155 | MUZAFFARPUR TPP STG.II UNIT-4 (2X195 MW) | 195 | 2010-03-12 | 8 | 0 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-03-11 | 2012-04-03 | 11-07-2011 | 12-09-2012 | N.A. | N.A. | 11-04-2012 | 05-08-2013 | 11-08-2012 | 23-08-2015 | N.A. | N.A. | 31-08-2012 | 10-10-2015 | 30-08-2012 | 13-10-2015 | 20-09-2012 | 05-11-2015 | 11-10-2012 | 25-11-2015 | N.A. | N.A. | 11-11-2011 | 17-10-2014 | 11-12-2011 | 15-05-2015 | 11-09-2012 | 09-01-2016 | 20-09-2012 | 07-12-2015 | 11-10-2012 | 08-03-2016 | 10-10-2012 | 16-03-2016 | N.A. | N.A. | 11-12-2012 | 24-03-2016 | 2013-02-11 | 24-03-2017 | N.A. | N.A. | 11-02-2013 | 29-04-2017 | 11-02-2013 | 07-03-2018 | N.A. | N.A. | 364 | 753 | 1067
156 | BHAVNAGAR CFBC BECL UNIT-2 ( 2X 250 MW) | 250 | 2010-02-18 | 14 | 0 | 1 | 0 | N.A. | N.A. | 01-11-2010 | 08-11-2010 | N.A. | N.A. | 2011-03-20 | 2012-05-15 | 22-08-2011 | 13-10-2012 | N.A. | N.A. | 20-06-2012 | 29-06-2014 | 16-11-2012 | 15-12-2015 | N.A. | N.A. | 17-12-2012 | 28-01-2016 | 16-01-2013 | 31-01-2016 | 01-01-2013 | 14-02-2016 | 31-01-2013 | 03-03-2016 | N.A. | N.A. | 20-10-2011 | 23-12-2013 | N.A. | N.A. | 18-10-2012 | 22-12-2014 | 17-11-2012 | 13-06-2015 | 17-12-2012 | 04-02-2016 | 18-01-2013 | 12-02-2016 | N.A. | N.A. | 17-03-2013 | 09-06-2016 | 2013-05-05 | 27-03-2017 | 05-05-2013 | 27-03-2017 | 05-05-2013 | 27-03-2017 | 07-05-2013 |  | N.A. | N.A. | 395 | 817 | 1172
157 | YERMARUS TPS UNIT-2 (2X800 MW) | 800 | 2010-04-09 | 15 | 10 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | 01-04-2011 | 01-04-2012 | 2012-01-25 | 2012-12-03 | N.A. | N.A. | 25-01-2012 | 31-07-2013 | 08-07-2013 | 30-12-2014 | 08-03-2014 | 25-02-2016 | N.A. | N.A. | 15-04-2014 | 04-03-2016 | 30-04-2014 | 09-03-2016 | 15-05-2014 | 28-04-2016 | 08-06-2014 | 15-06-2016 | N.A. | N.A. | 09-07-2012 | 22-04-2014 | N.A. | N.A. | 08-02-2014 | 30-11-2015 | 10-05-2014 | 20-11-2015 | 31-05-2014 | 10-02-2016 | 31-03-2014 | 31-03-2016 | N.A. | N.A. | 08-07-2014 | 21-07-2016 | 2014-10-08 | 29-03-2017 | N.A. | N.A. | 08-10-2014 | 06-04-2017 | 08-10-2014 | 31-01-2022 | N.A. | N.A. | 656 | 969 | 1643
158 | UNCHAHAR STAGE-IV UNIT-6 (1X500 MW) | 500 | 2013-11-15 | 13 | 14 | 2 | 0 | 15-11-2013 | 15-11-2013 | N.A. | N.A. | N.A. | N.A. | 2014-09-15 | 2015-06-08 | 15-02-2015 | 14-10-2015 | N.A. | N.A. | 15-01-2016 | 24-06-2016 | 31-08-2016 | 26-01-2017 | N.A. | N.A. |  | 18-01-2017 |  | 30-01-2017 |  | 22-02-2017 | 15-11-2016 | 10-03-2017 | N.A. | N.A. | 15-06-2015 | 29-02-2016 | 15-07-2015 | 29-02-2016 | 15-09-2016 | 19-10-2016 |  | 16-11-2016 | 15-11-2016 | 14-03-2017 | 25-11-2016 | 26-03-2017 | N.A. | N.A. | 30-11-2016 | 31-03-2017 | 2016-12-05 | 31-03-2017 | N.A. | N.A. | 14-04-2017 | 01-09-2017 | 14-04-2017 | 30-10-2017 | N.A. | N.A. | 304 | 570 | 1116
159 | NABINAGAR UNIT-2 (4X250 MW ) | 250 | 2008-01-22 | 8 | 0 | 0 | 0 | 01-10-2010 | 01-10-2010 | N.A. | N.A. | N.A. | N.A. | 2011-08-31 | 2011-12-20 | 31-12-2011 | 21-03-2013 | N.A. | N.A. | 30-09-2012 | 02-03-2015 | 28-02-2013 | 02-10-2016 | N.A. | N.A. | 03-03-2013 | 14-10-2016 | 08-03-2013 | 15-10-2016 | 10-03-2013 | 28-01-2017 | 31-03-2013 | 21-02-2017 | N.A. | N.A. | 31-05-2012 | 06-10-2015 | 31-07-2012 | 30-11-2015 | 31-03-2013 | 31-03-2017 | 03-04-2013 | 29-12-2016 | 30-04-2013 | 30-03-2017 | 10-05-2013 | 31-03-2017 | N.A. | N.A. | 31-05-2013 | 01-04-2017 | 2013-08-31 | 03-04-2017 | 31-08-2013 | 03-04-2017 | 31-08-2013 | 31-08-2017 | 31-08-2013 | 19-09-2018 | N.A. | N.A. | 1317 | 1428 | 2048
160 | NASIK INDIA BULLS PH-I UNIT-3 (5 X 270 MW ) | 270 | 2009-11-24 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2010-11-24 | 2011-01-10 | 24-04-2011 | 12-12-2011 | N.A. | N.A. | 24-02-2012 | 30-10-2013 | 24-06-2012 | 29-09-2016 | N.A. | N.A. | 10-07-2012 | 04-10-2016 | 15-07-2012 | 07-10-2016 | 20-07-2012 | 25-11-2016 | 14-08-2012 | 06-12-2016 | N.A. | N.A. | 24-07-2011 | 04-01-2012 | N.A. | N.A. | 24-06-2012 | 25-01-2017 | 10-07-2012 | 29-10-2016 | 10-08-2012 | 29-12-2016 | 15-08-2012 | 27-01-2017 | N.A. | N.A. | 24-08-2012 | 13-04-2017 | 2012-10-24 | 14-04-2017 | 24-10-2012 | 14-04-2017 | 24-12-2012 | 14-04-2017 | 24-12-2012 | 30-10-2017 | N.A. | N.A. | 365 | 412 | 1065
161 | NASIK INDIA BULLS PH-I UNIT-4 (5 X 270 MW ) | 270 | 2009-11-24 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-01-24 | 2011-05-16 | 24-06-2011 | 23-12-2011 | N.A. | N.A. | 24-04-2012 | 09-08-2016 | 24-08-2012 | 30-12-2016 | N.A. | N.A. | 10-09-2012 | 15-01-2017 | 15-09-2012 | 18-01-2017 | 20-09-2012 | 04-02-2017 | 14-10-2012 | 13-02-2017 | N.A. | N.A. | 24-09-2011 | 12-04-2016 | N.A. | N.A. | 24-08-2012 | 29-03-2017 | 10-09-2012 | 30-01-2017 | 14-10-2012 | 04-03-2017 |  | 29-03-2017 | N.A. | N.A. | 24-10-2012 | 19-05-2017 | 2012-12-24 | 19-05-2017 | 24-12-2012 | 19-05-2017 | 24-02-2013 | 19-05-2017 | 24-02-2013 | 31-01-2018 | N.A. | N.A. | 426 | 538 | 1126
162 | BARA PRAYAGRAJ STPP UNIT-3 (3X660 MW) | 660 | 2009-10-21 | 13 | 0 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-09-20 | 2011-09-05 | N.A. | N.A. | 20-03-2012 | 12-05-2012 | 20-04-2013 | 29-11-2014 | 20-12-2013 | 31-05-2016 | N.A. | N.A. | 21-12-2013 | 28-06-2016 | 20-01-2014 | 30-06-2016 | 01-03-2014 | 15-01-2017 | 20-03-2014 | 06-02-2017 | N.A. | N.A. | 21-12-2012 | 10-01-2014 | 21-01-2013 | 11-11-2014 | 20-12-2013 | 05-02-2017 | 21-01-2014 | 09-04-2016 | 20-02-2014 | 14-02-2017 | 20-03-2014 | 15-02-2017 | N.A. | N.A. | 20-05-2014 | 26-03-2017 | 2014-06-20 | 22-05-2017 | 20-06-2014 | 22-05-2017 | 20-07-2014 | 25-05-2017 | 20-07-2014 | 25-01-2018 | N.A. | N.A. | 699 | 684 | 1703
163 | NASIK INDIA BULLS PH-I UNIT-5 (5 X 270 MW ) | 270 | 2009-11-24 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-03-24 | 2011-06-15 | 24-08-2011 | 06-03-2012 | N.A. | N.A. | 24-06-2012 | 09-01-2017 | 24-10-2012 | 20-02-2017 | N.A. | N.A. | 10-11-2012 | 24-02-2017 | 15-11-2012 | 26-02-2017 | 20-11-2012 | 10-03-2017 | 14-12-2012 | 25-03-2017 | N.A. | N.A. | 24-11-2011 | 14-07-2016 | N.A. | N.A. | 24-10-2012 | 28-04-2017 | 10-11-2012 | 13-02-2017 | 14-12-2012 | 21-03-2017 | 17-12-2012 | 28-04-2017 | N.A. | N.A. | 24-12-2012 | 30-05-2017 | 2013-02-24 | 30-05-2017 | 24-02-2013 | 30-05-2017 | 24-02-2013 |  | 24-04-2013 |  | N.A. | N.A. | 485 | 568 | 1188
164 | BARAUNI UNIT-8 (2X250MW) | 250 | 2011-03-11 | 8 | 1 | 0 | 0 | 11-03-2011 | 11-03-2011 | 18-05-2011 | 04-05-2011 | 25-10-2011 | 20-01-2012 | 2012-03-15 | 2012-12-10 | 21-08-2012 | 05-06-2013 | N.A. | N.A. | 22-04-2013 | 21-08-2014 | 21-10-2013 | 18-06-2017 | N.A. | N.A. | 24-10-2013 | 29-06-2017 | 10-11-2013 | 23-07-2017 | 13-11-2013 | 08-08-2017 | 15-12-2013 | 03-09-2017 | N.A. | N.A. | 11-09-2012 | 21-08-2014 | 09-11-2012 | 12-09-2014 | 11-08-2013 | 30-12-2015 | 27-09-2013 | 09-07-2016 | 26-10-2013 | 16-01-2017 | 11-12-2013 | 19-06-2017 | N.A. | N.A. | 10-01-2014 | 14-11-2017 | 2014-02-10 | 11-01-2018 | 10-02-2014 | 11-01-2018 | 10-02-2014 | 01-03-2020 | 10-03-2014 | 09-03-2020 | N.A. | N.A. | 370 | 640 | 1067
165 | RAYALASEEMA STG-IV (600 MW) | 600 | 2011-02-10 | 11 | 18 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2012-02-10 | 2013-02-04 | 10-08-2012 | 30-11-2013 | N.A. | N.A. | 10-08-2013 | 10-11-2015 | 10-02-2014 | 29-12-2016 | N.A. | N.A. | 25-02-2014 | 23-02-2017 | 28-02-2014 | 25-02-2017 | 30-03-2014 | 18-04-2017 | 10-05-2014 | 13-05-2017 | N.A. | N.A. | 10-06-2012 | 07-03-2016 | 10-08-2012 | 01-05-2016 | 10-02-2014 | 20-06-2017 | 01-03-2014 | 24-02-2017 | 10-03-2014 | 18-05-2017 | 10-04-2014 | 21-06-2017 | N.A. | N.A. | 10-06-2014 | 02-07-2017 | 2014-07-10 | 12-03-2018 | N.A. | N.A. | 10-08-2014 | 28-03-2018 | 10-08-2014 | 27-04-2018 | N.A. | N.A. | 365 | 725 | 1246
166 | BARAUNI UNIT-9 (2X250MW) | 250 | 2011-03-11 | 8 | 1 | 0 | 0 | 11-03-2011 | 11-03-2011 | 18-05-2011 | 04-05-2011 | 25-10-2011 | 20-01-2012 | 2012-06-15 | 2013-01-21 | 21-11-2012 | 15-09-2013 | N.A. | N.A. | 22-07-2013 | 21-09-2014 | 21-01-2014 | 28-08-2017 | N.A. | N.A. |  | 25-01-2018 |  | 15-02-2018 | 13-02-2014 | 22-02-2018 | 15-03-2014 | 09-03-2018 | N.A. | N.A. | 11-12-2012 | 22-08-2014 | 09-02-2013 | 25-08-2014 | 11-11-2013 | 17-03-2018 | 27-12-2013 | 20-06-2017 | 26-01-2014 | 08-02-2018 | 11-03-2014 | 18-03-2018 | N.A. | N.A. | 10-04-2014 | 31-03-2018 | 2014-05-10 | 31-03-2018 | 10-05-2014 | 31-03-2018 | 10-05-2014 |  | 10-06-2014 |  | N.A. | N.A. | 462 | 682 | 1156
169 | KOTHAGUDEM (1X800 MW) | 800 | 2015-01-01 | 21 | 1 | 3 | 0 | 01-01-2015 | 01-01-2015 | N.A. | N.A. | N.A. | N.A. | 2015-09-15 | 2016-01-24 | N.A. | N.A. | 29-02-2016 | 17-08-2016 | 31-12-2016 | 22-09-2017 | 31-05-2017 | 31-01-2018 | N.A. | N.A. | 15-06-2017 | 29-03-2018 | 30-06-2017 | 01-04-2018 | 15-07-2017 | 16-04-2018 | 05-08-2017 | 30-05-2018 | N.A. | N.A. | 01-06-2016 | 25-11-2016 | 01-07-2016 | 13-03-2017 | 31-07-2017 | 25-01-2018 | 01-07-2017 | 08-02-2018 | 31-08-2017 | 28-03-2018 | 15-09-2017 | 31-03-2018 | 29-09-2017 | 30-06-2018 | 30-09-2017 | 30-06-2018 | 2017-11-30 | 05-10-2018 | 31-12-2017 | 26-12-2018 | 31-12-2017 | 26-12-2018 | 31-12-2017 | 19-02-2019 | N.A. | N.A. | 257 | 388 | 1064
170 | NABINAGAR UNIT-3 (4X250 MW ) | 250 | 2008-01-22 | 8 | 0 | 0 | 0 | 01-10-2010 | 01-10-2010 | N.A. | N.A. | N.A. | N.A. | 2011-11-30 | 2012-05-25 | 31-03-2012 | 10-06-2013 | N.A. | N.A. | 31-12-2012 | 30-11-2016 | 31-05-2013 | 13-09-2018 | N.A. | N.A. | 03-06-2013 | 22-09-2018 | 08-06-2013 | 03-10-2018 | 10-06-2013 | 03-11-2018 | 30-06-2013 | 17-11-2018 | N.A. | N.A. | 31-08-2012 | 18-08-2016 | 31-10-2012 | 02-01-2017 | 30-06-2013 | 31-03-2018 | 03-07-2013 | 20-02-2018 | 31-07-2013 | 26-07-2018 | 10-08-2013 | 01-11-2018 | N.A. | N.A. | 31-08-2013 | 31-12-2018 | 2013-11-30 | 23-01-2019 | 30-11-2013 | 20-02-2019 | 30-11-2013 | 20-02-2019 | 30-11-2013 | 11-09-2019 | N.A. | N.A. | 1408 | 1585 | 2139
171 | BONGAIGAON PROJECT UNIT-3 (3 X 250 MW) | 250 | 2008-02-05 | 19 | 0 | 0 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2009-07-05 | 2012-04-02 | 05-11-2009 | 25-02-2013 | N.A. | N.A. | 05-08-2010 | 22-03-2014 | 05-01-2011 | 01-07-2017 | N.A. | N.A. | 10-01-2011 | 15-06-2018 | 16-01-2011 | 19-06-2018 | 20-01-2011 | 03-08-2018 | 20-02-2011 | 10-09-2018 | N.A. | N.A. | 05-03-2010 | 13-12-2016 | 06-05-2010 | 13-12-2016 | 05-01-2011 | 21-11-2018 | 11-01-2011 | 19-03-2018 | 04-02-2011 | 26-07-2018 | 12-03-2011 | 26-07-2018 | N.A. | N.A. | 05-04-2011 | 02-01-2019 | 2011-07-05 | 10-02-2019 | 05-07-2011 | 26-03-2019 | 05-07-2011 | 26-03-2019 | 05-07-2011 | 26-03-2019 | N.A. | N.A. | 516 | 1518 | 1246
172 | GADARWARA UNIT-1 (2X800 MW) | 800 | 2013-03-22 | 4 | 0 | 2 | 1 | 22-03-2013 | 22-03-2013 | N.A. | N.A. | N.A. | N.A. | 2014-03-22 | 2014-11-27 | N.A. | N.A. | 01-11-2014 | 29-08-2015 | 22-07-2015 | 05-12-2016 | 10-03-2016 | 22-04-2017 | 22-03-2016 | 02-05-2017 | N.A. | N.A. | N.A. | N.A. | 22-04-2016 | 15-06-2017 | 22-05-2016 | 21-07-2017 | N.A. | N.A. | 22-01-2015 | 05-03-2016 | 22-03-2015 | 15-04-2016 | 22-01-2016 | 22-08-2017 | 30-01-2016 | 22-02-2017 | 22-03-2016 | 03-07-2017 | 22-04-2016 | 09-09-2017 | N.A. | N.A. | 22-07-2016 | 30-08-2018 | 2016-09-22 | 13-10-2018 | 22-09-2016 | 29-03-2019 | 22-09-2016 | 01-06-2019 | 22-10-2016 | 06-06-2019 | 22-11-2016 | 14-08-2019 | 365 | 615 | 1280
174 | IB VALLEY TPS. BANHARPALL UNIT-3 (2X660 MW) | 660 | 2014-03-26 | 23 | 0 | 0 | 0 | 26-03-2014 | 26-03-2014 | N.A. | N.A. | N.A. | N.A. | 2014-11-21 | 2015-01-20 | N.A. | N.A. | 19-06-2015 | 25-07-2016 | 11-09-2016 | 26-12-2017 | 09-04-2017 | 18-11-2018 | N.A. | N.A. | 19-04-2017 | 13-12-2018 | 09-05-2017 | 16-12-2018 | 08-06-2017 | 24-01-2019 | 08-07-2017 | 23-02-2019 | N.A. | N.A. | 16-11-2015 | 11-03-2016 | 15-01-2016 | 30-07-2016 | 09-04-2017 | 30-09-2017 | 15-04-2017 | 19-02-2018 | 24-05-2017 | 05-06-2018 | 08-06-2017 | 09-10-2018 | N.A. | N.A. | 07-08-2017 | 30-03-2019 | 2017-08-14 | 20-04-2019 | 06-09-2017 | 01-07-2019 | 13-09-2017 | 04-07-2019 | 06-09-2017 | 02-07-2019 | 13-09-2017 |  | 240 | 300 | 1237
175 | IB VALLEY TPS. BANHARPALL UNIT-4 (2X660 MW) | 660 | 2014-03-26 | 23 | 0 | 0 | 0 | 24-07-2014 | 10-07-2014 | N.A. | N.A. | N.A. | N.A. | 2015-03-21 | 2015-05-29 | N.A. | N.A. | 17-10-2015 | 25-07-2016 | 09-01-2017 | 30-11-2017 | 07-08-2017 | 31-08-2018 | N.A. | N.A. | 17-08-2017 | 11-09-2018 | 06-09-2017 | 15-09-2018 | 06-10-2017 | 31-10-2018 | 10-11-2017 | 07-12-2018 | N.A. | N.A. | 14-05-2016 | 02-08-2016 | 07-08-2016 | 19-01-2017 | 22-08-2017 | 27-12-2017 | 21-09-2017 | 07-04-2018 | 06-10-2017 | 21-06-2018 | 13-10-2017 | 09-10-2018 | N.A. | N.A. | 13-12-2017 | 23-01-2019 | 2018-01-04 | 11-05-2019 | 18-01-2018 | 16-08-2019 | 18-01-2018 | 21-08-2019 | 18-01-2018 | 17-08-2019 | 18-01-2018 |  | 360 | 429 | 1380
176 | WANAKBORI (800 MW) | 800 | 2014-10-21 | 14 | 1 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2016-02-21 | 2016-02-25 | N.A. | N.A. | 30-09-2016 | 31-01-2017 | 21-07-2017 | 12-01-2018 | 21-03-2018 | 12-07-2018 | N.A. | N.A. | 31-03-2018 | 31-07-2018 | 07-04-2018 | 04-08-2018 | 10-04-2018 | 12-10-2018 | 30-04-2018 | 27-11-2018 | N.A. | N.A. | 20-08-2016 | 22-12-2016 | N.A. | N.A. | 21-03-2018 | 24-07-2018 | 05-04-2018 | 05-07-2018 | 15-05-2018 | 21-10-2018 | 30-06-2018 | 28-12-2018 | N.A. | N.A. | 21-07-2018 | 03-03-2019 | 2018-10-20 | 14-06-2019 | 22-10-2018 | 12-10-2019 | 22-10-2018 | 12-10-2019 | 22-10-2018 | 23-10-2019 | 22-10-2018 |  | 488 | 492 | 1460
177 | NEYVELI NEW THERMAL POWER PROJECT UNIT-1 (2X500 MW) | 500 | 2013-10-31 | 17 | 2 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | 30-04-2014 | 30-06-2014 | 2014-12-31 | 2016-03-07 | N.A. | N.A. | 30-06-2015 | 12-12-2016 | 30-06-2016 | 24-08-2018 | 30-04-2017 | 28-12-2018 | N.A. | N.A. | 05-05-2017 | 28-12-2018 | 15-05-2017 | 04-01-2019 | 10-06-2017 | 20-01-2019 | 30-06-2017 | 20-02-2019 | N.A. | N.A. | 25-10-2015 | 28-05-2016 | N.A. | N.A. | 11-01-2017 | 31-05-2017 | 10-02-2017 | 20-11-2017 | 21-02-2017 | 15-04-2018 | 30-04-2017 | 30-11-2018 | N.A. | N.A. | 31-07-2017 | 28-03-2019 | 2017-08-28 | 29-09-2019 | 31-08-2017 | 19-12-2019 | 31-08-2017 | 19-12-2019 | 30-09-2017 | 24-04-2020 | N.A. | N.A. | 426 | 858 | 1397
178 | SURATGARH UNIT-7 (2X660 MW) | 660 | 2013-03-28 | 24 | 1 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2014-03-28 | 2014-03-26 | N.A. | N.A. |  | 31-12-2014 | 28-08-2015 | 31-12-2015 | 28-02-2016 | 24-02-2017 | N.A. | N.A. | 20-03-2016 | 16-04-2018 | 12-04-2016 | 30-04-2018 | 10-05-2016 | 09-06-2018 | 29-05-2016 | 25-08-2018 | N.A. | N.A. | 15-12-2014 | 02-05-2015 | N.A. | N.A. | 15-03-2016 | 20-01-2017 | 17-03-2016 | 09-12-2016 | 28-04-2016 | 03-05-2017 | 31-05-2016 | 09-11-2017 | N.A. | N.A. | 28-06-2016 | 18-12-2018 | 2016-07-28 | 30-03-2019 | 28-08-2016 | 15-03-2020 | 28-08-2016 | 01-12-2020 | 28-08-2016 | 15-03-2020 | 28-09-2016 | 31-03-2022 | 365 | 363 | 1218
179 | NABINAGAR SG PKG UNIT-1 (3X660 MW) | 0 | 2013-01-31 | 8 | 4 | 0 | 0 | 31-01-2013 | 31-01-2013 | N.A. | N.A. | N.A. | N.A. | 2014-01-31 | 2014-06-14 | N.A. | N.A. | 31-12-2014 | 31-08-2015 | 31-08-2015 | 17-12-2016 | 31-07-2016 | 16-07-2017 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 30-09-2016 | 22-09-2017 | 14-10-2016 | 22-12-2017 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 30-11-2016 | 14-01-2019 | 2017-01-31 | 29-03-2019 | 31-01-2017 | 12-07-2019 | 31-01-2017 | 12-07-2019 | 31-03-2017 | 08-10-2019 | N.A. | N.A. | 365 | 499 | 1461
181 | DARLIPALLI SG & ESP PKG UNIT-1 (2X800 MW) | 0 | 2014-02-17 | 18 | 4 | 3 | 0 | N.A. | N.A. | 17-10-2014 | 25-11-2014 | N.A. | N.A. | 2015-04-17 | 2015-04-08 | N.A. | N.A. | 02-11-2015 | 17-04-2016 | 16-08-2016 | 13-10-2017 | 16-04-2017 | 28-10-2018 | N.A. | N.A. | 26-04-2017 | 12-11-2018 | 06-05-2017 | 24-11-2018 | 16-05-2017 | 27-12-2018 | 16-06-2017 | 12-02-2019 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 16-08-2017 | 04-04-2019 | 2017-10-16 | 02-10-2019 | 16-10-2017 | 30-12-2019 | 16-10-2017 | 01-03-2020 | 16-11-2017 | 31-03-2020 | N.A. | N.A. | 424 | 415 | 1337
182 | BHADRADRI (MANUGURU) (4X270 MW) TPS UNIT-1 | 270 | 2015-03-21 | 21 | 1 | 1 | 0 | 21-03-2015 | 21-03-2015 | N.A. | N.A. | N.A. | N.A. | 2017-09-15 | 2017-09-15 | 31-12-2017 | 06-01-2018 | N.A. | N.A. | 31-05-2018 | 17-08-2018 | 18-08-2018 | 25-03-2019 | N.A. | N.A. | 17-09-2018 | 10-05-2019 | 26-09-2018 | 19-05-2019 | 01-11-2018 | 28-06-2019 | 25-11-2018 | 23-07-2019 | N.A. | N.A. | 15-03-2018 | 31-05-2018 | 15-03-2018 | 01-09-2018 | 15-10-2018 | 13-02-2019 | 16-10-2018 | 14-02-2019 | 10-11-2018 | 02-04-2019 | 15-11-2018 | 15-04-2019 | N.A. | N.A. | 14-01-2019 | 19-09-2019 | 2019-01-16 | 20-03-2020 | 18-01-2019 | 05-06-2020 | 18-01-2019 | 05-06-2020 | 30-01-2019 | 16-06-2020 | N.A. | N.A. | 909 | 909 | 1397
183 | BHADRADRI (MANUGURU) (4X270 MW) TPS UNIT-2 | 270 | 2015-03-21 | 21 | 1 | 1 | 0 | 21-03-2015 | 21-03-2015 | N.A. | N.A. | N.A. | N.A. | 2017-10-15 | 2018-01-12 | 31-01-2018 | 28-03-2018 | N.A. | N.A. | 30-06-2018 | 04-11-2018 | 18-09-2018 | 19-10-2019 | N.A. | N.A. | 17-10-2018 | 21-10-2019 | 26-10-2018 | 24-10-2019 | 01-12-2018 | 09-02-2020 | 25-12-2018 | 21-02-2020 | N.A. | N.A. | 15-04-2018 | 03-01-2019 | 15-04-2018 | 12-03-2019 | 15-11-2018 | 03-07-2019 | 16-11-2018 | 19-06-2019 | 10-12-2018 | 25-09-2019 | 15-12-2018 | 23-10-2019 | N.A. | N.A. | 14-02-2019 | 03-07-2020 | 2019-02-16 | 23-11-2020 | 18-02-2019 | 07-12-2020 | 18-02-2019 | 07-12-2020 | 28-02-2019 | 17-12-2020 | N.A. | N.A. | 939 | 1028 | 1428
184 | NEYVELI NEW THERMAL POWER PROJECT UNIT-2 (2X500 MW) | 500 | 2013-10-31 | 17 | 2 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | 30-10-2014 | 27-09-2014 | 2015-06-30 | 2016-03-28 | N.A. | N.A. | 30-12-2015 | 07-01-2017 | 30-12-2016 | 10-12-2018 | 30-10-2017 | 30-05-2019 | N.A. | N.A. | 05-11-2017 | 04-06-2019 | 15-11-2017 | 15-06-2019 | 15-12-2017 | 20-08-2019 | 30-12-2017 | 26-09-2019 | N.A. | N.A. | 25-04-2016 | 01-06-2016 | N.A. | N.A. | 11-07-2017 | 21-08-2017 | 05-08-2017 | 01-06-2018 | 21-08-2017 | 21-09-2018 | 31-10-2017 | 10-07-2019 | N.A. | N.A. | 31-01-2018 | 26-02-2020 | 2018-03-28 | 31-01-2021 | 31-03-2018 | 03-02-2021 | 31-03-2018 | 03-02-2021 | 30-04-2018 | 03-04-2021 | N.A. | N.A. | 607 | 879 | 1609
185 | GADARWARA UNIT-2 (2X800 MW) | 800 | 2013-03-22 | 4 | 0 | 2 | 1 | 22-03-2013 | 22-03-2013 | N.A. | N.A. | N.A. | N.A. | 2014-07-22 | 2015-04-10 | N.A. | N.A. | 01-03-2015 | 11-04-2016 | 22-11-2015 | 28-10-2017 | 10-07-2016 | 31-12-2018 | 22-07-2016 | 09-01-2019 | N.A. | N.A. | N.A. | N.A. | 22-08-2016 | 05-04-2019 | 22-09-2016 | 23-12-2019 | N.A. | N.A. | 22-05-2015 | 03-07-2017 | 22-07-2015 | 03-07-2017 | 22-05-2016 | 18-01-2019 | 30-05-2016 | 08-11-2018 | 22-07-2016 | 22-01-2019 | 22-08-2016 | 31-03-2019 | N.A. | N.A. | 22-11-2016 | 26-08-2020 | 2017-01-22 | 19-01-2021 | 22-01-2017 | 15-02-2021 | 22-01-2017 | 01-03-2021 | 22-02-2017 | 15-03-2021 | N.A. | N.A. | 487 | 749 | 1402
186 | BHADRADRI (MANUGURU) (4X270 MW) TPS UNIT-3 | 270 | 2015-03-21 | 21 | 1 | 1 | 0 | 21-03-2015 | 21-03-2015 | N.A. | N.A. | N.A. | N.A. | 2017-11-15 | 2018-01-11 | 28-02-2018 | 28-03-2018 | N.A. | N.A. | 31-07-2018 | 28-11-2018 | 18-10-2018 | 30-12-2019 | N.A. | N.A. | 17-11-2018 | 18-01-2020 | 26-11-2018 | 22-01-2020 | 01-01-2019 | 28-10-2020 | 25-01-2019 | 08-11-2020 | N.A. | N.A. | 15-05-2018 | 05-03-2019 | 15-05-2018 | 20-06-2019 | 15-12-2018 | 24-02-2020 | 16-12-2018 | 21-01-2020 | 10-01-2019 | 20-06-2020 | 15-01-2019 | 01-09-2020 | N.A. | N.A. | 05-02-2019 | 15-01-2021 | 2019-02-13 | 20-03-2021 | 16-02-2019 | 26-03-2021 | 16-02-2019 | 26-03-2021 | 31-03-2019 |  | N.A. | N.A. | 970 | 1027 | 1425
189 | NABINAGAR SG PKG UNIT-2 (3X660 MW) | 0 | 2013-01-31 | 8 | 4 | 0 | 0 | 31-01-2013 | 31-01-2013 | 30-11-2013 | 28-12-2013 | N.A. | N.A. | 2014-07-31 | 2014-11-29 | N.A. | N.A. | 30-06-2015 | 20-02-2016 | 29-02-2016 | 11-12-2017 | 31-01-2017 | 15-09-2019 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 31-03-2017 | 11-11-2019 | 14-04-2017 | 24-12-2019 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 31-05-2017 | 12-02-2020 | 2017-07-31 | 24-03-2021 | 31-07-2017 | 31-03-2021 | 31-07-2017 | 23-07-2021 | 30-09-2017 | 12-08-2021 | N.A. | N.A. | 546 | 667 | 1642
190 | SURATGARH UNIT-8 (2X660 MW) | 660 | 2013-03-28 | 24 | 1 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2014-06-28 | 2014-06-25 | N.A. | N.A. |  | 01-04-2015 | 28-11-2015 | 15-03-2016 | 28-05-2016 | 28-09-2017 | N.A. | N.A. | 20-06-2016 | 26-09-2018 | 12-07-2016 | 06-10-2018 | 10-08-2016 | 04-03-2019 | 29-08-2016 | 07-06-2019 | N.A. | N.A. | 15-03-2015 | 28-06-2015 | N.A. | N.A. | 15-06-2016 | 09-11-2017 | 17-06-2016 | 04-09-2017 | 28-07-2016 | 18-08-2018 | 31-08-2016 | 05-02-2019 | N.A. | N.A. | 28-09-2016 | 23-03-2021 | 2016-10-28 | 30-08-2021 | 28-11-2016 | 06-10-2021 | 28-11-2016 | 07-10-2021 | 28-11-2016 | 06-10-2021 | 28-12-2016 | 31-03-2022 | 457 | 454 | 1310
191 | NABINAGAR UNIT-4 (4X250 MW ) | 250 | 2008-01-22 | 8 | 0 | 0 | 0 | 01-10-2010 | 01-10-2010 | N.A. | N.A. | N.A. | N.A. | 2012-02-29 | 2012-12-07 | 30-06-2012 | 16-09-2013 | N.A. | N.A. | 31-03-2013 | 28-04-2019 | 31-08-2013 | 04-11-2020 | N.A. | N.A. | 03-09-2013 | 09-11-2020 | 08-09-2013 | 13-11-2020 | 10-09-2013 | 23-07-2021 | 30-09-2013 | 05-08-2021 | N.A. | N.A. | 30-11-2012 | 01-05-2019 | 31-01-2013 | 25-06-2019 | 30-09-2013 | 23-07-2021 | 03-10-2013 | 15-10-2020 | 31-10-2013 | 23-07-2021 | 10-11-2013 | 24-08-2021 | N.A. | N.A. | 30-11-2013 | 20-09-2021 | 2014-02-28 | 30-10-2021 | 28-02-2014 | 10-11-2021 | 28-02-2014 | 01-12-2021 | 28-02-2014 | 04-01-2022 | 28-02-2014 | 31-03-2022 | 1499 | 1781 | 2229
192 | DARLIPALLI SG & ESP PKG UNIT-2 (2X800 MW) | 0 | 2014-02-17 | 18 | 4 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2015-08-17 | 2015-07-24 | N.A. | N.A. | 02-03-2016 | 13-07-2016 | 16-12-2016 | 04-12-2018 | 16-08-2017 | 24-10-2019 | N.A. | N.A. | 06-09-2017 | 04-01-2020 | 14-09-2017 | 08-01-2020 | 16-09-2017 | 10-12-2020 | 16-10-2017 | 24-01-2021 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 16-12-2017 | 23-03-2021 | 2018-02-16 | 24-05-2021 | 16-02-2018 | 21-07-2021 | 16-02-2018 | 01-09-2021 | 16-03-2018 | 30-09-2021 | 16-03-2018 |  | 546 | 522 | 1460
194 | BARH STG-I PCP PACKAGE (3X660 MW) UNIT-2 | 0 | 2015-05-22 | 8 | 13 | 0 | 1 | 22-05-2015 | 22-05-2015 | N.A. | N.A. | N.A. | N.A. | 2016-04-23 | 2016-08-20 | N.A. | N.A. | N.A. | N.A. | 30-05-2016 | 10-01-2021 | 22-08-2016 | 31-01-2022 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 22-11-2016 | 15-04-2022 | 2016-12-22 | 27-04-2022 | 22-12-2016 | 30-04-2022 | 22-12-2016 | 30-04-2022 | 22-12-2016 | 31-05-2022 | N.A. | N.A. | 337 | 456 | 580
195 | BARH STG-I PCP PACKAGE (3X660 MW) UNIT-3 | 0 | 2015-05-22 | 8 | 13 | 0 | 1 | 22-05-2015 | 22-05-2015 | N.A. | N.A. | N.A. | N.A. | 2016-10-23 | 2018-03-01 | N.A. | N.A. | N.A. | N.A. | 30-11-2016 |  | 22-04-2017 |  | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 22-05-2017 |  | 2017-06-22 |  | 22-06-2017 |  | 22-06-2017 |  | 22-07-2017 |  | N.A. | N.A. | 520 | 1014 | 762
196 | BHADRADRI (MANUGURU) (4X270 MW) TPS UNIT-4 | 270 | 2015-03-21 | 21 | 1 | 1 | 0 | 21-03-2015 | 21-03-2015 | N.A. | N.A. | N.A. | N.A. | 2017-11-14 | 2018-03-08 | 28-02-2018 | 21-08-2018 | N.A. | N.A. | 30-07-2018 | 16-02-2020 | 17-10-2018 | 16-04-2021 | N.A. | N.A. | 10-11-2018 | 10-07-2021 | 17-11-2018 | 13-07-2021 | 25-01-2019 | 09-09-2021 | 15-02-2019 | 23-09-2021 | N.A. | N.A. | 14-05-2018 | 24-12-2019 | 14-05-2018 | 17-12-2019 | 14-12-2018 | 01-02-2021 | 10-04-2019 | 29-01-2021 | 10-05-2019 | 05-04-2021 | 14-01-2019 | 25-05-2021 | N.A. | N.A. | 01-03-2019 | 13-10-2021 | 2019-03-12 | 02-01-2022 | 15-03-2019 | 09-01-2022 | 15-03-2019 | 09-01-2022 | 31-03-2019 | 31-01-2022 | N.A. | N.A. | 969 | 1083 | 1452
197 | BHUSAWAL UNIT-6 (1X660 MW) | 660 | 2018-12-31 | 9 | 16 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2019-11-30 | 2019-11-22 | N.A. | N.A. | 30-06-2020 | 20-01-2021 | 31-05-2021 | 30-06-2022 | 30-11-2021 | 30-07-2022 | N.A. | N.A. | 20-12-2021 | 11-07-2022 | 30-12-2021 | 15-07-2022 | 24-01-2022 | 25-08-2022 | 19-02-2022 | 15-09-2022 | N.A. | N.A. | 31-10-2020 | 31-01-2022 | 30-11-2020 | 05-02-2022 | 30-11-2021 | 05-09-2022 | 10-12-2021 | 10-09-2022 | 20-01-2022 | 10-10-2022 | 23-01-2022 | 20-10-2022 | N.A. | N.A. | 31-03-2022 | 31-10-2022 | 2022-04-30 | 30-11-2022 | 31-05-2022 | 31-12-2022 | 31-05-2022 | 31-12-2022 | 31-05-2022 | 31-12-2022 | 30-06-2022 | 28-02-2023 | 334 | 326 | 1216
198 | ENNORE SEZ (2X660 MW) UNIT-1 | 660 | 2014-09-27 | 17 | 1 | 3 | 0 | 27-09-2014 | 27-09-2014 | 27-12-2014 | 27-12-2014 | 10-01-2015 | 27-03-2017 | 2015-08-28 | 2017-09-15 | N.A. | N.A. | 28-01-2016 | 30-11-2018 | 28-12-2016 | 15-02-2020 | 30-05-2017 | 17-09-2022 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 20-06-2017 | 21-12-2022 | 15-07-2017 | 05-03-2023 | N.A. | N.A. | 27-04-2016 | 02-04-2022 | 27-05-2016 | 11-03-2022 | 27-04-2017 | 25-01-2023 | 10-06-2017 | 26-01-2023 | 12-07-2017 | 24-02-2023 | 30-07-2017 | 20-03-2023 | 12-08-2017 | 25-03-2023 | 27-09-2017 | 30-03-2023 | 2017-10-27 | 21-04-2023 | 27-10-2017 | 21-04-2023 | 27-01-2018 | 11-06-2023 | 27-11-2017 | 21-05-2023 | N.A. | N.A. | 335 | 1084 | 1126
199 | ENNORE SEZ (2X660 MW) UNIT-2 | 660 | 2014-09-27 | 17 | 1 | 3 | 0 | 27-09-2014 | 27-09-2014 | 27-12-2014 | 27-12-2014 | 10-01-2015 | 27-03-2017 | 2015-10-28 | 2018-06-08 | N.A. | N.A. | 28-03-2016 | 16-05-2019 | 27-02-2017 | 29-03-2021 | 29-07-2017 | 17-11-2022 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 20-08-2017 | 21-02-2023 | 15-09-2017 | 05-05-2023 | N.A. | N.A. | 27-06-2016 | 08-05-2022 | 27-07-2016 | 11-05-2022 | 20-06-2017 | 25-03-2023 | 10-08-2017 | 26-03-2023 | 12-09-2017 | 24-04-2023 | 30-09-2017 | 20-05-2023 | 12-10-2017 | 25-05-2023 | 27-11-2017 | 30-06-2023 | 2017-12-27 | 21-07-2023 | 27-12-2017 | 21-07-2023 | 27-03-2018 | 11-08-2023 | 27-01-2018 | 30-09-2023 | N.A. | N.A. | 396 | 1350 | 1187
203 | NABINAGAR SG PKG UNIT-3 (3X660 MW) | 0 | 2013-01-31 | 8 | 4 | 0 | 0 | 31-01-2013 | 31-01-2013 | 30-11-2013 | 28-12-2013 | N.A. | N.A. | 2015-01-31 | 2015-04-29 | N.A. | N.A. | 31-12-2015 | 31-08-2016 | 31-08-2016 | 04-07-2019 | 31-07-2017 | 11-12-2020 | N.A. | N.A. | 05-01-2017 | 04-01-2021 | 10-01-2017 | 07-01-2021 | 05-09-2017 | 22-01-2021 | 30-09-2017 | 17-02-2021 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 30-11-2017 | 28-03-2021 | 2018-01-31 | 20-01-2022 | 31-01-2018 | 25-01-2022 | 31-01-2018 | 25-01-2022 | 31-03-2018 | 24-02-2022 | N.A. | N.A. | 730 | 818 | 1826
204 | NORTH CHENNAI STAGE III (1X800 MW) | 800 | 2016-01-29 | 17 | 6 | 3 | 0 | 29-01-2016 | 29-01-2016 | N.A. | N.A. | 30-05-2016 | 13-02-2017 | 2016-11-29 | 2017-08-30 | N.A. | N.A. | 13-05-2017 | 31-07-2018 | 28-02-2018 | 31-12-2019 | 29-10-2018 | 23-02-2021 | N.A. | N.A. | 15-11-2018 | 15-03-2022 | 29-11-2018 | 30-03-2022 | 31-12-2018 | 10-05-2022 | 29-01-2019 | 25-06-2022 | N.A. | N.A. | 29-08-2017 | 14-11-2018 | 28-10-2017 | 30-01-2019 | 15-11-2018 | 01-02-2020 | 20-11-2018 | 03-11-2020 | 29-12-2018 | 17-02-2021 | 15-01-2019 | 10-05-2022 | N.A. | N.A. | 28-02-2019 | 31-08-2022 | 2019-03-28 | 30-09-2022 | 28-04-2019 | 30-10-2022 | 28-04-2019 | 30-09-2022 | 28-04-2019 | 30-10-2022 | N.A. | N.A. | 305 | 579 | 1154
205 | NORTH KARANPURA UNIT-1 (3X660 MW) | 660 | 2014-02-28 | 12 | 1 | 0 | 1 | 28-02-2014 | 20-10-2014 | N.A. | N.A. | 28-03-2014 | 08-01-2015 | 2015-06-28 | 2016-04-29 | N.A. | N.A. | 28-12-2015 | 12-08-2017 | 28-11-2016 | 05-01-2019 | 28-06-2017 | 24-12-2020 | N.A. | N.A. | 28-05-2017 | 10-11-2020 | 28-06-2017 | 12-11-2020 | 28-07-2017 | 25-01-2021 | 28-08-2017 | 08-02-2021 | N.A. | N.A. | 28-03-2016 | 27-12-2018 | 28-05-2016 | 25-11-2017 | 28-04-2017 | 28-08-2019 | 28-05-2017 | 17-07-2020 | 28-06-2017 | 16-10-2020 | 28-07-2017 | 25-01-2021 | N.A. | N.A. | 28-10-2017 | 26-03-2022 | 2017-11-28 | 27-05-2022 | 28-11-2017 | 27-05-2022 | 28-11-2017 | 27-05-2022 | 28-02-2018 | 27-05-2022 | N.A. | N.A. | 485 | 791 | 1369
206 | NORTH KARANPURA UNIT-2 (3X660 MW) | 660 | 2014-02-28 | 12 | 1 | 0 | 1 | 28-02-2014 | 28-02-2014 | N.A. | N.A. | N.A. | N.A. | 2015-12-28 | 2016-07-27 | N.A. | N.A. | 28-06-2016 | 25-10-2017 | 28-05-2017 | 22-10-2019 | 28-12-2017 | 30-11-2022 | N.A. | N.A. | 28-11-2017 | 23-11-2022 | 28-12-2017 | 30-12-2022 | 28-01-2018 | 02-01-2023 | 28-02-2018 | 24-01-2023 | N.A. | N.A. | 28-09-2016 | 03-09-2020 | 28-11-2016 | 31-01-2018 | 28-10-2017 | 05-11-2021 | 28-11-2017 | 21-09-2022 | 28-12-2017 | 25-10-2022 | 28-01-2018 | 24-11-2022 | N.A. | N.A. | 28-04-2018 | 30-05-2023 | 2018-05-28 | 24-06-2023 | 28-05-2018 | 24-06-2023 | 28-05-2018 | 25-07-2023 | 28-07-2018 | 25-07-2023 | N.A. | N.A. | 668 | 880 | 1550
207 | NORTH KARANPURA UNIT-3 (3X660 MW) | 660 | 2014-02-28 | 12 | 1 | 0 | 1 | 28-02-2014 | 28-02-2014 | N.A. | N.A. | N.A. | N.A. | 2016-06-28 | 2017-06-28 | N.A. | N.A. | 28-12-2016 | 20-01-2018 | 28-11-2017 | 18-11-2022 | 28-06-2018 | 24-05-2023 | N.A. | N.A. | 28-05-2018 | 20-04-2023 | 28-06-2018 | 24-05-2023 | 28-07-2018 | 22-06-2023 | 28-08-2018 | 20-07-2023 | N.A. | N.A. | 28-03-2017 | 24-02-2022 | 28-05-2017 | 23-03-2022 | 28-04-2018 | 28-12-2022 | 28-05-2018 | 06-04-2023 | 28-06-2018 | 24-05-2023 | 28-07-2018 | 23-06-2023 | N.A. | N.A. | 28-10-2018 | 27-12-2023 | 2018-11-28 | 25-01-2024 | 28-11-2018 | 25-01-2024 | 28-11-2018 | 23-02-2024 | 28-01-2019 | 23-02-2024 | N.A. | N.A. | 851 | 1216 | 1734
208 | NTPC TELANGANA (KARIMNAGAR) SG PKG. UNIT-1 (2X800 MW) | 0 | 2016-02-05 | 21 | 12 | 1 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2017-04-05 | 2017-12-28 | N.A. | N.A. | 04-01-2018 | 09-03-2019 | 05-11-2018 | 05-11-2021 | 15-03-2019 | 10-05-2022 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 05-05-2019 | 05-06-2022 | 05-06-2019 | 30-06-2022 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 05-08-2019 | 25-07-2022 | 2019-10-05 | 27-07-2022 | 05-11-2019 | 27-07-2022 | N.A. | N.A. | 05-11-2019 | 26-08-2022 | 05-12-2019 | 30-09-2022 | 425 | 692 | 1338
209 | NTPC TELANGANA (KARIMNAGAR) SG PKG. UNIT-2 (2X800 MW) | 0 | 2016-02-05 | 21 | 12 | 1 | 1 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2017-10-05 | 2017-12-28 | N.A. | N.A. | 04-07-2018 | 22-05-2019 | 05-05-2019 | 31-03-2022 | 15-09-2019 | 30-06-2022 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 05-11-2019 | 05-07-2022 | 05-12-2019 | 31-07-2022 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 05-02-2020 | 25-08-2022 | 2020-04-05 | 31-08-2022 | 05-05-2020 | 31-08-2022 | N.A. | N.A. | 05-05-2020 | 30-09-2022 | 05-06-2020 | 31-10-2022 | 608 | 692 | 1521
210 | PANKI TPS (1X660 MW) | 660 | 2018-03-31 | 13 | 1 | 2 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2019-04-30 | 2019-04-21 | N.A. | N.A. | 30-10-2019 | 23-02-2020 | 30-09-2020 | 17-12-2021 | 28-02-2021 | 30-06-2022 | N.A. | N.A. | 03-03-2021 | 15-07-2022 | 10-03-2021 | 23-07-2022 | 09-04-2021 | 26-08-2022 | 30-04-2021 | 25-09-2022 | N.A. | N.A. | 28-02-2020 | 28-08-2021 | 30-04-2020 | 04-10-2021 | 31-01-2021 | 10-07-2022 | 01-02-2021 | 06-04-2022 | 17-04-2021 | 30-09-2022 | 17-05-2021 | 20-10-2022 | N.A. | N.A. | 30-05-2021 | 28-10-2022 | 2021-06-30 | 31-12-2022 | 31-07-2021 | 31-01-2023 | 30-09-2021 | 31-01-2023 | 30-09-2021 | 31-03-2023 | 30-01-2022 | 30-06-2023 | 395 | 386 | 1187
211 | PATRATU (3X800 MW) UNIT-1 | 800 | 2018-03-08 | 12 | 1 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2019-05-08 | 2019-08-27 | N.A. | N.A. | 02-02-2020 | 18-03-2021 | 08-01-2021 | 30-09-2022 | 08-07-2021 | 30-04-2023 | N.A. | N.A. | 20-07-2021 | 20-05-2023 | 30-07-2021 | 30-05-2023 | 08-08-2021 | 08-06-2023 | 08-09-2021 | 08-07-2023 | N.A. | N.A. | 08-03-2020 | 31-03-2022 | 08-06-2020 | 31-03-2022 | 08-05-2021 | 28-02-2023 | 08-06-2021 | 31-03-2023 | 08-07-2021 | 30-04-2023 | 08-08-2021 | 31-05-2023 | N.A. | N.A. | 08-11-2021 | 30-01-2024 | 2021-12-08 | 15-02-2024 | 08-12-2021 | 28-02-2024 | 08-12-2021 | 30-03-2024 | 08-02-2022 | 30-03-2024 | 08-03-2022 | 30-04-2024 | 426 | 537 | 1371
212 | PATRATU (3X800 MW) UNIT-2 | 800 | 2018-03-08 | 12 | 1 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2019-11-08 | 2019-12-30 | N.A. | N.A. | 02-08-2020 | 13-05-2021 | 08-07-2021 | 30-11-2022 | 08-01-2022 | 30-06-2023 | N.A. | N.A. | 15-01-2022 | 15-07-2023 | 23-01-2022 | 25-07-2023 | 08-02-2022 | 08-08-2023 | 08-03-2022 | 08-09-2023 | N.A. | N.A. | 08-09-2020 | 31-05-2022 | 08-12-2020 | 31-05-2022 | 08-11-2021 | 30-04-2023 | 08-12-2021 | 31-05-2023 | 08-01-2022 | 30-06-2023 | 08-02-2022 | 31-07-2023 | N.A. | N.A. | 08-05-2022 | 30-03-2024 | 2022-06-08 | 25-04-2024 | 08-06-2022 | 30-04-2024 | 08-06-2022 | 31-05-2024 | 08-08-2022 | 31-05-2024 | 08-09-2022 | 29-06-2024 | 610 | 662 | 1553
213 | PATRATU (3X800 MW) UNIT-3 | 800 | 2018-03-08 | 12 | 1 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2020-05-08 | 2021-01-22 | N.A. | N.A. | 02-02-2021 | 31-01-2022 | 08-01-2022 | 31-03-2023 | 08-07-2022 | 31-10-2023 | N.A. | N.A. | 13-07-2022 | 13-12-2023 | 20-07-2022 | 31-12-2023 | 25-07-2022 | 08-01-2024 | 08-09-2022 | 31-01-2024 | N.A. | N.A. | 08-03-2021 | 30-09-2022 | 08-06-2021 | 30-09-2022 | 08-05-2022 | 30-09-2023 | 08-07-2022 | 31-10-2023 | 08-07-2022 | 30-11-2023 | 08-08-2022 | 31-12-2023 | N.A. | N.A. | 08-11-2022 | 31-05-2024 | 2022-12-08 | 29-06-2024 | 08-12-2022 | 31-10-2024 | 08-12-2022 | 31-10-2024 | 08-02-2023 | 31-10-2024 | 08-03-2023 | 30-11-2024 | 792 | 1051 | 1736
214 | SAGARDIGHI TPEP UNIT-5 (1X660 MW) | 660 | 2020-07-01 | 0 | 1 | 0 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2021-04-29 | 2021-04-28 | N.A. | N.A. | 30-12-2021 | 28-02-2022 | 30-12-2022 | 01-10-2022 | 13-06-2023 | 15-04-2023 | N.A. | N.A. | 14-06-2023 | 15-04-2023 | 28-06-2023 | 30-04-2023 | 13-07-2023 | 10-05-2023 | 12-08-2023 | 24-06-2023 | N.A. | N.A. | 03-03-2022 | 04-02-2022 | 02-05-2022 | 23-03-2022 | 01-06-2023 | 09-04-2023 | 28-03-2023 | 16-02-2023 | 17-05-2023 | 02-04-2023 | 11-07-2023 | 04-05-2023 | N.A. | N.A. | 01-09-2023 | 15-07-2023 | 2023-12-15 | 15-10-2023 | 30-12-2023 | 30-10-2023 | 01-01-2024 | 30-10-2023 | 01-01-2024 | 30-10-2023 | 01-04-2024 | 01-04-2024 | 302 | 301 | 1262
215 | ROURKELA TPP (1X250 MW) | 250 | 2016-05-11 | 18 | 1 | 0 | 0 | 11-05-2016 | 11-05-2016 | N.A. | N.A. | N.A. | N.A. | 2017-02-10 | 2017-05-29 | 08-06-2017 | 04-11-2017 | N.A. | N.A. | 08-01-2018 | 08-09-2018 | 10-04-2018 | 19-11-2020 | N.A. | N.A. | 06-05-2018 | 14-01-2021 | 10-05-2018 | 17-01-2021 | 25-05-2018 | 10-04-2021 | 10-06-2018 | 20-04-2021 | N.A. | N.A. | 10-09-2017 | 18-10-2018 | 10-09-2017 | 20-12-2018 | 10-05-2018 | 26-03-2021 | 16-05-2018 | 21-01-2021 | 10-06-2018 | 06-03-2021 | 10-07-2018 | 31-03-2021 | N.A. | N.A. | 10-08-2018 | 06-09-2021 | 2018-09-10 | 08-01-2022 | 10-10-2018 | 31-01-2022 | 10-10-2018 | 31-01-2022 | 10-10-2018 | 28-02-2022 | N.A. | N.A. | 275 | 383 | 852
216 | TUTICORIN STG IV (1X525 MW) | 525 | 2016-02-24 | 17 | 0 | 3 | 0 | 24-02-2016 | 24-02-2016 | N.A. | N.A. | N.A. | N.A. | 2016-11-06 | 2016-12-15 | 05-04-2017 | 13-08-2017 | N.A. | N.A. | 20-01-2018 | 20-10-2018 | 17-09-2018 | 20-10-2020 | N.A. | N.A. | 30-09-2018 | 28-10-2020 | 09-10-2018 | 02-11-2020 | 20-10-2018 | 12-01-2021 | 18-11-2018 | 15-02-2021 | N.A. | N.A. | 25-08-2017 | 08-09-2017 | 01-10-2017 | 21-02-2018 | 27-07-2018 | 31-12-2020 | 12-08-2018 | 30-12-2019 | 01-10-2018 | 25-08-2020 | 25-10-2018 | 12-01-2021 | N.A. | N.A. | 13-02-2018 | 21-09-2021 | 2019-01-08 | 15-10-2021 | 08-01-2019 | 30-11-2021 | 08-01-2019 | 15-01-2022 | 08-01-2019 | 31-01-2022 | N.A. | N.A. | 256 | 295 | 1049
217 | UDANGUDI STPP UNIT-1 (2X660 MW) | 660 | 2017-12-07 | 25 | 1 | 3 | 0 | 07-12-2017 | 07-12-2017 | N.A. | N.A. | 20-04-2018 | 07-02-2019 | 2018-09-27 | 2019-09-20 | N.A. | N.A. | 09-02-2019 | 26-06-2021 | 27-02-2020 | 27-04-2022 | 09-07-2020 | 10-11-2022 | N.A. | N.A. | 23-07-2020 | 22-10-2022 | 30-07-2020 | 30-11-2022 | 13-08-2020 | 12-01-2023 | 03-09-2020 | 22-02-2023 | N.A. | N.A. | 15-08-2019 | 05-05-2022 | N.A. | N.A. | 30-07-2020 | 06-02-2023 | 30-07-2020 | 10-02-2023 | 17-09-2020 | 20-03-2023 | 15-10-2020 | 28-03-2023 | N.A. | N.A. | 10-12-2020 | 12-04-2023 | 2021-01-07 | 25-04-2023 | 07-01-2021 | 25-04-2023 | 15-01-2021 | 12-05-2023 | 25-02-2021 | 25-05-2023 | 08-04-2021 | 20-06-2023 | 294 | 652 | 1127
218 | UDANGUDI STPP UNIT-2 (2X660 MW) | 660 | 2017-12-07 | 25 | 1 | 3 | 0 | 07-12-2017 | 07-12-2017 | N.A. | N.A. | 20-06-2018 | 30-01-2019 | 2018-11-27 | 2019-09-16 | N.A. | N.A. | 09-04-2019 | 18-06-2021 | 27-04-2020 | 20-05-2022 | 09-09-2020 | 24-12-2022 | N.A. | N.A. | 23-09-2020 | 10-01-2023 | 30-09-2020 | 18-01-2023 | 13-10-2020 | 02-02-2023 | 03-11-2020 | 08-03-2023 | N.A. | N.A. | 15-10-2019 | 08-06-2022 | N.A. | N.A. | 30-09-2020 | 05-03-2023 | 01-10-2020 | 10-03-2023 | 17-11-2020 | 12-04-2023 | 15-12-2020 | 18-04-2023 | N.A. | N.A. | 10-02-2021 | 25-04-2023 | 2021-03-07 | 12-05-2023 | 07-03-2021 | 12-05-2023 | 15-03-2021 | 20-05-2023 | 25-04-2021 | 28-05-2023 | 08-06-2021 | 30-06-2023 | 355 | 648 | 1186
219 | UPPUR (2X800 MW) UNIT-1 | 800 | 2017-08-03 | 17 | 6 | 3 | 0 | 03-08-2017 | 03-08-2017 | N.A. | N.A. | N.A. | N.A. | 2018-03-29 | 2020-07-10 | N.A. | N.A. | 08-09-2018 |  | 01-08-2019 |  | 13-02-2020 |  | N.A. | N.A. | 12-03-2020 |  | 19-03-2020 |  | 02-04-2020 |  | 16-04-2020 |  | N.A. | N.A. | 11-04-2019 |  | 25-05-2019 |  | 13-02-2020 |  | 19-03-2020 |  | 16-04-2020 |  | 02-04-2020 |  | N.A. | N.A. | 07-05-2020 |  | 2020-06-03 |  | 06-06-2020 |  | 06-06-2020 |  | 06-07-2020 |  | 02-02-2021 |  | 238 | 1072 | 1035
220 | UPPUR (2X800 MW) UNIT-2 | 800 | 2017-08-03 | 17 | 6 | 3 | 0 | 03-08-2017 | 03-08-2017 | N.A. | N.A. | N.A. | N.A. | 2018-05-14 | 2019-09-25 | N.A. | N.A. | 14-10-2018 |  | 01-10-2019 |  | 14-04-2020 |  | N.A. | N.A. | 13-05-2020 |  | 20-05-2020 |  | 31-05-2020 |  | 14-06-2020 |  | N.A. | N.A. | 09-06-2019 |  | 23-06-2019 |  | 14-04-2020 |  | 21-04-2020 |  | 21-05-2020 |  | 31-05-2020 |  | N.A. | N.A. | 06-07-2020 |  | 2020-07-31 |  | 03-08-2020 |  | 03-08-2020 |  | 03-09-2020 |  | 02-02-2021 |  | 284 | 783 | 1093
221 | VIJAYAWADA DR NTTPS STAGE-V (1X800MW) | 800 | 2015-12-15 | 6 | 0 | 3 | 0 | 15-12-2015 | 15-12-2015 | N.A. | N.A. | N.A. | N.A. | 2016-10-25 | 2017-05-22 | N.A. | N.A. | 06-04-2017 | 27-12-2017 | 27-03-2018 | 03-03-2019 | 11-12-2018 | 28-12-2019 | N.A. | N.A. | 12-12-2018 | 02-03-2020 | 25-12-2018 | 13-03-2020 | 27-12-2018 | 03-04-2021 | 20-01-2019 | 01-06-2021 | N.A. | N.A. | 26-08-2017 | 22-08-2018 | 23-11-2017 | 03-10-2018 | 14-11-2018 | 05-06-2020 | 30-11-2018 | 17-06-2020 | 14-01-2019 | 18-11-2020 | 14-02-2019 | 22-02-2021 | N.A. | N.A. | 14-03-2019 | 07-12-2021 | 2019-04-30 | 28-02-2022 | 14-06-2019 | 28-02-2022 | 14-06-2019 | 28-02-2022 | 14-06-2019 | 28-02-2022 | N.A. | N.A. | 315 | 524 | 1232
227 | CHANDWA PH-I UNIT-1 (2X270MW ) | 270 | 2010-01-07 | 12 | 0 | 0 | 0 | N.A. | N.A. | 31-08-2010 | 31-08-2010 | N.A. | N.A. | 2010-10-31 | 2010-10-05 | 30-04-2011 | 03-04-2011 | N.A. | N.A. | 30-11-2011 | 26-12-2011 | 30-04-2012 |  | N.A. | N.A. | 05-05-2012 |  | 15-05-2012 |  | 01-06-2012 |  | 30-06-2012 |  | N.A. | N.A. | 31-05-2011 | 26-05-2011 | 31-07-2011 | 27-07-2011 | 29-02-2012 |  | 01-03-2012 |  | 15-03-2012 |  | 31-03-2012 |  | N.A. | N.A. | 07-07-2012 |  | 2012-09-07 |  | N.A. | N.A. | 07-09-2012 |  | 07-09-2012 |  | N.A. | N.A. | 297 | 271 | 974
228 | CHANDWA PH-I UNIT-2 (2X270MW ) | 270 | 2010-01-07 | 12 | 0 | 0 | 0 | N.A. | N.A. | 31-08-2010 | 31-08-2010 | N.A. | N.A. | 2011-01-31 | 2010-12-19 | 31-07-2011 | 19-07-2011 | N.A. | N.A. | 29-02-2012 | 24-08-2012 | 31-07-2012 |  | N.A. | N.A. | 05-08-2012 |  | 16-08-2012 |  | 25-08-2012 |  | 30-09-2012 |  | N.A. | N.A. | 31-08-2011 | 24-08-2011 | 31-10-2011 | 18-09-2011 | 31-05-2012 |  | 01-06-2012 |  | 15-06-2012 |  | 30-06-2012 |  | N.A. | N.A. | 07-10-2012 |  | 2012-12-07 |  | N.A. | N.A. | 07-12-2012 |  | 07-12-2012 |  | N.A. | N.A. | 389 | 346 | 1065
229 | CHANDWA PH-II UNIT-3 (2X270MW ) | 270 | 2010-06-29 | 12 | 0 | 0 | 0 | 29-06-2010 | 29-06-2010 | 31-01-2011 | 31-08-2010 | N.A. | N.A. | 2011-03-31 | 2011-06-21 | 30-09-2011 | 21-12-2011 | N.A. | N.A. | 30-04-2012 |  | 30-09-2012 |  | N.A. | N.A. | 05-10-2012 |  | 20-10-2012 |  | 30-10-2012 |  | 30-11-2012 |  | N.A. | N.A. | 31-10-2011 |  | 31-12-2011 |  | 31-07-2012 |  | 14-08-2012 |  | 31-08-2012 |  | 31-08-2012 |  | N.A. | N.A. | 29-12-2012 |  | 2013-02-28 |  | N.A. | N.A. | 28-02-2013 |  | 28-02-2013 |  | N.A. | N.A. | 275 | 357 | 975
230 | CHANDWA PH-II UNIT-4 (2X270MW ) | 270 | 2010-06-29 | 12 | 0 | 0 | 0 | 29-06-2010 | 29-06-2010 | 31-01-2011 | 31-08-2010 | N.A. | N.A. | 2011-06-30 | 2011-07-26 | 31-12-2011 | 30-04-2012 | N.A. | N.A. | 31-07-2012 |  | 31-12-2012 |  | N.A. | N.A. | 05-01-2013 |  | 10-01-2013 |  | 01-02-2013 |  | 28-02-2013 |  | N.A. | N.A. | 31-01-2012 |  | 31-03-2012 |  | 31-10-2012 |  | 15-11-2012 |  | 30-11-2012 |  | 30-11-2012 |  | N.A. | N.A. | 29-03-2013 |  | 2013-05-29 |  | N.A. | N.A. | 29-05-2013 |  | 29-05-2013 |  | N.A. | N.A. | 366 | 392 | 1065
231 | AMRAVATI TPP PH-II UNIT-6 (5 X 270 MW) | 270 | 2010-10-11 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-06-11 | 2011-11-23 | 11-10-2011 |  | N.A. | N.A. | 11-07-2012 |  | 11-10-2012 |  | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 11-02-2012 |  | N.A. | N.A. | 11-12-2012 |  | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 11-01-2013 |  | 2013-04-11 |  | N.A. | N.A. | 11-04-2013 |  | 11-04-2013 |  | N.A. | N.A. | 243 | 408 | 913
232 | AMRAVATI TPP PH-II UNIT-7 (5 X 270 MW) | 270 | 2010-10-11 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-08-11 | 2012-01-31 | 11-12-2011 |  | N.A. | N.A. | 11-09-2012 |  | 11-12-2012 |  | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 11-04-2012 |  | N.A. | N.A. | 11-02-2013 |  | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 11-03-2013 |  | 2013-06-11 |  | N.A. | N.A. | 11-06-2013 |  | 11-06-2013 |  | N.A. | N.A. | 304 | 477 | 974
237 | MPCL MALIBRAHAMANI UNIT-1 (2 X 525 MW) | 525 | 2009-06-12 | 18 | 0 | 3 | 0 | N.A. | N.A. | 10-11-2009 | 10-11-2009 | N.A. | N.A. | 2010-03-13 | 2011-08-03 | 10-08-2010 | 24-03-2012 | N.A. | N.A. | 14-06-2011 | 03-04-2013 | 05-03-2012 |  | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 04-04-2012 |  | 03-05-2012 |  | N.A. | N.A. | 08-04-2011 | 10-10-2012 | 08-06-2011 | 28-01-2013 | 24-01-2012 |  | 13-02-2012 |  | 13-03-2012 |  | 11-04-2012 |  | N.A. | N.A. | 07-05-2012 |  | 2012-07-05 |  | N.A. | N.A. | 05-07-2012 |  | 05-07-2012 |  | N.A. | N.A. | 274 | 782 | 1119
238 | MPCL MALIBRAHAMANI UNIT-2 (2 X 525 MW) | 525 | 2009-06-12 | 18 | 0 | 3 | 0 | N.A. | N.A. | 10-11-2009 | 10-11-2009 | N.A. | N.A. | 2010-06-13 | 2011-10-10 | 10-11-2010 | 20-07-2012 | N.A. | N.A. | 14-09-2011 |  | 05-06-2012 |  | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 04-07-2012 |  | 03-08-2012 |  | N.A. | N.A. | 08-07-2011 | 07-02-2013 | 08-09-2011 |  | 23-04-2012 |  | 13-05-2012 |  | 13-06-2012 |  | 10-07-2012 |  | N.A. | N.A. | 05-08-2012 |  | 2012-10-03 |  | N.A. | N.A. | 03-10-2012 |  | 03-10-2012 |  | N.A. | N.A. | 366 | 850 | 1209
243 | NASIK UNIT # 10 (5 X 270 MW) (PH-II) | 270 | 2010-10-08 | 3 | 0 | 1 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-06-08 | 2011-09-28 | 08-10-2011 |  | N.A. | N.A. |  |  | 07-10-2012 |  | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 06-02-2012 |  | N.A. | N.A. | 06-12-2012 |  | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 08-03-2014 |  | 2014-07-08 |  | N.A. | N.A. | 08-07-2014 |  | 08-07-2014 |  | N.A. | N.A. | 243 | 355 | 1369
246 | SURANA TPP UNIT-1 (2X210 MW) | 210 | 2010-03-30 | 15 | 0 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-01-30 | 2011-09-08 | 29-08-2011 | 10-05-2012 | N.A. | N.A. | 29-05-2012 |  | 29-09-2012 |  | N.A. | N.A. | [6 empty] | 29-10-2012 |  | N.A. | N.A. | 29-11-2011 |  | 29-12-2011 |  | 29-07-2012 |  |  |  | 29-09-2012 |  | 29-10-2012 |  | 15-11-2012 |  | 29-11-2012 |  | 2013-01-29 |  | N.A. | N.A. | 29-01-2013 |  | 29-01-2013 |  | 29-01-2013 |  | 306 | 527 | 1036
247 | SURANA TPP UNIT-2 (2X210 MW) | 210 | 2010-03-30 | 15 | 0 | 3 | 0 | N.A. | N.A. | N.A. | N.A. | N.A. | N.A. | 2011-04-30 | 2012-04-24 | 29-11-2011 | 23-09-2012 | N.A. | N.A. | 29-08-2012 |  | 29-12-2012 |  | N.A. | N.A. | [6 empty] | 29-01-2013 |  | N.A. | N.A. | 29-02-2012 |  | 29-03-2012 |  | 29-10-2012 |  |  |  | 29-12-2012 |  | 29-01-2013 |  | 15-02-2013 |  | 28-02-2013 |  | 2013-04-29 |  | N.A. | N.A. | 29-04-2013 |  | 29-04-2013 |  | 29-04-2013 |  | 396 | 756 | 1126
248 | VISA RAIGARH TPP UNIT-1 (2X600 MW) | 600 | 2010-08-09 | 2 | 0 | 1 | 0 | 09-08-2010 | 09-08-2010 | N.A. | N.A. | N.A. | N.A. | 2011-05-20 | 2011-09-30 |  |  | N.A. | N.A. |  |  |  |  | N.A. | N.A. | [8 empty] | N.A. | N.A. |  |  | N.A. | N.A. | [6 empty] | N.A. | N.A. | N.A. | N.A. |  |  |  |  | N.A. | N.A. |  |  |  |  | N.A. | N.A. | 284 | 417